## Cover
Remediation Plan - CAPA For Compliance Assessment at CSL Behring, Broadmeadows, Australia

## CAPAs
Site | SystemID | FID | CapaSubTaskID | System # | CAPA Subtask | CAPA Subtask description | System / Generic | CSL effort | PQE effort | Possible PQE Support | CSL Workgroup | Accountable action owner | Responsible owner | Deadline | Status | Comment
BRN | BRN-LAS_052 | BRN-LAS_052-S1-1-1 | BRN-LAS_052-S1-1-1-1.1-System | LAS_052 | 1.1 | Change Control Management including impact assessment | System | 0.5 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_052 | BRN-LAS_052-S1-1-1 | BRN-LAS_052-S1-1-1-1.2-System | LAS_052 | 1.2 | Update the application SW in order to configure unique and personal accounts. If it is not possible to configure personal account within application SW, implement a proper user management within OS accounts | System | 3 | 3 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_052 | BRN-LAS_052-S1-1-1 | BRN-LAS_052-S1-1-1-1.3-System | LAS_052 | 1.3 | Test and document the configuration changes or procedural changes | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_052 | BRN-LAS_052-S1-1-1 | BRN-LAS_052-S1-1-1-1.4-System | LAS_052 | 1.4 | Issue and approve a User List | System | 0.1 | 0.5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_052 | BRN-LAS_052-S1-1-1 | BRN-LAS_052-S1-1-1-1.5-System | LAS_052 | 1.5 | Update relevant SOPs and periodically review the User List according to procedure | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_052 | BRN-LAS_052-S2-2-2 | BRN-LAS_052-S2-2-2-2.1-System | LAS_052 | 2.1 | Investigate with the supplier if it is possible to implement a proper configuration of user groups with segregation of duties | System | 1 | 0 | NO | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_052 | BRN-LAS_052-S2-2-2 | BRN-LAS_052-S2-2-2-2.2-System | LAS_052 | 2.2 | Change Control Management including impact assessment | System | 0.5 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_052 | BRN-LAS_052-S2-2-2 | BRN-LAS_052-S2-2-2-2.3-System | LAS_052 | 2.3 | Configure 3 user groups and define the role of each user | System | 1 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_052 | BRN-LAS_052-S2-2-2 | BRN-LAS_052-S2-2-2-2.4-System | LAS_052 | 2.4 | Configure user privileges according to a proper segregation of duties | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_052 | BRN-LAS_052-S2-2-2 | BRN-LAS_052-S2-2-2-2.5-System | LAS_052 | 2.5 | Test and document the configuration changes | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_052 | BRN-LAS_052-S2-2-2 | BRN-LAS_052-S2-2-2-2.6-System | LAS_052 | 2.6 | Update relevant SOP | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_052 | BRN-LAS_052-S3-3-3 | BRN-LAS_052-S3-3-3-3.1-System | LAS_052 | 3.1 | Investigate with the supplier if it is possible to upgrade the software to grant proper security features for user access | System | 1 | 0 | NO | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_052 | BRN-LAS_052-S3-3-3 | BRN-LAS_052-S3-3-3-3.2-Generic | LAS_052 | 3.2 | Define the Password features in an approved procedure | Generic | 1 | 3 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_052 | BRN-LAS_052-S3-3-3 | BRN-LAS_052-S3-3-3-3.3-System | LAS_052 | 3.3 | Personnel training to access the system | System | 0.5 | 0.5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_052 | BRN-LAS_052-S3-3-3 | BRN-LAS_052-S3-3-3-3.4-System | LAS_052 | 3.4 | Update relevant SOP | System | 0.2 | 0.2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_052 | BRN-LAS_052-S4-2-4 | BRN-LAS_052-S4-2-4-4.1-System | LAS_052 | 4.1 | Issue a User List with the actual status of users | System | 0.1 | 0.5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_052 | BRN-LAS_052-S4-2-4 | BRN-LAS_052-S4-2-4-4.2-Generic | LAS_052 | 4.2 | Issue and approve a Periodic Review for User List | Generic | 0.1 | 0.5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_052 | BRN-LAS_052-S4-2-4 | BRN-LAS_052-S4-2-4-4.3-System | LAS_052 | 4.3 | Execute Periodic Review | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_052 | BRN-LAS_052-S4-2-4 | BRN-LAS_052-S4-2-4-4.4-System | LAS_052 | 4.4 | Setup of periodic task in relevant system | System | 0.2 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_052 | BRN-LAS_052-I1-1-5 | BRN-LAS_052-I1-1-5-5.1-System | LAS_052 | 5.1 | Change Control Management including impact assessment | System | 0.5 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_052 | BRN-LAS_052-I1-1-5 | BRN-LAS_052-I1-1-5-5.2-System | LAS_052 | 5.2 | Implement a process of automatic data backup | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_052 | BRN-LAS_052-I1-1-5 | BRN-LAS_052-I1-1-5-5.3-Generic | LAS_052 | 5.3 | If automatic backup its not possible, document manual backups of system data with a proper frequency to be defined in a dedicated procedure | Generic | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_052 | BRN-LAS_052-I1-1-5 | BRN-LAS_052-I1-1-5-5.4-System | LAS_052 | 5.4 | Test and document the implemented changes | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_052 | BRN-LAS_052-I1-1-5 | BRN-LAS_052-I1-1-5-5.5-System | LAS_052 | 5.5 | Update relevant SOP | System | 0.2 | 0.2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_052 | BRN-LAS_052-T1-1-6 | BRN-LAS_052-T1-1-6-6.1-System | LAS_052 | 6.1 | Change Control Management including impact assessment | System | 0.5 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_052 | BRN-LAS_052-T1-1-6 | BRN-LAS_052-T1-1-6-6.2-System | LAS_052 | 6.2 | Update Audit Trail functionality in order to track and record modifications to ER | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_052 | BRN-LAS_052-T1-1-6 | BRN-LAS_052-T1-1-6-6.3-Generic | LAS_052 | 6.3 | If Audit Trail is not compliant (e.g. does not track modifications to ER), implement a paper based management of system regulated input records (i.e. methods) with the following paper procedures: -user access log -verification log to be used by the Users before launching a method -traceability log to be used by the system administrators when changing a method | Generic | 2 | 3 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_052 | BRN-LAS_052-T1-1-6 | BRN-LAS_052-T1-1-6-6.4-System | LAS_052 | 6.4 | Test and document that Audit Trail is fully compliant or, in case of paper Audit Trail, that the personnel is trained to use it | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_052 | BRN-LAS_052-T1-1-6 | BRN-LAS_052-T1-1-6-6.5-System | LAS_052 | 6.5 | Update relevant SOP | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_052 | BRN-LAS_052-T3-2-7 | BRN-LAS_052-T3-2-7-7.1-Generic | LAS_052 | 7.1 | If there is no Audit Trail Process fully compliant, issue and approve a fully compliant Audit Trail Review Working Instruction | Generic | 1 | 3 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_052 | BRN-LAS_052-T3-2-7 | BRN-LAS_052-T3-2-7-7.2-System | LAS_052 | 7.2 | Execute Audit Trail Review Working Instruction: - perform Data Assessment for Electronic Records managed by the system - update Operational Method SOP (Methods/Instrument) - update test documentation | System | 0.5 | 2.5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_052 | BRN-LAS_052-T3-2-7 | BRN-LAS_052-T3-2-7-7.3-System | LAS_052 | 7.3 | Setup of periodic task | System | 0.2 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_052 | BRN-LAS_052-T4-2-8 | BRN-LAS_052-T4-2-8-8.1-System | LAS_052 | 8.1 | Implement a process of automatic data transfer | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_052 | BRN-LAS_052-T4-2-8 | BRN-LAS_052-T4-2-8-8.2-Generic | LAS_052 | 8.2 | If automatic backup its not possible, document manual transfers of system data with a proper frequency to be defined in a dedicated procedure | Generic | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_052 | BRN-LAS_052-T4-2-8 | BRN-LAS_052-T4-2-8-8.3-System | LAS_052 | 8.3 | Test and document the implemented changes | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_052 | BRN-LAS_052-T4-2-8 | BRN-LAS_052-T4-2-8-8.4-System | LAS_052 | 8.4 | Update relevant SOP | System | 0.2 | 0.2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_052 | BRN-LAS_052-VD1-1-9 | BRN-LAS_052-VD1-1-9-9.1-System | LAS_052 | 9.1 | Review the Computer System Validation in place and identify the missing/incomplete validation documents or testing protocols | System | 1 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started | Validation Plan not present, Traceability Matrix present, VR (called Qualifizierungsbericht, eng. Qualification report) does not address the procedures., URS document present but it is missing Functional Process Requirements, Access Control and Security Roles partially covered, no reference to regulatory rules (e.g. Annex11 coverage), Configuration Specification not identified., RA is identified but does not cover the risk associated to Regulatory Requirements and ERES definition., IQ/OQ has been identified, but the level of detail is not consistent with DI expectations, i.e. Security/Integrity/Traceability verifications. Missing tests for documental checks (e.g. Users List, SOPs, etc.), functional checks (Part 11 and Annex 11 verifications), PQ protocol is not identified
BRN | BRN-LAS_052 | BRN-LAS_052-VD1-1-9 | BRN-LAS_052-VD1-1-9-9.2-System | LAS_052 | 9.2 | Issue and approve the missing validation documentation | System | 2 | 3 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_052 | BRN-LAS_052-VD1-1-9 | BRN-LAS_052-VD1-1-9-9.3-System | LAS_052 | 9.3 | Perform and document the missing/incomplete tests | System | 3 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_052 | BRN-LAS_052-VD1-1-9 | BRN-LAS_052-VD1-1-9-9.4-System | LAS_052 | 9.4 | Assure the Traceability of the testing with coded requirements against coded test and update the documentation accordingly | System | 2 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_053 | BRN-LAS_053-S1-1-1 | BRN-LAS_053-S1-1-1-1.1-System | LAS_053 | 1.1 | Change Control Management including impact assessment | System | 0.5 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_053 | BRN-LAS_053-S1-1-1 | BRN-LAS_053-S1-1-1-1.2-System | LAS_053 | 1.2 | Update the application SW in order to configure unique and personal accounts. If it is not possible to configure personal account within application SW, implement a proper user management within OS accounts | System | 3 | 3 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_053 | BRN-LAS_053-S1-1-1 | BRN-LAS_053-S1-1-1-1.3-System | LAS_053 | 1.3 | Test and document the configuration changes or procedural changes | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_053 | BRN-LAS_053-S1-1-1 | BRN-LAS_053-S1-1-1-1.4-System | LAS_053 | 1.4 | Issue and approve a User List | System | 0.1 | 0.5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_053 | BRN-LAS_053-S1-1-1 | BRN-LAS_053-S1-1-1-1.5-System | LAS_053 | 1.5 | Update relevant SOPs and periodically review the User List according to procedure | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_053 | BRN-LAS_053-S2-2-2 | BRN-LAS_053-S2-2-2-2.1-System | LAS_053 | 2.1 | Investigate with the supplier if it is possible to implement a proper configuration of user groups with segregation of duties | System | 1 | 0 | NO | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_053 | BRN-LAS_053-S2-2-2 | BRN-LAS_053-S2-2-2-2.2-System | LAS_053 | 2.2 | Change Control Management including impact assessment | System | 0.5 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_053 | BRN-LAS_053-S2-2-2 | BRN-LAS_053-S2-2-2-2.3-System | LAS_053 | 2.3 | Configure 3 user groups and define the role of each user | System | 1 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_053 | BRN-LAS_053-S2-2-2 | BRN-LAS_053-S2-2-2-2.4-System | LAS_053 | 2.4 | Configure user privileges according to a proper segregation of duties | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_053 | BRN-LAS_053-S2-2-2 | BRN-LAS_053-S2-2-2-2.5-System | LAS_053 | 2.5 | Test and document the configuration changes | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_053 | BRN-LAS_053-S2-2-2 | BRN-LAS_053-S2-2-2-2.6-System | LAS_053 | 2.6 | Update relevant SOP | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_053 | BRN-LAS_053-S3-3-3 | BRN-LAS_053-S3-3-3-3.1-System | LAS_053 | 3.1 | Investigate with the supplier if it is possible to upgrade the software to grant proper security features for user access | System | 1 | 0 | NO | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_053 | BRN-LAS_053-S3-3-3 | BRN-LAS_053-S3-3-3-3.2-Generic | LAS_053 | 3.2 | Define the Password features in an approved procedure | Generic | 1 | 3 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_053 | BRN-LAS_053-S3-3-3 | BRN-LAS_053-S3-3-3-3.3-System | LAS_053 | 3.3 | Personnel training to access the system | System | 0.5 | 0.5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_053 | BRN-LAS_053-S3-3-3 | BRN-LAS_053-S3-3-3-3.4-System | LAS_053 | 3.4 | Update relevant SOP | System | 0.2 | 0.2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_053 | BRN-LAS_053-S4-2-4 | BRN-LAS_053-S4-2-4-4.1-System | LAS_053 | 4.1 | Issue a User List with the actual status of users | System | 0.1 | 0.5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_053 | BRN-LAS_053-S4-2-4 | BRN-LAS_053-S4-2-4-4.2-Generic | LAS_053 | 4.2 | Issue and approve a Periodic Review for User List | Generic | 0.1 | 0.5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_053 | BRN-LAS_053-S4-2-4 | BRN-LAS_053-S4-2-4-4.3-System | LAS_053 | 4.3 | Execute Periodic Review | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_053 | BRN-LAS_053-S4-2-4 | BRN-LAS_053-S4-2-4-4.4-System | LAS_053 | 4.4 | Setup of periodic task in relevant system | System | 0.2 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_053 | BRN-LAS_053-I1-1-5 | BRN-LAS_053-I1-1-5-5.1-System | LAS_053 | 5.1 | Change Control Management including impact assessment | System | 0.5 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_053 | BRN-LAS_053-I1-1-5 | BRN-LAS_053-I1-1-5-5.2-System | LAS_053 | 5.2 | Implement a process of automatic data backup | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_053 | BRN-LAS_053-I1-1-5 | BRN-LAS_053-I1-1-5-5.3-Generic | LAS_053 | 5.3 | If automatic backup its not possible, document manual backups of system data with a proper frequency to be defined in a dedicated procedure | Generic | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_053 | BRN-LAS_053-I1-1-5 | BRN-LAS_053-I1-1-5-5.4-System | LAS_053 | 5.4 | Test and document the implemented changes | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_053 | BRN-LAS_053-I1-1-5 | BRN-LAS_053-I1-1-5-5.5-System | LAS_053 | 5.5 | Update relevant SOP | System | 0.2 | 0.2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_053 | BRN-LAS_053-T1-1-6 | BRN-LAS_053-T1-1-6-6.1-System | LAS_053 | 6.1 | Change Control Management including impact assessment | System | 0.5 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_053 | BRN-LAS_053-T1-1-6 | BRN-LAS_053-T1-1-6-6.2-System | LAS_053 | 6.2 | Update Audit Trail functionality in order to track and record modifications to ER | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_053 | BRN-LAS_053-T1-1-6 | BRN-LAS_053-T1-1-6-6.3-Generic | LAS_053 | 6.3 | If Audit Trail is not compliant (e.g. does not track modifications to ER), implement a paper based management of system regulated input records (i.e. methods) with the following paper procedures: -user access log -verification log to be used by the Users before launching a method -traceability log to be used by the system administrators when changing a method | Generic | 2 | 3 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_053 | BRN-LAS_053-T1-1-6 | BRN-LAS_053-T1-1-6-6.4-System | LAS_053 | 6.4 | Test and document that Audit Trail is fully compliant or, in case of paper Audit Trail, that the personnel is trained to use it | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_053 | BRN-LAS_053-T1-1-6 | BRN-LAS_053-T1-1-6-6.5-System | LAS_053 | 6.5 | Update relevant SOP | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_053 | BRN-LAS_053-T3-2-7 | BRN-LAS_053-T3-2-7-7.1-Generic | LAS_053 | 7.1 | If there is no Audit Trail Process fully compliant, issue and approve a fully compliant Audit Trail Review Working Instruction | Generic | 1 | 3 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_053 | BRN-LAS_053-T3-2-7 | BRN-LAS_053-T3-2-7-7.2-System | LAS_053 | 7.2 | Execute Audit Trail Review Working Instruction: - perform Data Assessment for Electronic Records managed by the system - update Operational Method SOP (Methods/Instrument) - update test documentation | System | 0.5 | 2.5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_053 | BRN-LAS_053-T3-2-7 | BRN-LAS_053-T3-2-7-7.3-System | LAS_053 | 7.3 | Setup of periodic task | System | 0.2 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_053 | BRN-LAS_053-T4-2-8 | BRN-LAS_053-T4-2-8-8.1-System | LAS_053 | 8.1 | Implement a process of automatic data transfer | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_053 | BRN-LAS_053-T4-2-8 | BRN-LAS_053-T4-2-8-8.2-Generic | LAS_053 | 8.2 | If automatic backup its not possible, document manual transfers of system data with a proper frequency to be defined in a dedicated procedure | Generic | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_053 | BRN-LAS_053-T4-2-8 | BRN-LAS_053-T4-2-8-8.3-System | LAS_053 | 8.3 | Test and document the implemented changes | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_053 | BRN-LAS_053-T4-2-8 | BRN-LAS_053-T4-2-8-8.4-System | LAS_053 | 8.4 | Update relevant SOP | System | 0.2 | 0.2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_053 | BRN-LAS_053-VD1-1-9 | BRN-LAS_053-VD1-1-9-9.1-System | LAS_053 | 9.1 | Review the Computer System Validation in place and identify the missing/incomplete validation documents or testing protocols | System | 1 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started | Validation Plan not present, Traceability Matrix present, VR (called Qualifizierungsbericht, eng. Qualification report) does not address the procedures., URS document present but it is missing Functional Process Requirements, Access Control and Security Roles partially covered, no reference to regulatory rules (e.g. Annex11 coverage), Configuration Specification not identified., RA is identified but does not cover the risk associated to Regulatory Requirements and ERES definition., IQ/OQ has been identified, but the level of detail is not consistent with DI expectations, i.e. Security/Integrity/Traceability verifications. Missing tests for documental checks (e.g. Users List, SOPs, etc.), functional checks (Part 11 and Annex 11 verifications), PQ protocol is not identified
BRN | BRN-LAS_053 | BRN-LAS_053-VD1-1-9 | BRN-LAS_053-VD1-1-9-9.2-System | LAS_053 | 9.2 | Issue and approve the missing validation documentation | System | 2 | 3 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_053 | BRN-LAS_053-VD1-1-9 | BRN-LAS_053-VD1-1-9-9.3-System | LAS_053 | 9.3 | Perform and document the missing/incomplete tests | System | 3 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_053 | BRN-LAS_053-VD1-1-9 | BRN-LAS_053-VD1-1-9-9.4-System | LAS_053 | 9.4 | Assure the Traceability of the testing with coded requirements against coded test and update the documentation accordingly | System | 2 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_054 | BRN-LAS_054-S1-1-1 | BRN-LAS_054-S1-1-1-1.1-System | LAS_054 | 1.1 | Change Control Management including impact assessment | System | 0.5 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_054 | BRN-LAS_054-S1-1-1 | BRN-LAS_054-S1-1-1-1.2-System | LAS_054 | 1.2 | Update the application SW in order to configure unique and personal accounts. If it is not possible to configure personal account within application SW, implement a proper user management within OS accounts | System | 3 | 3 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_054 | BRN-LAS_054-S1-1-1 | BRN-LAS_054-S1-1-1-1.3-System | LAS_054 | 1.3 | Test and document the configuration changes or procedural changes | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_054 | BRN-LAS_054-S1-1-1 | BRN-LAS_054-S1-1-1-1.4-System | LAS_054 | 1.4 | Issue and approve a User List | System | 0.1 | 0.5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_054 | BRN-LAS_054-S1-1-1 | BRN-LAS_054-S1-1-1-1.5-System | LAS_054 | 1.5 | Update relevant SOPs and periodically review the User List according to procedure | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_054 | BRN-LAS_054-S2-2-2 | BRN-LAS_054-S2-2-2-2.1-System | LAS_054 | 2.1 | Investigate with the supplier if it is possible to implement a proper configuration of user groups with segregation of duties | System | 1 | 0 | NO | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_054 | BRN-LAS_054-S2-2-2 | BRN-LAS_054-S2-2-2-2.2-System | LAS_054 | 2.2 | Change Control Management including impact assessment | System | 0.5 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_054 | BRN-LAS_054-S2-2-2 | BRN-LAS_054-S2-2-2-2.3-System | LAS_054 | 2.3 | Configure 3 user groups and define the role of each user | System | 1 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_054 | BRN-LAS_054-S2-2-2 | BRN-LAS_054-S2-2-2-2.4-System | LAS_054 | 2.4 | Configure user privileges according to a proper segregation of duties | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_054 | BRN-LAS_054-S2-2-2 | BRN-LAS_054-S2-2-2-2.5-System | LAS_054 | 2.5 | Test and document the configuration changes | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_054 | BRN-LAS_054-S2-2-2 | BRN-LAS_054-S2-2-2-2.6-System | LAS_054 | 2.6 | Update relevant SOP | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_054 | BRN-LAS_054-S3-3-3 | BRN-LAS_054-S3-3-3-3.1-System | LAS_054 | 3.1 | Investigate with the supplier if it is possible to upgrade the software to grant proper security features for user access | System | 1 | 0 | NO | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_054 | BRN-LAS_054-S3-3-3 | BRN-LAS_054-S3-3-3-3.2-Generic | LAS_054 | 3.2 | Define the Password features in an approved procedure | Generic | 1 | 3 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_054 | BRN-LAS_054-S3-3-3 | BRN-LAS_054-S3-3-3-3.3-System | LAS_054 | 3.3 | Personnel training to access the system | System | 0.5 | 0.5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_054 | BRN-LAS_054-S3-3-3 | BRN-LAS_054-S3-3-3-3.4-System | LAS_054 | 3.4 | Update relevant SOP | System | 0.2 | 0.2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_054 | BRN-LAS_054-S4-2-4 | BRN-LAS_054-S4-2-4-4.1-System | LAS_054 | 4.1 | Issue a User List with the actual status of users | System | 0.1 | 0.5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_054 | BRN-LAS_054-S4-2-4 | BRN-LAS_054-S4-2-4-4.2-Generic | LAS_054 | 4.2 | Issue and approve a Periodic Review for User List | Generic | 0.1 | 0.5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_054 | BRN-LAS_054-S4-2-4 | BRN-LAS_054-S4-2-4-4.3-System | LAS_054 | 4.3 | Execute Periodic Review | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_054 | BRN-LAS_054-S4-2-4 | BRN-LAS_054-S4-2-4-4.4-System | LAS_054 | 4.4 | Setup of periodic task in relevant system | System | 0.2 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_054 | BRN-LAS_054-I1-1-5 | BRN-LAS_054-I1-1-5-5.1-System | LAS_054 | 5.1 | Change Control Management including impact assessment | System | 0.5 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_054 | BRN-LAS_054-I1-1-5 | BRN-LAS_054-I1-1-5-5.2-System | LAS_054 | 5.2 | Implement a process of automatic data backup | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_054 | BRN-LAS_054-I1-1-5 | BRN-LAS_054-I1-1-5-5.3-Generic | LAS_054 | 5.3 | If automatic backup its not possible, document manual backups of system data with a proper frequency to be defined in a dedicated procedure | Generic | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_054 | BRN-LAS_054-I1-1-5 | BRN-LAS_054-I1-1-5-5.4-System | LAS_054 | 5.4 | Test and document the implemented changes | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_054 | BRN-LAS_054-I1-1-5 | BRN-LAS_054-I1-1-5-5.5-System | LAS_054 | 5.5 | Update relevant SOP | System | 0.2 | 0.2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_054 | BRN-LAS_054-T1-1-6 | BRN-LAS_054-T1-1-6-6.1-System | LAS_054 | 6.1 | Change Control Management including impact assessment | System | 0.5 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_054 | BRN-LAS_054-T1-1-6 | BRN-LAS_054-T1-1-6-6.2-System | LAS_054 | 6.2 | Update Audit Trail functionality in order to track and record modifications to ER | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_054 | BRN-LAS_054-T1-1-6 | BRN-LAS_054-T1-1-6-6.3-Generic | LAS_054 | 6.3 | If Audit Trail is not compliant (e.g. does not track modifications to ER), implement a paper based management of system regulated input records (i.e. methods) with the following paper procedures: -user access log -verification log to be used by the Users before launching a method -traceability log to be used by the system administrators when changing a method | Generic | 2 | 3 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_054 | BRN-LAS_054-T1-1-6 | BRN-LAS_054-T1-1-6-6.4-System | LAS_054 | 6.4 | Test and document that Audit Trail is fully compliant or, in case of paper Audit Trail, that the personnel is trained to use it | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_054 | BRN-LAS_054-T1-1-6 | BRN-LAS_054-T1-1-6-6.5-System | LAS_054 | 6.5 | Update relevant SOP | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_054 | BRN-LAS_054-T3-2-7 | BRN-LAS_054-T3-2-7-7.1-Generic | LAS_054 | 7.1 | If there is no Audit Trail Process fully compliant, issue and approve a fully compliant Audit Trail Review Working Instruction | Generic | 1 | 3 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_054 | BRN-LAS_054-T3-2-7 | BRN-LAS_054-T3-2-7-7.2-System | LAS_054 | 7.2 | Execute Audit Trail Review Working Instruction: - perform Data Assessment for Electronic Records managed by the system - update Operational Method SOP (Methods/Instrument) - update test documentation | System | 0.5 | 2.5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_054 | BRN-LAS_054-T3-2-7 | BRN-LAS_054-T3-2-7-7.3-System | LAS_054 | 7.3 | Setup of periodic task | System | 0.2 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_054 | BRN-LAS_054-T4-2-8 | BRN-LAS_054-T4-2-8-8.1-System | LAS_054 | 8.1 | Change Control Management including impact assessment | System | 0.5 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_054 | BRN-LAS_054-T4-2-8 | BRN-LAS_054-T4-2-8-8.2-System | LAS_054 | 8.2 | Implement a process of automatic data transfer | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_054 | BRN-LAS_054-T4-2-8 | BRN-LAS_054-T4-2-8-8.3-Generic | LAS_054 | 8.3 | If automatic backup its not possible, document manual transfers of system data with a proper frequency to be defined in a dedicated procedure | Generic | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_054 | BRN-LAS_054-T4-2-8 | BRN-LAS_054-T4-2-8-8.4-System | LAS_054 | 8.4 | Test and document the implemented changes | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_054 | BRN-LAS_054-VD1-1-9 | BRN-LAS_054-VD1-1-9-9.1-System | LAS_054 | 9.1 | Update relevant SOP | System | 0.2 | 0.2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started | Validation Plan not present, Traceability Matrix present, VR (called Qualifizierungsbericht, eng. Qualification report) does not address the procedures., URS document present but it is missing Functional Process Requirements, Access Control and Security Roles partially covered, no reference to regulatory rules (e.g. Annex11 coverage), Configuration Specification not identified., RA is identified but does not cover the risk associated to Regulatory Requirements and ERES definition., IQ/OQ has been identified, but the level of detail is not consistent with DI expectations, i.e. Security/Integrity/Traceability verifications. Missing tests for documental checks (e.g. Users List, SOPs, etc.), functional checks (Part 11 and Annex 11 verifications), PQ protocol is not identified
BRN | BRN-LAS_054 | BRN-LAS_054-VD1-1-9 | BRN-LAS_054-VD1-1-9-9.2-System | LAS_054 | 9.2 | Issue and approve the missing validation documentation | System | 2 | 3 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_054 | BRN-LAS_054-VD1-1-9 | BRN-LAS_054-VD1-1-9-9.3-System | LAS_054 | 9.3 | Perform and document the missing/incomplete tests | System | 3 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_054 | BRN-LAS_054-VD1-1-9 | BRN-LAS_054-VD1-1-9-9.4-System | LAS_054 | 9.4 | Assure the Traceability of the testing with coded requirements against coded test and update the documentation accordingly | System | 2 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_058 | BRN-LAS_058-S1-1-1 | BRN-LAS_058-S1-1-1-1.1-System | LAS_058 | 1.1 | Change Control Management including impact assessment | System | 0.5 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_058 | BRN-LAS_058-S1-1-1 | BRN-LAS_058-S1-1-1-1.2-System | LAS_058 | 1.2 | Update the application SW in order to configure unique and personal accounts. If it is not possible to configure personal account within application SW, implement a proper user management within OS accounts | System | 3 | 3 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_058 | BRN-LAS_058-S1-1-1 | BRN-LAS_058-S1-1-1-1.3-System | LAS_058 | 1.3 | Test and document the configuration changes or procedural changes | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_058 | BRN-LAS_058-S1-1-1 | BRN-LAS_058-S1-1-1-1.4-System | LAS_058 | 1.4 | Issue and approve a User List | System | 0.1 | 0.5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_058 | BRN-LAS_058-S1-1-1 | BRN-LAS_058-S1-1-1-1.5-System | LAS_058 | 1.5 | Update relevant SOPs and periodically review the User List according to procedure | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_058 | BRN-LAS_058-S2-2-2 | BRN-LAS_058-S2-2-2-2.1-System | LAS_058 | 2.1 | Change Control Management including impact assessment | System | 0.5 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_058 | BRN-LAS_058-S2-2-2 | BRN-LAS_058-S2-2-2-2.2-System | LAS_058 | 2.2 | Configure 3 user groups and define the role of each user | System | 1 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_058 | BRN-LAS_058-S2-2-2 | BRN-LAS_058-S2-2-2-2.3-System | LAS_058 | 2.3 | Configure user privileges according to a proper segregation of duties | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_058 | BRN-LAS_058-S2-2-2 | BRN-LAS_058-S2-2-2-2.4-System | LAS_058 | 2.4 | Test and document the configuration changes | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_058 | BRN-LAS_058-S2-2-2 | BRN-LAS_058-S2-2-2-2.5-System | LAS_058 | 2.5 | Update relevant SOP | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_058 | BRN-LAS_058-S3-3-3 | BRN-LAS_058-S3-3-3-3.1-Generic | LAS_058 | 3.1 | Issue and approve a Security SOP with proper PW security features according to best practices (length, complexity, expiring) | Generic | 1 | 5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_058 | BRN-LAS_058-S3-3-3 | BRN-LAS_058-S3-3-3-3.2-System | LAS_058 | 3.2 | Update all passwords according to the approved Security SOP | System | 1 | 0.1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_058 | BRN-LAS_058-S3-3-3 | BRN-LAS_058-S3-3-3-3.3-System | LAS_058 | 3.3 | Test and document the Password policies | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_058 | BRN-LAS_058-S4-2-4 | BRN-LAS_058-S4-2-4-4.1-System | LAS_058 | 4.1 | Issue a User List with the actual status of users | System | 0.1 | 0.5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_058 | BRN-LAS_058-S4-2-4 | BRN-LAS_058-S4-2-4-4.2-Generic | LAS_058 | 4.2 | Issue and approve a Periodic Review for User List | Generic | 0.1 | 0.5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_058 | BRN-LAS_058-S4-2-4 | BRN-LAS_058-S4-2-4-4.3-System | LAS_058 | 4.3 | Execute Periodic Review | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_058 | BRN-LAS_058-S4-2-4 | BRN-LAS_058-S4-2-4-4.4-System | LAS_058 | 4.4 | Setup of periodic task in relevant system | System | 0.2 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_058 | BRN-LAS_058-I1-1-5 | BRN-LAS_058-I1-1-5-5.1-Generic | LAS_058 | 5.1 | Verify if modality and frequency of the backups are defined in an official document with a risk-based approach | Generic | 1 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_058 | BRN-LAS_058-I1-1-5 | BRN-LAS_058-I1-1-5-5.2-System | LAS_058 | 5.2 | If not, execute the risk analyses and reconfigure the backup | System | 0.1 | 0.5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_058 | BRN-LAS_058-I1-1-5 | BRN-LAS_058-I1-1-5-5.3-System | LAS_058 | 5.3 | Test and document the configuration changes | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_058 | BRN-LAS_058-I1-1-5 | BRN-LAS_058-I1-1-5-5.4-System | LAS_058 | 5.4 | Update relevant SOP | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_058 | BRN-LAS_058-I2-1-6 | BRN-LAS_058-I2-1-6-6.1-System | LAS_058 | 6.1 | Change Control Management including impact assessment | System | 0.5 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_058 | BRN-LAS_058-I2-1-6 | BRN-LAS_058-I2-1-6-6.2-System | LAS_058 | 6.2 | Change permissions for users not authorized to modify data, preventing the deletion or alteration. | System | 0.5 | 0 | NO | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_058 | BRN-LAS_058-I2-1-6 | BRN-LAS_058-I2-1-6-6.3-System | LAS_058 | 6.3 | Test and document the configuration changes | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_058 | BRN-LAS_058-I2-1-6 | BRN-LAS_058-I2-1-6-6.4-System | LAS_058 | 6.4 | Update relevant SOP | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_058 | BRN-LAS_058-I3-1-7 | BRN-LAS_058-I3-1-7-7.1-System | LAS_058 | 7.1 | Change Control Management including impact assessment | System | 0.5 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_058 | BRN-LAS_058-I3-1-7 | BRN-LAS_058-I3-1-7-7.2-System | LAS_058 | 7.2 | Configure the protection of input data through an automatic security policy or folder restrictions | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_058 | BRN-LAS_058-I3-1-7 | BRN-LAS_058-I3-1-7-7.3-System | LAS_058 | 7.3 | Configure user privileges to prevent the deletion or alteration of input data | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_058 | BRN-LAS_058-I3-1-7 | BRN-LAS_058-I3-1-7-7.4-System | LAS_058 | 7.4 | Test and document the configuration changes | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_058 | BRN-LAS_058-I3-1-7 | BRN-LAS_058-I3-1-7-7.5-System | LAS_058 | 7.5 | Update relevant SOP | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_058 | BRN-LAS_058-T1-2-8 | BRN-LAS_058-T1-2-8-8.1-System | LAS_058 | 8.1 | Investigate with the supplier if it is possible to implement a proper configuration of the AT | System | 1 | 0 | NO | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_058 | BRN-LAS_058-T1-2-8 | BRN-LAS_058-T1-2-8-8.2-System | LAS_058 | 8.2 | Change Control Management including impact assessment | System | 0.5 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_058 | BRN-LAS_058-T1-2-8 | BRN-LAS_058-T1-2-8-8.3-System | LAS_058 | 8.3 | Configure Audit Trail functionality within the SW or, if not applicable, implement a paper based management for tracking relevant operation (i.e. old&new value, reason for change) to relevant data | System | 2 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_058 | BRN-LAS_058-T1-2-8 | BRN-LAS_058-T1-2-8-8.4-System | LAS_058 | 8.4 | Test and document configuration changes or the procedural changes | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_058 | BRN-LAS_058-T1-2-8 | BRN-LAS_058-T1-2-8-8.5-System | LAS_058 | 8.5 | Update relevant SOP | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_058 | BRN-LAS_058-T3-3-9 | BRN-LAS_058-T3-3-9-9.1-Generic | LAS_058 | 9.1 | Issue and approve a fully compliant Audit Trail Review Working Instruction | Generic | 0.5 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_058 | BRN-LAS_058-T3-3-9 | BRN-LAS_058-T3-3-9-9.2-System | LAS_058 | 9.2 | Execute Audit Trail Review Working Instruction: - perform Data Assessment for Electronic Records managed by the system - update Operational Method SOP (Methods/Instrument) - update test documentation | System | 0.5 | 2.5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_058 | BRN-LAS_058-T3-3-9 | BRN-LAS_058-T3-3-9-9.3-System | LAS_058 | 9.3 | Setup of periodic task | System | 0.2 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_058 | BRN-LAS_058-VD1-1-10 | BRN-LAS_058-VD1-1-10-10.1-System | LAS_058 | 10.1 | Review the Computer System Validation in place and identify the missing/incomplete validation documents or testing protocols | System | 1 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started | Validation Plan not present, Global CSV SOPs not applied., Traceability Matrix is present not complete, VR (called Qualifizierungsbericht, eng. Qualification report) not complete, URS document present but it is missing Functional Process Requirements, Access Control and Security Roles partially covered, no reference to regulatory rules (e.g. Annex11 coverage), Configuration Specification not identified., Risk Assessment not present, IQ and OQ protocols identified, however the level of details is not consistent with DI expectations., PQ not identified.
BRN | BRN-LAS_058 | BRN-LAS_058-VD1-1-10 | BRN-LAS_058-VD1-1-10-10.2-System | LAS_058 | 10.2 | Issue and approve the missing validation documentation | System | 2 | 3 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_058 | BRN-LAS_058-VD1-1-10 | BRN-LAS_058-VD1-1-10-10.3-System | LAS_058 | 10.3 | Perform and document the missing/incomplete tests | System | 3 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_058 | BRN-LAS_058-VD1-1-10 | BRN-LAS_058-VD1-1-10-10.4-System | LAS_058 | 10.4 | Assure the Traceability of the testing with coded requirements against coded test and update the documentation accordingly | System | 2 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_060 | BRN-LAS_060-S1-1-1 | BRN-LAS_060-S1-1-1-1.1-System | LAS_060 | 1.1 | Change Control Management including impact assessment | System | 0.5 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_060 | BRN-LAS_060-S1-1-1 | BRN-LAS_060-S1-1-1-1.2-System | LAS_060 | 1.2 | Update the application SW in order to configure unique and personal accounts. If it is not possible to configure personal account within application SW, implement a proper user management within OS accounts | System | 3 | 3 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_060 | BRN-LAS_060-S1-1-1 | BRN-LAS_060-S1-1-1-1.3-System | LAS_060 | 1.3 | Test and document the configuration changes or procedural changes | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_060 | BRN-LAS_060-S1-1-1 | BRN-LAS_060-S1-1-1-1.4-System | LAS_060 | 1.4 | Issue and approve a User List | System | 0.1 | 0.5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_060 | BRN-LAS_060-S1-1-1 | BRN-LAS_060-S1-1-1-1.5-System | LAS_060 | 1.5 | Update relevant SOPs and periodically review the User List according to procedure | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_060 | BRN-LAS_060-S2-2-2 | BRN-LAS_060-S2-2-2-2.1-System | LAS_060 | 2.1 | Change Control Management including impact assessment | System | 0.5 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_060 | BRN-LAS_060-S2-2-2 | BRN-LAS_060-S2-2-2-2.2-System | LAS_060 | 2.2 | Configure 3 user groups and define the role of each user | System | 1 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_060 | BRN-LAS_060-S2-2-2 | BRN-LAS_060-S2-2-2-2.3-System | LAS_060 | 2.3 | Configure user privileges according to a proper segregation of duties | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_060 | BRN-LAS_060-S2-2-2 | BRN-LAS_060-S2-2-2-2.4-System | LAS_060 | 2.4 | Test and document the configuration changes | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_060 | BRN-LAS_060-S2-2-2 | BRN-LAS_060-S2-2-2-2.5-System | LAS_060 | 2.5 | Update relevant SOP | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_060 | BRN-LAS_060-S3-3-3 | BRN-LAS_060-S3-3-3-3.1-Generic | LAS_060 | 3.1 | Issue and approve a Security SOP with proper PW security features according to best practices (length, complexity, expiring) | Generic | 1 | 5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_060 | BRN-LAS_060-S3-3-3 | BRN-LAS_060-S3-3-3-3.2-System | LAS_060 | 3.2 | Update all passwords according to the approved Security SOP | System | 1 | 0.1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_060 | BRN-LAS_060-S3-3-3 | BRN-LAS_060-S3-3-3-3.3-System | LAS_060 | 3.3 | Test and document the Password policies | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_060 | BRN-LAS_060-S4-2-4 | BRN-LAS_060-S4-2-4-4.1-System | LAS_060 | 4.1 | Issue a User List with the actual status of users | System | 0.1 | 0.5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_060 | BRN-LAS_060-S4-2-4 | BRN-LAS_060-S4-2-4-4.2-Generic | LAS_060 | 4.2 | Issue and approve a Periodic Review for User List | Generic | 0.1 | 0.5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_060 | BRN-LAS_060-S4-2-4 | BRN-LAS_060-S4-2-4-4.3-System | LAS_060 | 4.3 | Execute Periodic Review | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_060 | BRN-LAS_060-S4-2-4 | BRN-LAS_060-S4-2-4-4.4-System | LAS_060 | 4.4 | Setup of periodic task in relevant system | System | 0.2 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_060 | BRN-LAS_060-I1-1-5 | BRN-LAS_060-I1-1-5-5.1-Generic | LAS_060 | 5.1 | Verify if modality and frequency of the backups are defined in an official document with a risk-based approach | Generic | 1 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_060 | BRN-LAS_060-I1-1-5 | BRN-LAS_060-I1-1-5-5.2-System | LAS_060 | 5.2 | If not, execute the risk analyses and reconfigure the backup | System | 0.1 | 0.5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_060 | BRN-LAS_060-I1-1-5 | BRN-LAS_060-I1-1-5-5.3-System | LAS_060 | 5.3 | Test and document the configuration changes | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_060 | BRN-LAS_060-I1-1-5 | BRN-LAS_060-I1-1-5-5.4-System | LAS_060 | 5.4 | Update relevant SOP | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_060 | BRN-LAS_060-I2-1-6 | BRN-LAS_060-I2-1-6-6.1-System | LAS_060 | 6.1 | Change Control Management including impact assessment | System | 0.5 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_060 | BRN-LAS_060-I2-1-6 | BRN-LAS_060-I2-1-6-6.2-System | LAS_060 | 6.2 | Change permissions for users not authorized to modify data, preventing the deletion or alteration. | System | 0.5 | 0 | NO | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_060 | BRN-LAS_060-I2-1-6 | BRN-LAS_060-I2-1-6-6.3-System | LAS_060 | 6.3 | Test and document the configuration changes | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_060 | BRN-LAS_060-I2-1-6 | BRN-LAS_060-I2-1-6-6.4-System | LAS_060 | 6.4 | Update relevant SOP | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_060 | BRN-LAS_060-I3-1-7 | BRN-LAS_060-I3-1-7-7.1-System | LAS_060 | 7.1 | Change Control Management including impact assessment | System | 0.5 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_060 | BRN-LAS_060-I3-1-7 | BRN-LAS_060-I3-1-7-7.2-System | LAS_060 | 7.2 | Configure the protection of input data through an automatic security policy or folder restrictions | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_060 | BRN-LAS_060-I3-1-7 | BRN-LAS_060-I3-1-7-7.3-System | LAS_060 | 7.3 | Configure user privileges to prevent the deletion or alteration of input data | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_060 | BRN-LAS_060-I3-1-7 | BRN-LAS_060-I3-1-7-7.4-System | LAS_060 | 7.4 | Test and document the configuration changes | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_060 | BRN-LAS_060-I3-1-7 | BRN-LAS_060-I3-1-7-7.5-System | LAS_060 | 7.5 | Update relevant SOP | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_060 | BRN-LAS_060-T1-1-8 | BRN-LAS_060-T1-1-8-8.1-System | LAS_060 | 8.1 | Investigate with the supplier if it is possible to implement a proper configuration of the AT | System | 1 | 0 | NO | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_060 | BRN-LAS_060-T1-1-8 | BRN-LAS_060-T1-1-8-8.2-System | LAS_060 | 8.2 | Change Control Management including impact assessment | System | 0.5 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_060 | BRN-LAS_060-T1-1-8 | BRN-LAS_060-T1-1-8-8.3-System | LAS_060 | 8.3 | Configure Audit Trail functionality within the SW or, if not applicable, implement a paper based management for tracking relevant operation (i.e. old&new value, reason for change) to relevant data | System | 2 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_060 | BRN-LAS_060-T1-1-8 | BRN-LAS_060-T1-1-8-8.4-System | LAS_060 | 8.4 | Test and document configuration changes or the procedural changes | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_060 | BRN-LAS_060-T1-1-8 | BRN-LAS_060-T1-1-8-8.5-System | LAS_060 | 8.5 | Update relevant SOP | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_060 | BRN-LAS_060-T3-2-9 | BRN-LAS_060-T3-2-9-9.1-Generic | LAS_060 | 9.1 | Issue and approve a fully compliant Audit Trail Review Working Instruction | Generic | 0.5 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_060 | BRN-LAS_060-T3-2-9 | BRN-LAS_060-T3-2-9-9.2-System | LAS_060 | 9.2 | Execute Audit Trail Review Working Instruction: - perform Data Assessment for Electronic Records managed by the system - update Operational Method SOP (Methods/Instrument) - update test documentation | System | 0.5 | 2.5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_060 | BRN-LAS_060-T3-2-9 | BRN-LAS_060-T3-2-9-9.3-System | LAS_060 | 9.3 | Setup of periodic task | System | 0.2 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_060 | BRN-LAS_060-VD1-1-10 | BRN-LAS_060-VD1-1-10-10.1-System | LAS_060 | 10.1 | Review the Computer System Validation in place and identify the missing/incomplete validation documents or testing protocols | System | 1 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started | Validation Plan not present, Global CSV SOPs not applied., Traceability Matrix is present not complete, VR (called Qualifizierungsbericht, eng. Qualification report) not complete, URS document present but it is missing Functional Process Requirements, Access Control and Security Roles partially covered, no reference to regulatory rules (e.g. Annex11 coverage), Configuration Specification not identified., Risk Assessment not present, IQ and OQ protocols identified, however the level of details is not consistent with DI expectations., PQ not identified.
BRN | BRN-LAS_060 | BRN-LAS_060-VD1-1-10 | BRN-LAS_060-VD1-1-10-10.2-System | LAS_060 | 10.2 | Issue and approve the missing validation documentation | System | 2 | 3 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_060 | BRN-LAS_060-VD1-1-10 | BRN-LAS_060-VD1-1-10-10.3-System | LAS_060 | 10.3 | Perform and document the missing/incomplete tests | System | 3 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_060 | BRN-LAS_060-VD1-1-10 | BRN-LAS_060-VD1-1-10-10.4-System | LAS_060 | 10.4 | Assure the Traceability of the testing with coded requirements against coded test and update the documentation accordingly | System | 2 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_061 | BRN-LAS_061-S1-1-1 | BRN-LAS_061-S1-1-1-1.1-System | LAS_061 | 1.1 | Change Control Management including impact assessment | System | 0.5 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_061 | BRN-LAS_061-S1-1-1 | BRN-LAS_061-S1-1-1-1.2-System | LAS_061 | 1.2 | Update the application SW in order to configure unique and personal accounts. If it is not possible to configure personal account within application SW, implement a proper user management within OS accounts | System | 3 | 3 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_061 | BRN-LAS_061-S1-1-1 | BRN-LAS_061-S1-1-1-1.3-System | LAS_061 | 1.3 | Test and document the configuration changes or procedural changes | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_061 | BRN-LAS_061-S1-1-1 | BRN-LAS_061-S1-1-1-1.4-System | LAS_061 | 1.4 | Issue and approve a User List | System | 0.1 | 0.5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_061 | BRN-LAS_061-S1-1-1 | BRN-LAS_061-S1-1-1-1.5-System | LAS_061 | 1.5 | Update relevant SOPs and periodically review the User List according to procedure | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_061 | BRN-LAS_061-S2-2-2 | BRN-LAS_061-S2-2-2-2.1-System | LAS_061 | 2.1 | Change Control Management including impact assessment | System | 0.5 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_061 | BRN-LAS_061-S2-2-2 | BRN-LAS_061-S2-2-2-2.2-System | LAS_061 | 2.2 | Configure 3 user groups and define the role of each user | System | 1 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_061 | BRN-LAS_061-S2-2-2 | BRN-LAS_061-S2-2-2-2.3-System | LAS_061 | 2.3 | Configure user privileges according to a proper segregation of duties | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_061 | BRN-LAS_061-S2-2-2 | BRN-LAS_061-S2-2-2-2.4-System | LAS_061 | 2.4 | Test and document the configuration changes | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_061 | BRN-LAS_061-S2-2-2 | BRN-LAS_061-S2-2-2-2.5-System | LAS_061 | 2.5 | Update relevant SOP | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_061 | BRN-LAS_061-S3-3-3 | BRN-LAS_061-S3-3-3-3.1-Generic | LAS_061 | 3.1 | Issue and approve a Security SOP with proper PW security features according to best practices (length, complexity, expiring) | Generic | 1 | 5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_061 | BRN-LAS_061-S3-3-3 | BRN-LAS_061-S3-3-3-3.2-System | LAS_061 | 3.2 | Update all passwords according to the approved Security SOP | System | 1 | 0.1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_061 | BRN-LAS_061-S3-3-3 | BRN-LAS_061-S3-3-3-3.3-System | LAS_061 | 3.3 | Test and document the Password policies | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_061 | BRN-LAS_061-S4-2-4 | BRN-LAS_061-S4-2-4-4.1-System | LAS_061 | 4.1 | Issue a User List with the actual status of users | System | 0.1 | 0.5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_061 | BRN-LAS_061-S4-2-4 | BRN-LAS_061-S4-2-4-4.2-Generic | LAS_061 | 4.2 | Issue and approve a Periodic Review for User List | Generic | 0.1 | 0.5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_061 | BRN-LAS_061-S4-2-4 | BRN-LAS_061-S4-2-4-4.3-System | LAS_061 | 4.3 | Execute Periodic Review | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_061 | BRN-LAS_061-S4-2-4 | BRN-LAS_061-S4-2-4-4.4-System | LAS_061 | 4.4 | Setup of periodic task in relevant system | System | 0.2 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_061 | BRN-LAS_061-I1-1-5 | BRN-LAS_061-I1-1-5-5.1-Generic | LAS_061 | 5.1 | Verify if modality and frequency of the backups are defined in an official document with a risk-based approach | Generic | 1 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_061 | BRN-LAS_061-I1-1-5 | BRN-LAS_061-I1-1-5-5.2-System | LAS_061 | 5.2 | If not, execute the risk analyses and reconfigure the backup | System | 0.1 | 0.5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_061 | BRN-LAS_061-I1-1-5 | BRN-LAS_061-I1-1-5-5.3-System | LAS_061 | 5.3 | Test and document the configuration changes | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_061 | BRN-LAS_061-I1-1-5 | BRN-LAS_061-I1-1-5-5.4-System | LAS_061 | 5.4 | Update relevant SOP | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_061 | BRN-LAS_061-I2-1-6 | BRN-LAS_061-I2-1-6-6.1-System | LAS_061 | 6.1 | Change Control Management including impact assessment | System | 0.5 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_061 | BRN-LAS_061-I2-1-6 | BRN-LAS_061-I2-1-6-6.2-System | LAS_061 | 6.2 | Change permissions for users not authorized to modify data, preventing the deletion or alteration. | System | 0.5 | 0 | NO | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_061 | BRN-LAS_061-I2-1-6 | BRN-LAS_061-I2-1-6-6.3-System | LAS_061 | 6.3 | Test and document the configuration changes | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_061 | BRN-LAS_061-I2-1-6 | BRN-LAS_061-I2-1-6-6.4-System | LAS_061 | 6.4 | Update relevant SOP | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_061 | BRN-LAS_061-I3-1-7 | BRN-LAS_061-I3-1-7-7.1-System | LAS_061 | 7.1 | Change Control Management including impact assessment | System | 0.5 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_061 | BRN-LAS_061-I3-1-7 | BRN-LAS_061-I3-1-7-7.2-System | LAS_061 | 7.2 | Configure the protection of input data through an automatic security policy or folder restrictions | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_061 | BRN-LAS_061-I3-1-7 | BRN-LAS_061-I3-1-7-7.3-System | LAS_061 | 7.3 | Configure user privileges to prevent the deletion or alteration of input data | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_061 | BRN-LAS_061-I3-1-7 | BRN-LAS_061-I3-1-7-7.4-System | LAS_061 | 7.4 | Test and document the configuration changes | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_061 | BRN-LAS_061-I3-1-7 | BRN-LAS_061-I3-1-7-7.5-System | LAS_061 | 7.5 | Update relevant SOP | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_061 | BRN-LAS_061-T1-2-8 | BRN-LAS_061-T1-2-8-8.1-System | LAS_061 | 8.1 | Investigate with the supplier if it is possible to implement a proper configuration of the AT | System | 1 | 0 | NO | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_061 | BRN-LAS_061-T1-2-8 | BRN-LAS_061-T1-2-8-8.2-System | LAS_061 | 8.2 | Change Control Management including impact assessment | System | 0.5 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_061 | BRN-LAS_061-T1-2-8 | BRN-LAS_061-T1-2-8-8.3-System | LAS_061 | 8.3 | Configure Audit Trail functionality within the SW or, if not applicable, implement a paper based management for tracking relevant operation (i.e. old&new value, reason for change) to relevant data | System | 2 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_061 | BRN-LAS_061-T1-2-8 | BRN-LAS_061-T1-2-8-8.4-System | LAS_061 | 8.4 | Test and document configuration changes or the procedural changes | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_061 | BRN-LAS_061-T1-2-8 | BRN-LAS_061-T1-2-8-8.5-System | LAS_061 | 8.5 | Update relevant SOP | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_061 | BRN-LAS_061-T3-3-9 | BRN-LAS_061-T3-3-9-9.1-Generic | LAS_061 | 9.1 | Issue and approve a fully compliant Audit Trail Review Working Instruction | Generic | 0.5 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_061 | BRN-LAS_061-T3-3-9 | BRN-LAS_061-T3-3-9-9.2-System | LAS_061 | 9.2 | Execute Audit Trail Review Working Instruction: - perform Data Assessment for Electronic Records managed by the system - update Operational Method SOP (Methods/Instrument) - update test documentation | System | 0.5 | 2.5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_061 | BRN-LAS_061-T3-3-9 | BRN-LAS_061-T3-3-9-9.3-System | LAS_061 | 9.3 | Setup of periodic task | System | 0.2 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_061 | BRN-LAS_061-VD1-1-10 | BRN-LAS_061-VD1-1-10-10.1-System | LAS_061 | 10.1 | Review the Computer System Validation in place and identify the missing/incomplete validation documents or testing protocols | System | 1 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started | Validation Plan not present, Global CSV SOPs not applied., Traceability Matrix is present not complete, VR (called Qualifizierungsbericht, eng. Qualification report) not complete
BRN | BRN-LAS_061 | BRN-LAS_061-VD1-1-10 | BRN-LAS_061-VD1-1-10-10.2-System | LAS_061 | 10.2 | Issue and approve the missing validation documentation | System | 2 | 3 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_061 | BRN-LAS_061-VD1-1-10 | BRN-LAS_061-VD1-1-10-10.3-System | LAS_061 | 10.3 | Perform and document the missing/incomplete tests | System | 3 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_061 | BRN-LAS_061-VD1-1-10 | BRN-LAS_061-VD1-1-10-10.4-System | LAS_061 | 10.4 | Assure the Traceability of the testing with coded requirements against coded test and update the documentation accordingly | System | 2 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_063 | BRN-LAS_063-S1-1-1 | BRN-LAS_063-S1-1-1-1.1-System | LAS_063 | 1.1 | Change Control Management including impact assessment | System | 0.5 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_063 | BRN-LAS_063-S1-1-1 | BRN-LAS_063-S1-1-1-1.2-System | LAS_063 | 1.2 | Update the application SW in order to configure unique and personal accounts. If it is not possible to configure personal account within application SW, implement a proper user management within OS accounts | System | 3 | 3 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_063 | BRN-LAS_063-S1-1-1 | BRN-LAS_063-S1-1-1-1.3-System | LAS_063 | 1.3 | Test and document the configuration changes or procedural changes | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_063 | BRN-LAS_063-S1-1-1 | BRN-LAS_063-S1-1-1-1.4-System | LAS_063 | 1.4 | Issue and approve a User List | System | 0.1 | 0.5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_063 | BRN-LAS_063-S1-1-1 | BRN-LAS_063-S1-1-1-1.5-System | LAS_063 | 1.5 | Update relevant SOPs and periodically review the User List according to procedure | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_063 | BRN-LAS_063-S2-2-2 | BRN-LAS_063-S2-2-2-2.1-System | LAS_063 | 2.1 | Change Control Management including impact assessment | System | 0.5 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_063 | BRN-LAS_063-S2-2-2 | BRN-LAS_063-S2-2-2-2.2-System | LAS_063 | 2.2 | Configure 3 user groups and define the role of each user | System | 1 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_063 | BRN-LAS_063-S2-2-2 | BRN-LAS_063-S2-2-2-2.3-System | LAS_063 | 2.3 | Configure user privileges according to a proper segregation of duties | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_063 | BRN-LAS_063-S2-2-2 | BRN-LAS_063-S2-2-2-2.4-System | LAS_063 | 2.4 | Test and document the configuration changes | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_063 | BRN-LAS_063-S2-2-2 | BRN-LAS_063-S2-2-2-2.5-System | LAS_063 | 2.5 | Update relevant SOP | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_063 | BRN-LAS_063-S3-3-3 | BRN-LAS_063-S3-3-3-3.1-Generic | LAS_063 | 3.1 | Issue and approve a Security SOP with proper PW security features according to best practices (length, complexity, expiring) | Generic | 1 | 5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_063 | BRN-LAS_063-S3-3-3 | BRN-LAS_063-S3-3-3-3.2-System | LAS_063 | 3.2 | Update all passwords according to the approved Security SOP | System | 1 | 0.1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_063 | BRN-LAS_063-S3-3-3 | BRN-LAS_063-S3-3-3-3.3-System | LAS_063 | 3.3 | Test and document the Password policies | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_063 | BRN-LAS_063-S4-2-4 | BRN-LAS_063-S4-2-4-4.1-System | LAS_063 | 4.1 | Issue a User List with the actual status of users | System | 0.1 | 0.5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_063 | BRN-LAS_063-S4-2-4 | BRN-LAS_063-S4-2-4-4.2-Generic | LAS_063 | 4.2 | Issue and approve a Periodic Review for User List | Generic | 0.1 | 0.5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_063 | BRN-LAS_063-S4-2-4 | BRN-LAS_063-S4-2-4-4.3-System | LAS_063 | 4.3 | Execute Periodic Review | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_063 | BRN-LAS_063-S4-2-4 | BRN-LAS_063-S4-2-4-4.4-System | LAS_063 | 4.4 | Setup of periodic task in relevant system | System | 0.2 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_063 | BRN-LAS_063-I1-1-5 | BRN-LAS_063-I1-1-5-5.1-Generic | LAS_063 | 5.1 | Verify if modality and frequency of the backups are defined in an official document with a risk-based approach | Generic | 1 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_063 | BRN-LAS_063-I1-1-5 | BRN-LAS_063-I1-1-5-5.2-System | LAS_063 | 5.2 | If not, execute the risk analyses and reconfigure the backup | System | 0.1 | 0.5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_063 | BRN-LAS_063-I1-1-5 | BRN-LAS_063-I1-1-5-5.3-System | LAS_063 | 5.3 | Test and document the configuration changes | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_063 | BRN-LAS_063-I1-1-5 | BRN-LAS_063-I1-1-5-5.4-System | LAS_063 | 5.4 | Update relevant SOP | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_063 | BRN-LAS_063-I2-1-6 | BRN-LAS_063-I2-1-6-6.1-System | LAS_063 | 6.1 | Change Control Management including impact assessment | System | 0.5 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_063 | BRN-LAS_063-I2-1-6 | BRN-LAS_063-I2-1-6-6.2-System | LAS_063 | 6.2 | Change permissions for users not authorized to modify data, preventing the deletion or alteration. | System | 0.5 | 0 | NO | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_063 | BRN-LAS_063-I2-1-6 | BRN-LAS_063-I2-1-6-6.3-System | LAS_063 | 6.3 | Test and document the configuration changes | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_063 | BRN-LAS_063-I2-1-6 | BRN-LAS_063-I2-1-6-6.4-System | LAS_063 | 6.4 | Update relevant SOP | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_063 | BRN-LAS_063-I3-1-7 | BRN-LAS_063-I3-1-7-7.1-System | LAS_063 | 7.1 | Change Control Management including impact assessment | System | 0.5 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_063 | BRN-LAS_063-I3-1-7 | BRN-LAS_063-I3-1-7-7.2-System | LAS_063 | 7.2 | Configure the protection of input data through an automatic security policy or folder restrictions | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_063 | BRN-LAS_063-I3-1-7 | BRN-LAS_063-I3-1-7-7.3-System | LAS_063 | 7.3 | Configure user privileges to prevent the deletion or alteration of input data | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_063 | BRN-LAS_063-I3-1-7 | BRN-LAS_063-I3-1-7-7.4-System | LAS_063 | 7.4 | Test and document the configuration changes | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_063 | BRN-LAS_063-I3-1-7 | BRN-LAS_063-I3-1-7-7.5-System | LAS_063 | 7.5 | Update relevant SOP | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_063 | BRN-LAS_063-T1-2-8 | BRN-LAS_063-T1-2-8-8.1-System | LAS_063 | 8.1 | Investigate with the supplier if it is possible to implement a proper configuration of the AT | System | 1 | 0 | NO | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_063 | BRN-LAS_063-T1-2-8 | BRN-LAS_063-T1-2-8-8.2-System | LAS_063 | 8.2 | Change Control Management including impact assessment | System | 0.5 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_063 | BRN-LAS_063-T1-2-8 | BRN-LAS_063-T1-2-8-8.3-System | LAS_063 | 8.3 | Configure Audit Trail functionality within the SW or, if not applicable, implement a paper based management for tracking relevant operation (i.e. old&new value, reason for change) to relevant data | System | 2 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_063 | BRN-LAS_063-T1-2-8 | BRN-LAS_063-T1-2-8-8.4-System | LAS_063 | 8.4 | Test and document configuration changes or the procedural changes | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_063 | BRN-LAS_063-T1-2-8 | BRN-LAS_063-T1-2-8-8.5-System | LAS_063 | 8.5 | Update relevant SOP | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_063 | BRN-LAS_063-T3-3-9 | BRN-LAS_063-T3-3-9-9.1-Generic | LAS_063 | 9.1 | Issue and approve a fully compliant Audit Trail Review Working Instruction | Generic | 0.5 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_063 | BRN-LAS_063-T3-3-9 | BRN-LAS_063-T3-3-9-9.2-System | LAS_063 | 9.2 | Execute Audit Trail Review Working Instruction: - perform Data Assessment for Electronic Records managed by the system - update Operational Method SOP (Methods/Instrument) - update test documentation | System | 0.5 | 2.5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_063 | BRN-LAS_063-T3-3-9 | BRN-LAS_063-T3-3-9-9.3-System | LAS_063 | 9.3 | Setup of periodic task | System | 0.2 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_063 | BRN-LAS_063-VD1-1-10 | BRN-LAS_063-VD1-1-10-10.1-System | LAS_063 | 10.1 | Review the Computer System Validation in place and identify the missing/incomplete validation documents or testing protocols | System | 1 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started | Validation Plan not present, Global CSV SOPs not applied., Traceability Matrix is present not complete, VR (called Qualifizierungsbericht, eng. Qualification report) not complete, URS document present but it is missing Functional Process Requirements, Access Control and Security Roles partially covered, no reference to regulatory rules (e.g. Annex11 coverage), Configuration Specification not identified., Risk Assessment not present, IQ and OQ protocols identified, however the level of details is not consistent with DI expectations., PQ not identified.
BRN | BRN-LAS_063 | BRN-LAS_063-VD1-1-10 | BRN-LAS_063-VD1-1-10-10.2-System | LAS_063 | 10.2 | Issue and approve the missing validation documentation | System | 2 | 3 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_063 | BRN-LAS_063-VD1-1-10 | BRN-LAS_063-VD1-1-10-10.3-System | LAS_063 | 10.3 | Perform and document the missing/incomplete tests | System | 3 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_063 | BRN-LAS_063-VD1-1-10 | BRN-LAS_063-VD1-1-10-10.4-System | LAS_063 | 10.4 | Assure the Traceability of the testing with coded requirements against coded test and update the documentation accordingly | System | 2 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_356 | BRN-LAS_356-S1-1-1 | BRN-LAS_356-S1-1-1-1.1-System | LAS_356 | 1.1 | Change Control Management including impact assessment | System | 0.5 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_356 | BRN-LAS_356-S1-1-1 | BRN-LAS_356-S1-1-1-1.2-System | LAS_356 | 1.2 | Update the application SW in order to configure unique and personal accounts. If it is not possible to configure personal account within application SW, implement a proper user management within OS accounts | System | 3 | 3 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_356 | BRN-LAS_356-S1-1-1 | BRN-LAS_356-S1-1-1-1.3-System | LAS_356 | 1.3 | Test and document the configuration changes or procedural changes | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_356 | BRN-LAS_356-S1-1-1 | BRN-LAS_356-S1-1-1-1.4-System | LAS_356 | 1.4 | Issue and approve a User List | System | 0.1 | 0.5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_356 | BRN-LAS_356-S1-1-1 | BRN-LAS_356-S1-1-1-1.5-System | LAS_356 | 1.5 | Update relevant SOPs and periodically review the User List according to procedure | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_356 | BRN-LAS_356-S2-2-2 | BRN-LAS_356-S2-2-2-2.1-System | LAS_356 | 2.1 | Change Control Management including impact assessment | System | 0.5 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_356 | BRN-LAS_356-S2-2-2 | BRN-LAS_356-S2-2-2-2.2-System | LAS_356 | 2.2 | Configure 3 user groups and define the role of each user | System | 1 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_356 | BRN-LAS_356-S2-2-2 | BRN-LAS_356-S2-2-2-2.3-System | LAS_356 | 2.3 | Configure user privileges according to a proper segregation of duties | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_356 | BRN-LAS_356-S2-2-2 | BRN-LAS_356-S2-2-2-2.4-System | LAS_356 | 2.4 | Test and document the configuration changes | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_356 | BRN-LAS_356-S2-2-2 | BRN-LAS_356-S2-2-2-2.5-System | LAS_356 | 2.5 | Update relevant SOP | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_356 | BRN-LAS_356-S3-3-3 | BRN-LAS_356-S3-3-3-3.1-Generic | LAS_356 | 3.1 | Issue and approve a Security SOP with proper PW security features according to best practices (length, complexity, expiring) | Generic | 1 | 5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_356 | BRN-LAS_356-S3-3-3 | BRN-LAS_356-S3-3-3-3.2-System | LAS_356 | 3.2 | Update all passwords according to the approved Security SOP | System | 1 | 0.1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_356 | BRN-LAS_356-S3-3-3 | BRN-LAS_356-S3-3-3-3.3-System | LAS_356 | 3.3 | Test and document the Password policies | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_356 | BRN-LAS_356-S4-2-4 | BRN-LAS_356-S4-2-4-4.1-System | LAS_356 | 4.1 | Issue a User List with the actual status of users | System | 0.1 | 0.5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_356 | BRN-LAS_356-S4-2-4 | BRN-LAS_356-S4-2-4-4.2-Generic | LAS_356 | 4.2 | Issue and approve a Periodic Review for User List | Generic | 0.1 | 0.5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_356 | BRN-LAS_356-S4-2-4 | BRN-LAS_356-S4-2-4-4.3-System | LAS_356 | 4.3 | Execute Periodic Review | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_356 | BRN-LAS_356-S4-2-4 | BRN-LAS_356-S4-2-4-4.4-System | LAS_356 | 4.4 | Setup of periodic task in relevant system | System | 0.2 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_356 | BRN-LAS_356-I2-1-5 | BRN-LAS_356-I2-1-5-5.1-System | LAS_356 | 5.1 | Change Control Management including impact assessment | System | 0.5 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_356 | BRN-LAS_356-I2-1-5 | BRN-LAS_356-I2-1-5-5.2-System | LAS_356 | 5.2 | Change permissions for users not authorized to modify data, preventing the deletion or alteration. | System | 0.5 | 0 | NO | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_356 | BRN-LAS_356-I2-1-5 | BRN-LAS_356-I2-1-5-5.3-System | LAS_356 | 5.3 | Test and document the configuration changes | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_356 | BRN-LAS_356-I2-1-5 | BRN-LAS_356-I2-1-5-5.4-System | LAS_356 | 5.4 | Update relevant SOP | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_356 | BRN-LAS_356-I3-1-6 | BRN-LAS_356-I3-1-6-6.1-System | LAS_356 | 6.1 | Change Control Management including impact assessment | System | 0.5 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_356 | BRN-LAS_356-I3-1-6 | BRN-LAS_356-I3-1-6-6.2-System | LAS_356 | 6.2 | Configure the protection of input data through an automatic security policy or folder restrictions | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_356 | BRN-LAS_356-I3-1-6 | BRN-LAS_356-I3-1-6-6.3-System | LAS_356 | 6.3 | Configure user privileges to prevent the deletion or alteration of input data | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_356 | BRN-LAS_356-I3-1-6 | BRN-LAS_356-I3-1-6-6.4-System | LAS_356 | 6.4 | Test and document the configuration changes | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_356 | BRN-LAS_356-I3-1-6 | BRN-LAS_356-I3-1-6-6.5-System | LAS_356 | 6.5 | Update relevant SOP | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_356 | BRN-LAS_356-T1-1-7 | BRN-LAS_356-T1-1-7-7.1-System | LAS_356 | 7.1 | Investigate with the supplier if it is possible to implement a proper configuration of the AT | System | 1 | 0 | NO | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_356 | BRN-LAS_356-T1-1-7 | BRN-LAS_356-T1-1-7-7.2-System | LAS_356 | 7.2 | Change Control Management including impact assessment | System | 0.5 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_356 | BRN-LAS_356-T1-1-7 | BRN-LAS_356-T1-1-7-7.3-System | LAS_356 | 7.3 | Configure Audit Trail functionality within the SW or, if not applicable, implement a paper based management for tracking relevant operation (i.e. old&new value, reason for change) to relevant data | System | 2 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_356 | BRN-LAS_356-T1-1-7 | BRN-LAS_356-T1-1-7-7.4-System | LAS_356 | 7.4 | Test and document configuration changes or the procedural changes | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_356 | BRN-LAS_356-T1-1-7 | BRN-LAS_356-T1-1-7-7.5-System | LAS_356 | 7.5 | Update relevant SOP | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_356 | BRN-LAS_356-T2-1-8 | BRN-LAS_356-T2-1-8-8.1-System | LAS_356 | 8.1 | Change Control Management including impact assessment | System | 0.5 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_356 | BRN-LAS_356-T2-1-8 | BRN-LAS_356-T2-1-8-8.2-System | LAS_356 | 8.2 | Verify if Time Reference protection can be configured within the system | System | 0.5 | 0.5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_356 | BRN-LAS_356-T2-1-8 | BRN-LAS_356-T2-1-8-8.3-Generic | LAS_356 | 8.3 | If not possible, manage Date & Time protection through an approved procedure | Generic | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_356 | BRN-LAS_356-T2-1-8 | BRN-LAS_356-T2-1-8-8.4-System | LAS_356 | 8.4 | Test and document configuration changes | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_356 | BRN-LAS_356-T2-1-8 | BRN-LAS_356-T2-1-8-8.5-System | LAS_356 | 8.5 | Update relevant SOP | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_356 | BRN-LAS_356-T3-3-9 | BRN-LAS_356-T3-3-9-9.1-Generic | LAS_356 | 9.1 | Issue and approve a fully compliant Audit Trail Review Working Instruction | Generic | 0.5 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_356 | BRN-LAS_356-T3-3-9 | BRN-LAS_356-T3-3-9-9.2-System | LAS_356 | 9.2 | Execute Audit Trail Review Working Instruction: - perform Data Assessment for Electronic Records managed by the system - update Operational Method SOP (Methods/Instrument) - update test documentation | System | 0.5 | 2.5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_356 | BRN-LAS_356-T3-3-9 | BRN-LAS_356-T3-3-9-9.3-System | LAS_356 | 9.3 | Setup of periodic task | System | 0.2 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_356 | BRN-LAS_356-VD1-1-10 | BRN-LAS_356-VD1-1-10-10.1-System | LAS_356 | 10.1 | Review the Computer System Validation in place and identify the missing/incomplete validation documents or testing protocols | System | 1 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started | Validation Plan not present, Global CSV SOPs not applied., Traceability Matrix is present not complete, VR (called Qualifizierungsbericht, eng. Qualification report) not complete, URS document present but it is missing Functional Process Requirements, Access Control and Security Roles partially covered, no reference to regulatory rules (e.g. Annex11 coverage), Configuration Specification not identified., Risk Assessment not present, Testing only for IQ/OQ for the Control System. The level of detail is not consistent with DI expectations, i.e. Security/Integrity/Traceability verifications. Missing tests for documental checks (e.g. Users List, SOPs, etc.), functional checks (Part 11 and Annex 11 verifications), PQ not identified.
BRN | BRN-LAS_356 | BRN-LAS_356-VD1-1-10 | BRN-LAS_356-VD1-1-10-10.2-System | LAS_356 | 10.2 | Issue and approve the missing validation documentation | System | 2 | 3 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_356 | BRN-LAS_356-VD1-1-10 | BRN-LAS_356-VD1-1-10-10.3-System | LAS_356 | 10.3 | Perform and document the missing/incomplete tests | System | 3 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_356 | BRN-LAS_356-VD1-1-10 | BRN-LAS_356-VD1-1-10-10.4-System | LAS_356 | 10.4 | Assure the Traceability of the testing with coded requirements against coded test and update the documentation accordingly | System | 2 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_069 | BRN-LAS_069-S1-1-1 | BRN-LAS_069-S1-1-1-1.1-System | LAS_069 | 1.1 | Change Control Management including impact assessment | System | 0.5 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_069 | BRN-LAS_069-S1-1-1 | BRN-LAS_069-S1-1-1-1.2-System | LAS_069 | 1.2 | Update the application SW in order to configure unique and personal accounts. If it is not possible to configure personal account within application SW, implement a proper user management within OS accounts | System | 3 | 3 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_069 | BRN-LAS_069-S1-1-1 | BRN-LAS_069-S1-1-1-1.3-System | LAS_069 | 1.3 | Test and document the configuration changes or procedural changes | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_069 | BRN-LAS_069-S1-1-1 | BRN-LAS_069-S1-1-1-1.4-System | LAS_069 | 1.4 | Issue and approve a User List | System | 0.1 | 0.5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_069 | BRN-LAS_069-S1-1-1 | BRN-LAS_069-S1-1-1-1.5-System | LAS_069 | 1.5 | Update relevant SOPs and periodically review the User List according to procedure | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_069 | BRN-LAS_069-S2-2-2 | BRN-LAS_069-S2-2-2-2.1-System | LAS_069 | 2.1 | Change Control Management including impact assessment | System | 0.5 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_069 | BRN-LAS_069-S2-2-2 | BRN-LAS_069-S2-2-2-2.2-System | LAS_069 | 2.2 | Configure 3 user groups and define the role of each user | System | 1 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_069 | BRN-LAS_069-S2-2-2 | BRN-LAS_069-S2-2-2-2.3-System | LAS_069 | 2.3 | Configure user privileges according to a proper segregation of duties | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_069 | BRN-LAS_069-S2-2-2 | BRN-LAS_069-S2-2-2-2.4-System | LAS_069 | 2.4 | Test and document the configuration changes | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_069 | BRN-LAS_069-S2-2-2 | BRN-LAS_069-S2-2-2-2.5-System | LAS_069 | 2.5 | Update relevant SOP | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_069 | BRN-LAS_069-S3-3-3 | BRN-LAS_069-S3-3-3-3.1-Generic | LAS_069 | 3.1 | Issue and approve a Security SOP with proper PW security features according to best practices (length, complexity, expiring) | Generic | 1 | 5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_069 | BRN-LAS_069-S3-3-3 | BRN-LAS_069-S3-3-3-3.2-System | LAS_069 | 3.2 | Update all passwords according to the approved Security SOP | System | 1 | 0.1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_069 | BRN-LAS_069-S3-3-3 | BRN-LAS_069-S3-3-3-3.3-System | LAS_069 | 3.3 | Test and document the Password policies | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_069 | BRN-LAS_069-S4-2-4 | BRN-LAS_069-S4-2-4-4.1-System | LAS_069 | 4.1 | Issue a User List with the actual status of users | System | 0.1 | 0.5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_069 | BRN-LAS_069-S4-2-4 | BRN-LAS_069-S4-2-4-4.2-Generic | LAS_069 | 4.2 | Issue and approve a Periodic Review for User List | Generic | 0.1 | 0.5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_069 | BRN-LAS_069-S4-2-4 | BRN-LAS_069-S4-2-4-4.3-System | LAS_069 | 4.3 | Execute Periodic Review | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_069 | BRN-LAS_069-S4-2-4 | BRN-LAS_069-S4-2-4-4.4-System | LAS_069 | 4.4 | Setup of periodic task in relevant system | System | 0.2 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_069 | BRN-LAS_069-I2-1-5 | BRN-LAS_069-I2-1-5-5.1-System | LAS_069 | 5.1 | Change Control Management including impact assessment | System | 0.5 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_069 | BRN-LAS_069-I2-1-5 | BRN-LAS_069-I2-1-5-5.2-System | LAS_069 | 5.2 | Change permissions for users not authorized to modify data, preventing the deletion or alteration. | System | 0.5 | 0 | NO | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_069 | BRN-LAS_069-I2-1-5 | BRN-LAS_069-I2-1-5-5.3-System | LAS_069 | 5.3 | Test and document the configuration changes | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_069 | BRN-LAS_069-I2-1-5 | BRN-LAS_069-I2-1-5-5.4-System | LAS_069 | 5.4 | Update relevant SOP | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_069 | BRN-LAS_069-I3-1-6 | BRN-LAS_069-I3-1-6-6.1-System | LAS_069 | 6.1 | Change Control Management including impact assessment | System | 0.5 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_069 | BRN-LAS_069-I3-1-6 | BRN-LAS_069-I3-1-6-6.2-System | LAS_069 | 6.2 | Configure the protection of input data through an automatic security policy or folder restrictions | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_069 | BRN-LAS_069-I3-1-6 | BRN-LAS_069-I3-1-6-6.3-System | LAS_069 | 6.3 | Configure user privileges to prevent the deletion or alteration of input data | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_069 | BRN-LAS_069-I3-1-6 | BRN-LAS_069-I3-1-6-6.4-System | LAS_069 | 6.4 | Test and document the configuration changes | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_069 | BRN-LAS_069-I3-1-6 | BRN-LAS_069-I3-1-6-6.5-System | LAS_069 | 6.5 | Update relevant SOP | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_069 | BRN-LAS_069-T1-1-7 | BRN-LAS_069-T1-1-7-7.1-System | LAS_069 | 7.1 | Investigate with the supplier if it is possible to implement a proper configuration of the AT | System | 1 | 0 | NO | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_069 | BRN-LAS_069-T1-1-7 | BRN-LAS_069-T1-1-7-7.2-System | LAS_069 | 7.2 | Change Control Management including impact assessment | System | 0.5 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_069 | BRN-LAS_069-T1-1-7 | BRN-LAS_069-T1-1-7-7.3-System | LAS_069 | 7.3 | Configure Audit Trail functionality within the SW or, if not applicable, implement a paper based management for tracking relevant operation (i.e. old&new value, reason for change) to relevant data | System | 2 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_069 | BRN-LAS_069-T1-1-7 | BRN-LAS_069-T1-1-7-7.4-System | LAS_069 | 7.4 | Test and document configuration changes or the procedural changes | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_069 | BRN-LAS_069-T1-1-7 | BRN-LAS_069-T1-1-7-7.5-System | LAS_069 | 7.5 | Update relevant SOP | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_069 | BRN-LAS_069-T2-1-8 | BRN-LAS_069-T2-1-8-8.1-System | LAS_069 | 8.1 | Change Control Management including impact assessment | System | 0.5 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_069 | BRN-LAS_069-T2-1-8 | BRN-LAS_069-T2-1-8-8.2-System | LAS_069 | 8.2 | Verify if Time Reference protection can be configured within the system | System | 0.5 | 0.5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_069 | BRN-LAS_069-T2-1-8 | BRN-LAS_069-T2-1-8-8.3-Generic | LAS_069 | 8.3 | If not possible, manage Date & Time protection through an approved procedure | Generic | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_069 | BRN-LAS_069-T2-1-8 | BRN-LAS_069-T2-1-8-8.4-System | LAS_069 | 8.4 | Test and document configuration changes | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_069 | BRN-LAS_069-T2-1-8 | BRN-LAS_069-T2-1-8-8.5-System | LAS_069 | 8.5 | Update relevant SOP | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_069 | BRN-LAS_069-T3-3-9 | BRN-LAS_069-T3-3-9-9.1-Generic | LAS_069 | 9.1 | Issue and approve a fully compliant Audit Trail Review Working Instruction | Generic | 0.5 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_069 | BRN-LAS_069-T3-3-9 | BRN-LAS_069-T3-3-9-9.2-System | LAS_069 | 9.2 | Execute Audit Trail Review Working Instruction: - perform Data Assessment for Electronic Records managed by the system - update Operational Method SOP (Methods/Instrument) - update test documentation | System | 0.5 | 2.5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_069 | BRN-LAS_069-T3-3-9 | BRN-LAS_069-T3-3-9-9.3-System | LAS_069 | 9.3 | Setup of periodic task | System | 0.2 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_069 | BRN-LAS_069-VD1-1-10 | BRN-LAS_069-VD1-1-10-10.1-System | LAS_069 | 10.1 | Review the Computer System Validation in place and identify the missing/incomplete validation documents or testing protocols | System | 1 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started | Validation Plan not present, Global CSV SOPs not applied., Traceability Matrix is present not complete, VR (called Qualifizierungsbericht, eng. Qualification report) not complete, URS document present but it is missing Functional Process Requirements, Access Control and Security Roles partially covered, no reference to regulatory rules (e.g. Annex11 coverage), Configuration Specification not identified., Risk Assessment not present, Testing only for IQ/OQ for the Control System. The level of detail is not consistent with DI expectations, i.e. Security/Integrity/Traceability verifications. Missing tests for documental checks (e.g. Users List, SOPs, etc.), functional checks (Part 11 and Annex 11 verifications), PQ not identified.
BRN | BRN-LAS_069 | BRN-LAS_069-VD1-1-10 | BRN-LAS_069-VD1-1-10-10.2-System | LAS_069 | 10.2 | Issue and approve the missing validation documentation | System | 2 | 3 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_069 | BRN-LAS_069-VD1-1-10 | BRN-LAS_069-VD1-1-10-10.3-System | LAS_069 | 10.3 | Perform and document the missing/incomplete tests | System | 3 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_069 | BRN-LAS_069-VD1-1-10 | BRN-LAS_069-VD1-1-10-10.4-System | LAS_069 | 10.4 | Assure the Traceability of the testing with coded requirements against coded test and update the documentation accordingly | System | 2 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_074 | BRN-LAS_074-S3-4-1 | BRN-LAS_074-S3-4-1-1.1-Generic | LAS_074 | 1.1 | Issue and approve a Security SOP with proper PW security features according to best practices (length, complexity, expiring) | Generic | 1 | 5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_074 | BRN-LAS_074-S3-4-1 | BRN-LAS_074-S3-4-1-1.2-System | LAS_074 | 1.2 | Update all passwords according to the approved Security SOP | System | 1 | 0.1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_074 | BRN-LAS_074-S3-4-1 | BRN-LAS_074-S3-4-1-1.3-System | LAS_074 | 1.3 | Test and document the Password policies | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_074 | BRN-LAS_074-S4-3-2 | BRN-LAS_074-S4-3-2-2.1-System | LAS_074 | 2.1 | Issue a User List with the actual status of users | System | 0.1 | 0.5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_074 | BRN-LAS_074-S4-3-2 | BRN-LAS_074-S4-3-2-2.2-Generic | LAS_074 | 2.2 | Issue and approve a Periodic Review for User List | Generic | 0.1 | 0.5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_074 | BRN-LAS_074-S4-3-2 | BRN-LAS_074-S4-3-2-2.3-System | LAS_074 | 2.3 | Execute Periodic Review | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_074 | BRN-LAS_074-S4-3-2 | BRN-LAS_074-S4-3-2-2.4-System | LAS_074 | 2.4 | Setup of periodic task in relevant system | System | 0.2 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_074 | BRN-LAS_074-I1-2-3 | BRN-LAS_074-I1-2-3-3.1-System | LAS_074 | 3.1 | Change Control Management including impact assessment | System | 0.5 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_074 | BRN-LAS_074-I1-2-3 | BRN-LAS_074-I1-2-3-3.2-System | LAS_074 | 3.2 | Implement a process of automatic data backup | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_074 | BRN-LAS_074-I1-2-3 | BRN-LAS_074-I1-2-3-3.3-Generic | LAS_074 | 3.3 | If automatic backup its not possible, document manual backups of system data with a proper frequency to be defined in a dedicated procedure | Generic | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_074 | BRN-LAS_074-I1-2-3 | BRN-LAS_074-I1-2-3-3.4-System | LAS_074 | 3.4 | Test and document the implemented changes | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_074 | BRN-LAS_074-I1-2-3 | BRN-LAS_074-I1-2-3-3.5-System | LAS_074 | 3.5 | Update relevant SOP | System | 0.2 | 0.2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_074 | BRN-LAS_074-T2-2-4 | BRN-LAS_074-T2-2-4-4.1-System | LAS_074 | 4.1 | Change Control Management including impact assessment | System | 0.5 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_074 | BRN-LAS_074-T2-2-4 | BRN-LAS_074-T2-2-4-4.2-System | LAS_074 | 4.2 | Verify if Time Reference protection can be configured within the system | System | 0.5 | 0.5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_074 | BRN-LAS_074-T2-2-4 | BRN-LAS_074-T2-2-4-4.3-Generic | LAS_074 | 4.3 | If not possible, manage Date & Time protection through an approved procedure | Generic | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_074 | BRN-LAS_074-T2-2-4 | BRN-LAS_074-T2-2-4-4.4-System | LAS_074 | 4.4 | Test and document configuration changes | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_074 | BRN-LAS_074-T2-2-4 | BRN-LAS_074-T2-2-4-4.5-System | LAS_074 | 4.5 | Update relevant SOP | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_074 | BRN-LAS_074-T3-3-5 | BRN-LAS_074-T3-3-5-5.1-Generic | LAS_074 | 5.1 | Issue and approve a fully compliant Audit Trail Review Working Instruction | Generic | 0.5 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_074 | BRN-LAS_074-T3-3-5 | BRN-LAS_074-T3-3-5-5.2-System | LAS_074 | 5.2 | Execute Audit Trail Review Working Instruction: - perform Data Assessment for Electronic Records managed by the system - update Operational Method SOP (Methods/Instrument) - update test documentation | System | 0.5 | 2.5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_074 | BRN-LAS_074-T3-3-5 | BRN-LAS_074-T3-3-5-5.3-System | LAS_074 | 5.3 | Setup of periodic task | System | 0.2 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_074 | BRN-LAS_074-VD1-2-6 | BRN-LAS_074-VD1-2-6-6.1-System | LAS_074 | 6.1 | Review the Computer System Validation in place and identify the missing/incomplete validation documents or testing protocols | System | 1 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started | Validation Plan not present, Global CSV SOPs not applied., Traceability Matrix is not present, VR (called Qualifizierungsbericht, eng. Qualification report) not complete, URS document present but it is missing Functional Process Requirements, Access Control and Security Roles partially covered, no reference to regulatory rules (e.g. Annex11 coverage), Not present, partially covered in delivered vendor documentation, Risk Assessment not present, Testing only for IQ/OQ for the Control System. The level of detail is not consistent with DI expectations, i.e. Security/Integrity/Traceability verifications. Missing tests for documental checks (e.g. Users List, SOPs, etc.), functional checks (Part 11 and Annex 11 verifications), PQ not identified.
BRN | BRN-LAS_074 | BRN-LAS_074-VD1-2-6 | BRN-LAS_074-VD1-2-6-6.2-System | LAS_074 | 6.2 | Issue and approve the missing validation documentation | System | 2 | 3 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_074 | BRN-LAS_074-VD1-2-6 | BRN-LAS_074-VD1-2-6-6.3-System | LAS_074 | 6.3 | Perform and document the missing/incomplete tests | System | 3 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_074 | BRN-LAS_074-VD1-2-6 | BRN-LAS_074-VD1-2-6-6.4-System | LAS_074 | 6.4 | Assure the Traceability of the testing with coded requirements against coded test and update the documentation accordingly | System | 2 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_076 | BRN-LAS_076-S3-4-1 | BRN-LAS_076-S3-4-1-1.1-Generic | LAS_076 | 1.1 | Issue and approve a Security SOP with proper PW security features according to best practices (length, complexity, expiring) | Generic | 1 | 5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto |  | To be started | From Dario: Design security Model fully managed by Roche. FMEAS needed because o tech limitation.
BRN | BRN-LAS_076 | BRN-LAS_076-S3-4-1 | BRN-LAS_076-S3-4-1-1.2-System | LAS_076 | 1.2 | Update all passwords according to the approved Security SOP | System | 1 | 0.1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto |  | To be started | From Dario: Design security Model fully managed by Roche. FMEAS needed because o tech limitation.
BRN | BRN-LAS_076 | BRN-LAS_076-S3-4-1 | BRN-LAS_076-S3-4-1-1.3-System | LAS_076 | 1.3 | Test and document the Password policies | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto |  | To be started | From Dario: Design security Model fully managed by Roche. FMEAS needed because o tech limitation.
BRN | BRN-LAS_076 | BRN-LAS_076-S4-3-2 | BRN-LAS_076-S4-3-2-2.1-System | LAS_076 | 2.1 | Issue a User List with the actual status of users | System | 0.1 | 0.5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto |  | To be started | From Dario: Design security Model fully managed by Roche. FMEAS needed because o tech limitation.
BRN | BRN-LAS_076 | BRN-LAS_076-S4-3-2 | BRN-LAS_076-S4-3-2-2.2-Generic | LAS_076 | 2.2 | Issue and approve a Periodic Review for User List | Generic | 0.1 | 0.5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto |  | To be started | From Dario: Design security Model fully managed by Roche. FMEAS needed because o tech limitation.
BRN | BRN-LAS_076 | BRN-LAS_076-S4-3-2 | BRN-LAS_076-S4-3-2-2.3-System | LAS_076 | 2.3 | Execute Periodic Review | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto |  | To be started | From Dario: Design security Model fully managed by Roche. FMEAS needed because o tech limitation.
BRN | BRN-LAS_076 | BRN-LAS_076-S4-3-2 | BRN-LAS_076-S4-3-2-2.4-System | LAS_076 | 2.4 | Setup of periodic task in relevant system | System | 0.2 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto |  | To be started | From Dario: Design security Model fully managed by Roche. FMEAS needed because o tech limitation.
BRN | BRN-LAS_076 | BRN-LAS_076-T3-3-3 | BRN-LAS_076-T3-3-3-3.1-Generic | LAS_076 | 3.1 | Issue and approve a fully compliant Audit Trail Review Working Instruction | Generic | 0.5 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto |  | To be started | From Dario: Design security Model fully managed by Roche. FMEAS needed because o tech limitation.
BRN | BRN-LAS_076 | BRN-LAS_076-T3-3-3 | BRN-LAS_076-T3-3-3-3.2-System | LAS_076 | 3.2 | Execute Audit Trail Review Working Instruction: - perform Data Assessment for Electronic Records managed by the system - update Operational Method SOP (Methods/Instrument) - update test documentation | System | 0.5 | 2.5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto |  | To be started | From Dario: Design security Model fully managed by Roche. FMEAS needed because o tech limitation.
BRN | BRN-LAS_076 | BRN-LAS_076-T3-3-3 | BRN-LAS_076-T3-3-3-3.3-System | LAS_076 | 3.3 | Setup of periodic task | System | 0.2 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto |  | To be started | From Dario: Design security Model fully managed by Roche. FMEAS needed because o tech limitation.
BRN | BRN-LAS_076 | BRN-LAS_076-VD1-2-4 | BRN-LAS_076-VD1-2-4-4.1-System | LAS_076 | 4.1 | Review the Computer System Validation in place and identify the missing/incomplete validation documents or testing protocols | System | 1 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2026-12-31 | To be started | Validation Plan not present, Global CSV SOPs not applied., VR (called Qualifizierungsbericht, eng. Qualification report) not complete, URS document present but it is missing Functional Process Requirements, Access Control and Security Roles partially covered, no reference to regulatory rules (e.g. Annex11 coverage), Not present, partially covered in delivered vendor documentation, , Testing only for IQ/OQ for the Control System. The level of detail is not consistent with DI expectations, i.e. Security/Integrity/Traceability verifications. Missing tests for documental checks (e.g. Users List, SOPs, etc.), functional checks (Part 11 and Annex 11 verifications), PQ not identified.
BRN | BRN-LAS_076 | BRN-LAS_076-VD1-2-4 | BRN-LAS_076-VD1-2-4-4.2-System | LAS_076 | 4.2 | Issue and approve the missing validation documentation | System | 2 | 3 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2026-12-31 | To be started | From Dario: Design security Model fully managed by Roche. FMEAS needed because o tech limitation.
BRN | BRN-LAS_076 | BRN-LAS_076-VD1-2-4 | BRN-LAS_076-VD1-2-4-4.3-System | LAS_076 | 4.3 | Perform and document the missing/incomplete tests | System | 3 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2026-12-31 | To be started | From Dario: Design security Model fully managed by Roche. FMEAS needed because o tech limitation.
BRN | BRN-LAS_076 | BRN-LAS_076-VD1-2-4 | BRN-LAS_076-VD1-2-4-4.4-System | LAS_076 | 4.4 | Assure the Traceability of the testing with coded requirements against coded test and update the documentation accordingly | System | 2 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2026-12-31 | To be started | From Dario: Design security Model fully managed by Roche. FMEAS needed because o tech limitation.
BRN | BRN-LAS_089 | BRN-LAS_089-I1-1-1 | BRN-LAS_089-I1-1-1-1.1-System | LAS_089 | 1.1 | Change Control Management including impact assessment | System | 0.5 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 30/04/2025 | To be started
BRN | BRN-LAS_089 | BRN-LAS_089-I1-1-1 | BRN-LAS_089-I1-1-1-1.2-System | LAS_089 | 1.2 | Implement a process of automatic data backup | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 30/04/2025 | To be started
BRN | BRN-LAS_089 | BRN-LAS_089-I1-1-1 | BRN-LAS_089-I1-1-1-1.3-Generic | LAS_089 | 1.3 | If automatic backup its not possible, document manual backups of system data with a proper frequency to be defined in a dedicated procedure | Generic | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 30/04/2025 | To be started
BRN | BRN-LAS_089 | BRN-LAS_089-I1-1-1 | BRN-LAS_089-I1-1-1-1.4-System | LAS_089 | 1.4 | Test and document the implemented changes | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 30/04/2025 | To be started
BRN | BRN-LAS_089 | BRN-LAS_089-I1-1-1 | BRN-LAS_089-I1-1-1-1.5-System | LAS_089 | 1.5 | Update relevant SOP | System | 0.2 | 0.2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 30/04/2025 | To be started
BRN | BRN-LAS_089 | BRN-LAS_089-I3-1-2 | BRN-LAS_089-I3-1-2-2.1-System | LAS_089 | 2.1 | Change Control Management including impact assessment | System | 0.5 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 30/04/2025 | To be started
BRN | BRN-LAS_089 | BRN-LAS_089-I3-1-2 | BRN-LAS_089-I3-1-2-2.2-System | LAS_089 | 2.2 | Configure the protection of input data through an automatic security policy or folder restrictions | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 30/04/2025 | To be started
BRN | BRN-LAS_089 | BRN-LAS_089-I3-1-2 | BRN-LAS_089-I3-1-2-2.3-System | LAS_089 | 2.3 | Configure user privileges to prevent the deletion or alteration of input data | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 30/04/2025 | To be started
BRN | BRN-LAS_089 | BRN-LAS_089-I3-1-2 | BRN-LAS_089-I3-1-2-2.4-System | LAS_089 | 2.4 | Test and document the configuration changes | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 30/04/2025 | To be started
BRN | BRN-LAS_089 | BRN-LAS_089-I3-1-2 | BRN-LAS_089-I3-1-2-2.5-System | LAS_089 | 2.5 | Update relevant SOP | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 30/04/2025 | To be started
BRN | BRN-LAS_089 | BRN-LAS_089-T3-2-3 | BRN-LAS_089-T3-2-3-3.1-Generic | LAS_089 | 3.1 | Issue and approve a fully compliant Audit Trail Review Working Instruction | Generic | 0.5 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 30/04/2025 | To be started
BRN | BRN-LAS_089 | BRN-LAS_089-T3-2-3 | BRN-LAS_089-T3-2-3-3.2-System | LAS_089 | 3.2 | Execute Audit Trail Review Working Instruction: - perform Data Assessment for Electronic Records managed by the system - update Operational Method SOP (Methods/Instrument) - update test documentation | System | 0.5 | 2.5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 30/04/2025 | To be started
BRN | BRN-LAS_089 | BRN-LAS_089-T3-2-3 | BRN-LAS_089-T3-2-3-3.3-System | LAS_089 | 3.3 | Setup of periodic task | System | 0.2 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 30/04/2025 | To be started
BRN | BRN-LAS_089 | BRN-LAS_089-VD1-1-4 | BRN-LAS_089-VD1-1-4-4.1-System | LAS_089 | 4.1 | Review the Computer System Validation in place and identify the missing/incomplete validation documents or testing protocols | System | 1 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 30/04/2025 | To be started | Validation Plan not present, Global CSV SOPs not applied., VR (called Qualifizierungsbericht, eng. Qualification report) not complete, URS Document present, however does not reference regulatory requirements (the general 21CFR Part 11 Compliance is present but should be broken down to the specific requirements to meet the expectation). , Not present, partially covered in delivered vendor documentation, Risk Assessment not complete, Supplier testing has been performed and it can be leveraged to cover partially the SW configuration, users, privileges, back and access control. Detailed revision shall be performed and the remaining elements tested in additional validation protocol
BRN | BRN-LAS_089 | BRN-LAS_089-VD1-1-4 | BRN-LAS_089-VD1-1-4-4.2-System | LAS_089 | 4.2 | Issue and approve the missing validation documentation | System | 2 | 3 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 30/04/2025 | To be started
BRN | BRN-LAS_089 | BRN-LAS_089-VD1-1-4 | BRN-LAS_089-VD1-1-4-4.3-System | LAS_089 | 4.3 | Perform and document the missing/incomplete tests | System | 3 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 30/04/2025 | To be started
BRN | BRN-LAS_089 | BRN-LAS_089-VD1-1-4 | BRN-LAS_089-VD1-1-4-4.4-System | LAS_089 | 4.4 | Assure the Traceability of the testing with coded requirements against coded test and update the documentation accordingly | System | 2 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 30/04/2025 | To be started
BRN | BRN-LAS_090 | BRN-LAS_090-I1-2-1 | BRN-LAS_090-I1-2-1-1.1-System | LAS_090 | 1.1 | Change Control Management including impact assessment | System | 0.5 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 30/04/2025 | To be started
BRN | BRN-LAS_090 | BRN-LAS_090-I1-2-1 | BRN-LAS_090-I1-2-1-1.2-System | LAS_090 | 1.2 | Implement a process of automatic data backup | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 30/04/2025 | To be started
BRN | BRN-LAS_090 | BRN-LAS_090-I1-2-1 | BRN-LAS_090-I1-2-1-1.3-Generic | LAS_090 | 1.3 | If automatic backup its not possible, document manual backups of system data with a proper frequency to be defined in a dedicated procedure | Generic | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 30/04/2025 | To be started
BRN | BRN-LAS_090 | BRN-LAS_090-I1-2-1 | BRN-LAS_090-I1-2-1-1.4-System | LAS_090 | 1.4 | Test and document the implemented changes | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 30/04/2025 | To be started
BRN | BRN-LAS_090 | BRN-LAS_090-I1-2-1 | BRN-LAS_090-I1-2-1-1.5-System | LAS_090 | 1.5 | Update relevant SOP | System | 0.2 | 0.2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 30/04/2025 | To be started
BRN | BRN-LAS_090 | BRN-LAS_090-I3-2-2 | BRN-LAS_090-I3-2-2-2.1-System | LAS_090 | 2.1 | Change Control Management including impact assessment | System | 0.5 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 30/04/2025 | To be started
BRN | BRN-LAS_090 | BRN-LAS_090-I3-2-2 | BRN-LAS_090-I3-2-2-2.2-System | LAS_090 | 2.2 | Configure the protection of input data through an automatic security policy or folder restrictions | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 30/04/2025 | To be started
BRN | BRN-LAS_090 | BRN-LAS_090-I3-2-2 | BRN-LAS_090-I3-2-2-2.3-System | LAS_090 | 2.3 | Configure user privileges to prevent the deletion or alteration of input data | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 30/04/2025 | To be started
BRN | BRN-LAS_090 | BRN-LAS_090-I3-2-2 | BRN-LAS_090-I3-2-2-2.4-System | LAS_090 | 2.4 | Test and document the configuration changes | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 30/04/2025 | To be started
BRN | BRN-LAS_090 | BRN-LAS_090-I3-2-2 | BRN-LAS_090-I3-2-2-2.5-System | LAS_090 | 2.5 | Update relevant SOP | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 30/04/2025 | To be started
BRN | BRN-LAS_090 | BRN-LAS_090-T3-3-3 | BRN-LAS_090-T3-3-3-3.1-Generic | LAS_090 | 3.1 | Issue and approve a fully compliant Audit Trail Review Working Instruction | Generic | 0.5 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 30/04/2025 | To be started
BRN | BRN-LAS_090 | BRN-LAS_090-T3-3-3 | BRN-LAS_090-T3-3-3-3.2-System | LAS_090 | 3.2 | Execute Audit Trail Review Working Instruction: - perform Data Assessment for Electronic Records managed by the system - update Operational Method SOP (Methods/Instrument) - update test documentation | System | 0.5 | 2.5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 30/04/2025 | To be started
BRN | BRN-LAS_090 | BRN-LAS_090-T3-3-3 | BRN-LAS_090-T3-3-3-3.3-System | LAS_090 | 3.3 | Setup of periodic task | System | 0.2 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 30/04/2025 | To be started
BRN | BRN-LAS_090 | BRN-LAS_090-VD1-2-4 | BRN-LAS_090-VD1-2-4-4.1-System | LAS_090 | 4.1 | Review the Computer System Validation in place and identify the missing/incomplete validation documents or testing protocols | System | 1 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 30/04/2025 | To be started | Validation Plan not present, Global CSV SOPs not applied., VR (called Qualifizierungsbericht, eng. Qualification report) not complete, URS Document present, however does not reference regulatory requirements (the general 21CFR Part 11 Compliance is present but should be broken down to the specific requirements to meet the expectation). , Not present, partially covered in delivered vendor documentation, Risk Assessment not complete, Supplier testing has been performed and it can be leveraged to cover partially the SW configuration, users, privileges, back and access control. Detailed revision shall be performed and the remaining elements tested in additional validation protocol
BRN | BRN-LAS_090 | BRN-LAS_090-VD1-2-4 | BRN-LAS_090-VD1-2-4-4.2-System | LAS_090 | 4.2 | Issue and approve the missing validation documentation | System | 2 | 3 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 30/04/2025 | To be started
BRN | BRN-LAS_090 | BRN-LAS_090-VD1-2-4 | BRN-LAS_090-VD1-2-4-4.3-System | LAS_090 | 4.3 | Perform and document the missing/incomplete tests | System | 3 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 30/04/2025 | To be started
BRN | BRN-LAS_090 | BRN-LAS_090-VD1-2-4 | BRN-LAS_090-VD1-2-4-4.4-System | LAS_090 | 4.4 | Assure the Traceability of the testing with coded requirements against coded test and update the documentation accordingly | System | 2 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 30/04/2025 | To be started
BRN | BRN-LAS_097 | BRN-LAS_097-S1-1-1 | BRN-LAS_097-S1-1-1-1.1-System | LAS_097 | 1.1 | Change Control Management including impact assessment | System | 0.5 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_097 | BRN-LAS_097-S1-1-1 | BRN-LAS_097-S1-1-1-1.2-System | LAS_097 | 1.2 | Create personal and unique accounts in system | System | 1 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_097 | BRN-LAS_097-S1-1-1 | BRN-LAS_097-S1-1-1-1.3-System | LAS_097 | 1.3 | Remove generic accounts from the system | System | 0.5 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_097 | BRN-LAS_097-S1-1-1 | BRN-LAS_097-S1-1-1-1.4-System | LAS_097 | 1.4 | Issue and approve an updated User List | System | 0.1 | 0.5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_097 | BRN-LAS_097-S1-1-1 | BRN-LAS_097-S1-1-1-1.5-System | LAS_097 | 1.5 | Update relevant SOPs and periodically review the User List according to procedure | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_097 | BRN-LAS_097-S2-2-2 | BRN-LAS_097-S2-2-2-2.1-System | LAS_097 | 2.1 | Investigate with the supplier if it is possible to implement a proper configuration of user groups with segregation of duties | System | 1 | 0 | NO | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_097 | BRN-LAS_097-S2-2-2 | BRN-LAS_097-S2-2-2-2.2-System | LAS_097 | 2.2 | Change Control Management including impact assessment | System | 0.5 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_097 | BRN-LAS_097-S2-2-2 | BRN-LAS_097-S2-2-2-2.3-System | LAS_097 | 2.3 | Configure 3 user groups and define the role of each user | System | 1 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_097 | BRN-LAS_097-S2-2-2 | BRN-LAS_097-S2-2-2-2.4-System | LAS_097 | 2.4 | Configure user privileges according to a proper segregation of duties | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_097 | BRN-LAS_097-S2-2-2 | BRN-LAS_097-S2-2-2-2.5-System | LAS_097 | 2.5 | Test and document the configuration changes | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_097 | BRN-LAS_097-S2-2-2 | BRN-LAS_097-S2-2-2-2.6-System | LAS_097 | 2.6 | Update relevant SOP | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_097 | BRN-LAS_097-S3-3-3 | BRN-LAS_097-S3-3-3-3.1-System | LAS_097 | 3.1 | Investigate with the supplier if it is possible to upgrade the software to grant proper security features for user access | System | 1 | 0 | NO | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_097 | BRN-LAS_097-S3-3-3 | BRN-LAS_097-S3-3-3-3.2-Generic | LAS_097 | 3.2 | Define the Password features in an approved procedure | Generic | 1 | 3 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_097 | BRN-LAS_097-S3-3-3 | BRN-LAS_097-S3-3-3-3.3-System | LAS_097 | 3.3 | Personnel training to access the system | System | 0.5 | 0.5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_097 | BRN-LAS_097-S3-3-3 | BRN-LAS_097-S3-3-3-3.4-System | LAS_097 | 3.4 | Update relevant SOP | System | 0.2 | 0.2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_097 | BRN-LAS_097-S4-2-4 | BRN-LAS_097-S4-2-4-4.1-System | LAS_097 | 4.1 | Issue a User List with the actual status of users | System | 0.1 | 0.5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_097 | BRN-LAS_097-S4-2-4 | BRN-LAS_097-S4-2-4-4.2-Generic | LAS_097 | 4.2 | Issue and approve a Periodic Review for User List | Generic | 0.1 | 0.5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_097 | BRN-LAS_097-S4-2-4 | BRN-LAS_097-S4-2-4-4.3-System | LAS_097 | 4.3 | Execute Periodic Review | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_097 | BRN-LAS_097-S4-2-4 | BRN-LAS_097-S4-2-4-4.4-System | LAS_097 | 4.4 | Setup of periodic task in relevant system | System | 0.2 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_097 | BRN-LAS_097-I1-1-5 | BRN-LAS_097-I1-1-5-5.1-System | LAS_097 | 5.1 | Change Control Management including impact assessment | System | 0.5 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_097 | BRN-LAS_097-I1-1-5 | BRN-LAS_097-I1-1-5-5.2-System | LAS_097 | 5.2 | Implement a process of automatic data backup | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_097 | BRN-LAS_097-I1-1-5 | BRN-LAS_097-I1-1-5-5.3-Generic | LAS_097 | 5.3 | If automatic backup its not possible, document manual backups of system data with a proper frequency to be defined in a dedicated procedure | Generic | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_097 | BRN-LAS_097-I1-1-5 | BRN-LAS_097-I1-1-5-5.4-System | LAS_097 | 5.4 | Test and document the implemented changes | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_097 | BRN-LAS_097-I1-1-5 | BRN-LAS_097-I1-1-5-5.5-System | LAS_097 | 5.5 | Update relevant SOP | System | 0.2 | 0.2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_097 | BRN-LAS_097-I2-1-6 | BRN-LAS_097-I2-1-6-6.1-System | LAS_097 | 6.1 | Change Control Management including impact assessment | System | 0.5 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_097 | BRN-LAS_097-I2-1-6 | BRN-LAS_097-I2-1-6-6.2-System | LAS_097 | 6.2 | Change permissions for users not authorized to modify data, preventing the deletion or alteration. | System | 0.5 | 0 | NO | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_097 | BRN-LAS_097-I2-1-6 | BRN-LAS_097-I2-1-6-6.3-System | LAS_097 | 6.3 | Test and document the configuration changes | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_097 | BRN-LAS_097-I2-1-6 | BRN-LAS_097-I2-1-6-6.4-System | LAS_097 | 6.4 | Update relevant SOP | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_097 | BRN-LAS_097-I3-1-7 | BRN-LAS_097-I3-1-7-7.1-System | LAS_097 | 7.1 | Change Control Management including impact assessment | System | 0.5 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_097 | BRN-LAS_097-I3-1-7 | BRN-LAS_097-I3-1-7-7.2-System | LAS_097 | 7.2 | Configure the protection of input data through an automatic security policy or folder restrictions | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_097 | BRN-LAS_097-I3-1-7 | BRN-LAS_097-I3-1-7-7.3-System | LAS_097 | 7.3 | Configure user privileges to prevent the deletion or alteration of input data | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_097 | BRN-LAS_097-I3-1-7 | BRN-LAS_097-I3-1-7-7.4-System | LAS_097 | 7.4 | Test and document the configuration changes | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_097 | BRN-LAS_097-I3-1-7 | BRN-LAS_097-I3-1-7-7.5-System | LAS_097 | 7.5 | Update relevant SOP | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_097 | BRN-LAS_097-T1-1-8 | BRN-LAS_097-T1-1-8-8.1-System | LAS_097 | 8.1 | Investigate with the supplier if it is possible to implement a proper configuration of the AT | System | 1 | 0 | NO | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_097 | BRN-LAS_097-T1-1-8 | BRN-LAS_097-T1-1-8-8.2-System | LAS_097 | 8.2 | Change Control Management including impact assessment | System | 0.5 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_097 | BRN-LAS_097-T1-1-8 | BRN-LAS_097-T1-1-8-8.3-System | LAS_097 | 8.3 | Configure Audit Trail functionality within the SW or, if not applicable, implement a paper based management for tracking relevant operation (i.e. old&new value, reason for change) to relevant data | System | 2 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_097 | BRN-LAS_097-T1-1-8 | BRN-LAS_097-T1-1-8-8.4-System | LAS_097 | 8.4 | Test and document configuration changes or the procedural changes | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_097 | BRN-LAS_097-T1-1-8 | BRN-LAS_097-T1-1-8-8.5-System | LAS_097 | 8.5 | Update relevant SOP | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_097 | BRN-LAS_097-T3-2-9 | BRN-LAS_097-T3-2-9-9.1-Generic | LAS_097 | 9.1 | Issue and approve a fully compliant Audit Trail Review Working Instruction | Generic | 0.5 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_097 | BRN-LAS_097-T3-2-9 | BRN-LAS_097-T3-2-9-9.2-System | LAS_097 | 9.2 | Execute Audit Trail Review Working Instruction: - perform Data Assessment for Electronic Records managed by the system - update Operational Method SOP (Methods/Instrument) - update test documentation | System | 0.5 | 2.5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_097 | BRN-LAS_097-T3-2-9 | BRN-LAS_097-T3-2-9-9.3-System | LAS_097 | 9.3 | Setup of periodic task | System | 0.2 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_097 | BRN-LAS_097-VD1-1-10 | BRN-LAS_097-VD1-1-10-10.1-System | LAS_097 | 10.1 | Review the Computer System Validation in place and identify the missing/incomplete validation documents or testing protocols | System | 1 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started | Validation Plan not present, Global CSV SOPs not applied., Traceability Matrix is not present, VR (called Qualifizierungsbericht, eng. Qualification report) not complete, URS document present but it is missing Functional Process Requirements, Access Control and Security Roles partially covered, no reference to regulatory rules (e.g. Annex11 coverage), Not complete, Risk Assessment not present, System decommissioned
BRN | BRN-LAS_097 | BRN-LAS_097-VD1-1-10 | BRN-LAS_097-VD1-1-10-10.2-System | LAS_097 | 10.2 | Issue and approve the missing validation documentation | System | 2 | 3 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_097 | BRN-LAS_097-VD1-1-10 | BRN-LAS_097-VD1-1-10-10.3-System | LAS_097 | 10.3 | Perform and document the missing/incomplete tests | System | 3 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_097 | BRN-LAS_097-VD1-1-10 | BRN-LAS_097-VD1-1-10-10.4-System | LAS_097 | 10.4 | Assure the Traceability of the testing with coded requirements against coded test and update the documentation accordingly | System | 2 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_098 | BRN-LAS_098-S1-2-1 | BRN-LAS_098-S1-2-1-1.1-System | LAS_098 | 1.1 | Change Control Management including impact assessment | System | 0.5 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_098 | BRN-LAS_098-S1-2-1 | BRN-LAS_098-S1-2-1-1.2-System | LAS_098 | 1.2 | Create personal and unique accounts in system | System | 1 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_098 | BRN-LAS_098-S1-2-1 | BRN-LAS_098-S1-2-1-1.3-System | LAS_098 | 1.3 | Remove generic accounts from the system | System | 0.5 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_098 | BRN-LAS_098-S1-2-1 | BRN-LAS_098-S1-2-1-1.4-System | LAS_098 | 1.4 | Issue and approve an updated User List | System | 0.1 | 0.5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_098 | BRN-LAS_098-S1-2-1 | BRN-LAS_098-S1-2-1-1.5-System | LAS_098 | 1.5 | Update relevant SOPs and periodically review the User List according to procedure | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_098 | BRN-LAS_098-S2-3-2 | BRN-LAS_098-S2-3-2-2.1-System | LAS_098 | 2.1 | Investigate with the supplier if it is possible to implement a proper configuration of user groups with segregation of duties | System | 1 | 0 | NO | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_098 | BRN-LAS_098-S2-3-2 | BRN-LAS_098-S2-3-2-2.2-System | LAS_098 | 2.2 | Change Control Management including impact assessment | System | 0.5 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_098 | BRN-LAS_098-S2-3-2 | BRN-LAS_098-S2-3-2-2.3-System | LAS_098 | 2.3 | Configure 3 user groups and define the role of each user | System | 1 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_098 | BRN-LAS_098-S2-3-2 | BRN-LAS_098-S2-3-2-2.4-System | LAS_098 | 2.4 | Configure user privileges according to a proper segregation of duties | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_098 | BRN-LAS_098-S2-3-2 | BRN-LAS_098-S2-3-2-2.5-System | LAS_098 | 2.5 | Test and document the configuration changes | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_098 | BRN-LAS_098-S2-3-2 | BRN-LAS_098-S2-3-2-2.6-System | LAS_098 | 2.6 | Update relevant SOP | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_098 | BRN-LAS_098-S3-4-3 | BRN-LAS_098-S3-4-3-3.1-System | LAS_098 | 3.1 | Investigate with the supplier if it is possible to upgrade the software to grant proper security features for user access | System | 1 | 0 | NO | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_098 | BRN-LAS_098-S3-4-3 | BRN-LAS_098-S3-4-3-3.2-Generic | LAS_098 | 3.2 | Define the Password features in an approved procedure | Generic | 1 | 3 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_098 | BRN-LAS_098-S3-4-3 | BRN-LAS_098-S3-4-3-3.3-System | LAS_098 | 3.3 | Personnel training to access the system | System | 0.5 | 0.5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_098 | BRN-LAS_098-S3-4-3 | BRN-LAS_098-S3-4-3-3.4-System | LAS_098 | 3.4 | Update relevant SOP | System | 0.2 | 0.2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_098 | BRN-LAS_098-S4-3-4 | BRN-LAS_098-S4-3-4-4.1-System | LAS_098 | 4.1 | Issue a User List with the actual status of users | System | 0.1 | 0.5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_098 | BRN-LAS_098-S4-3-4 | BRN-LAS_098-S4-3-4-4.2-Generic | LAS_098 | 4.2 | Issue and approve a Periodic Review for User List | Generic | 0.1 | 0.5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_098 | BRN-LAS_098-S4-3-4 | BRN-LAS_098-S4-3-4-4.3-System | LAS_098 | 4.3 | Execute Periodic Review | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_098 | BRN-LAS_098-S4-3-4 | BRN-LAS_098-S4-3-4-4.4-System | LAS_098 | 4.4 | Setup of periodic task in relevant system | System | 0.2 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_098 | BRN-LAS_098-I1-2-5 | BRN-LAS_098-I1-2-5-5.1-System | LAS_098 | 5.1 | Change Control Management including impact assessment | System | 0.5 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_098 | BRN-LAS_098-I1-2-5 | BRN-LAS_098-I1-2-5-5.2-System | LAS_098 | 5.2 | Implement a process of automatic data backup | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_098 | BRN-LAS_098-I1-2-5 | BRN-LAS_098-I1-2-5-5.3-Generic | LAS_098 | 5.3 | If automatic backup its not possible, document manual backups of system data with a proper frequency to be defined in a dedicated procedure | Generic | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_098 | BRN-LAS_098-I1-2-5 | BRN-LAS_098-I1-2-5-5.4-System | LAS_098 | 5.4 | Test and document the implemented changes | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_098 | BRN-LAS_098-I1-2-5 | BRN-LAS_098-I1-2-5-5.5-System | LAS_098 | 5.5 | Update relevant SOP | System | 0.2 | 0.2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_098 | BRN-LAS_098-I2-2-6 | BRN-LAS_098-I2-2-6-6.1-System | LAS_098 | 6.1 | Change Control Management including impact assessment | System | 0.5 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_098 | BRN-LAS_098-I2-2-6 | BRN-LAS_098-I2-2-6-6.2-System | LAS_098 | 6.2 | Change permissions for users not authorized to modify data, preventing the deletion or alteration. | System | 0.5 | 0 | NO | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_098 | BRN-LAS_098-I2-2-6 | BRN-LAS_098-I2-2-6-6.3-System | LAS_098 | 6.3 | Test and document the configuration changes | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_098 | BRN-LAS_098-I2-2-6 | BRN-LAS_098-I2-2-6-6.4-System | LAS_098 | 6.4 | Update relevant SOP | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_098 | BRN-LAS_098-I3-2-7 | BRN-LAS_098-I3-2-7-6.5-System | LAS_098 | 6.5 | Change Control Management including impact assessment | System | 0.5 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_098 | BRN-LAS_098-I3-2-7 | BRN-LAS_098-I3-2-7-7.1-System | LAS_098 | 7.1 | Configure the protection of input data through an automatic security policy or folder restrictions | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_098 | BRN-LAS_098-I3-2-7 | BRN-LAS_098-I3-2-7-7.2-System | LAS_098 | 7.2 | Configure user privileges to prevent the deletion or alteration of input data | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_098 | BRN-LAS_098-I3-2-7 | BRN-LAS_098-I3-2-7-7.3-System | LAS_098 | 7.3 | Test and document the configuration changes | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_098 | BRN-LAS_098-I3-2-7 | BRN-LAS_098-I3-2-7-7.4-System | LAS_098 | 7.4 | Update relevant SOP | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_098 | BRN-LAS_098-T1-2-8 | BRN-LAS_098-T1-2-8-8.1-System | LAS_098 | 8.1 | Investigate with the supplier if it is possible to implement a proper configuration of the AT | System | 1 | 0 | NO | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_098 | BRN-LAS_098-T1-2-8 | BRN-LAS_098-T1-2-8-8.2-System | LAS_098 | 8.2 | Change Control Management including impact assessment | System | 0.5 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_098 | BRN-LAS_098-T1-2-8 | BRN-LAS_098-T1-2-8-8.3-System | LAS_098 | 8.3 | Configure Audit Trail functionality within the SW or, if not applicable, implement a paper based management for tracking relevant operation (i.e. old&new value, reason for change) to relevant data | System | 2 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_098 | BRN-LAS_098-T1-2-8 | BRN-LAS_098-T1-2-8-8.4-System | LAS_098 | 8.4 | Test and document configuration changes or the procedural changes | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_098 | BRN-LAS_098-T1-2-8 | BRN-LAS_098-T1-2-8-8.5-System | LAS_098 | 8.5 | Update relevant SOP | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_098 | BRN-LAS_098-T3-3-9 | BRN-LAS_098-T3-3-9-9.1-Generic | LAS_098 | 9.1 | Issue and approve a fully compliant Audit Trail Review Working Instruction | Generic | 0.5 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_098 | BRN-LAS_098-T3-3-9 | BRN-LAS_098-T3-3-9-9.2-System | LAS_098 | 9.2 | Execute Audit Trail Review Working Instruction: - perform Data Assessment for Electronic Records managed by the system - update Operational Method SOP (Methods/Instrument) - update test documentation | System | 0.5 | 2.5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_098 | BRN-LAS_098-T3-3-9 | BRN-LAS_098-T3-3-9-9.3-System | LAS_098 | 9.3 | Setup of periodic task | System | 0.2 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_098 | BRN-LAS_098-VD1-2-10 | BRN-LAS_098-VD1-2-10-10.1-System | LAS_098 | 10.1 | Review the Computer System Validation in place and identify the missing/incomplete validation documents or testing protocols | System | 1 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started | Validation Plan not present, Global CSV SOPs not applied., Traceability Matrix is not present, VR (called Qualifizierungsbericht, eng. Qualification report) not complete, URS document present but it is missing Functional Process Requirements, Access Control and Security Roles partially covered, no reference to regulatory rules (e.g. Annex11 coverage), Not complete, Risk Assessment not present, Testing only for IQ/OQ for the Control System. The level of detail is not consistent with DI expectations, i.e. Security/Integrity/Traceability verifications. Missing tests for documental checks (e.g. Users List, SOPs, etc.), functional checks (Part 11 and Annex 11 verifications), PQ not identified.
BRN | BRN-LAS_098 | BRN-LAS_098-VD1-2-10 | BRN-LAS_098-VD1-2-10-10.2-System | LAS_098 | 10.2 | Issue and approve the missing validation documentation | System | 2 | 3 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_098 | BRN-LAS_098-VD1-2-10 | BRN-LAS_098-VD1-2-10-10.3-System | LAS_098 | 10.3 | Perform and document the missing/incomplete tests | System | 3 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_098 | BRN-LAS_098-VD1-2-10 | BRN-LAS_098-VD1-2-10-10.4-System | LAS_098 | 10.4 | Assure the Traceability of the testing with coded requirements against coded test and update the documentation accordingly | System | 2 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_100 | BRN-LAS_100-S1-2-1 | BRN-LAS_100-S1-2-1-1.1-System | LAS_100 | 1.1 | Change Control Management including impact assessment | System | 0.5 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_100 | BRN-LAS_100-S1-2-1 | BRN-LAS_100-S1-2-1-1.2-System | LAS_100 | 1.2 | Update system administration SOP to describe generic account's access mode and functionalities, and how to keep track of its actions | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_100 | BRN-LAS_100-S3-4-2 | BRN-LAS_100-S3-4-2-2.1-Generic | LAS_100 | 2.1 | Issue and approve a Security SOP with proper PW security features according to best practices (length, complexity, expiring) | Generic | 1 | 5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_100 | BRN-LAS_100-S3-4-2 | BRN-LAS_100-S3-4-2-2.2-System | LAS_100 | 2.2 | Update all passwords according to the approved Security SOP | System | 1 | 0.1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_100 | BRN-LAS_100-S3-4-2 | BRN-LAS_100-S3-4-2-2.3-System | LAS_100 | 2.3 | Test and document the Password policies | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_100 | BRN-LAS_100-I1-2-3 | BRN-LAS_100-I1-2-3-3.1-System | LAS_100 | 3.1 | Change Control Management including impact assessment | System | 0.5 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_100 | BRN-LAS_100-I1-2-3 | BRN-LAS_100-I1-2-3-3.2-System | LAS_100 | 3.2 | Implement a process of automatic data backup | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_100 | BRN-LAS_100-I1-2-3 | BRN-LAS_100-I1-2-3-3.3-Generic | LAS_100 | 3.3 | If automatic backup its not possible, document manual backups of system data with a proper frequency to be defined in a dedicated procedure | Generic | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_100 | BRN-LAS_100-I1-2-3 | BRN-LAS_100-I1-2-3-3.4-System | LAS_100 | 3.4 | Test and document the implemented changes | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_100 | BRN-LAS_100-I1-2-3 | BRN-LAS_100-I1-2-3-3.5-System | LAS_100 | 3.5 | Update relevant SOP | System | 0.2 | 0.2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_100 | BRN-LAS_100-I3-2-4 | BRN-LAS_100-I3-2-4-4.1-System | LAS_100 | 4.1 | Change Control Management including impact assessment | System | 0.5 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_100 | BRN-LAS_100-I3-2-4 | BRN-LAS_100-I3-2-4-4.2-System | LAS_100 | 4.2 | Configure the protection of input data through an automatic security policy or folder restrictions | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_100 | BRN-LAS_100-I3-2-4 | BRN-LAS_100-I3-2-4-4.3-System | LAS_100 | 4.3 | Configure user privileges to prevent the deletion or alteration of input data | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_100 | BRN-LAS_100-I3-2-4 | BRN-LAS_100-I3-2-4-4.4-System | LAS_100 | 4.4 | Test and document the configuration changes | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_100 | BRN-LAS_100-I3-2-4 | BRN-LAS_100-I3-2-4-4.5-System | LAS_100 | 4.5 | Update relevant SOP | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_100 | BRN-LAS_100-T1-2-5 | BRN-LAS_100-T1-2-5-5.1-System | LAS_100 | 5.1 | Change Control Management including impact assessment | System | 0.5 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_100 | BRN-LAS_100-T1-2-5 | BRN-LAS_100-T1-2-5-5.2-System | LAS_100 | 5.2 | Update Audit Trail functionality in order to track and record modifications to ER | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_100 | BRN-LAS_100-T1-2-5 | BRN-LAS_100-T1-2-5-5.3-Generic | LAS_100 | 5.3 | If Audit Trail is not compliant (e.g. does not track modifications to ER), implement a paper based management of system regulated input records (i.e. methods) with the following paper procedures: -user access log -verification log to be used by the Users before launching a method -traceability log to be used by the system administrators when changing a method | Generic | 2 | 3 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_100 | BRN-LAS_100-T1-2-5 | BRN-LAS_100-T1-2-5-5.4-System | LAS_100 | 5.4 | Test and document that Audit Trail is fully compliant or, in case of paper Audit Trail, that the personnel is trained to use it | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_100 | BRN-LAS_100-T1-2-5 | BRN-LAS_100-T1-2-5-5.5-System | LAS_100 | 5.5 | Update relevant SOP | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_100 | BRN-LAS_100-T2-2-6 | BRN-LAS_100-T2-2-6-6.1-System | LAS_100 | 6.1 | Change Control Management including impact assessment | System | 0.5 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_100 | BRN-LAS_100-T2-2-6 | BRN-LAS_100-T2-2-6-6.2-System | LAS_100 | 6.2 | Verify if Time Reference protection can be configured within the system | System | 0.5 | 0.5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_100 | BRN-LAS_100-T2-2-6 | BRN-LAS_100-T2-2-6-6.3-Generic | LAS_100 | 6.3 | If not possible, manage Date & Time protection through an approved procedure | Generic | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_100 | BRN-LAS_100-T2-2-6 | BRN-LAS_100-T2-2-6-6.4-System | LAS_100 | 6.4 | Test and document configuration changes | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_100 | BRN-LAS_100-T2-2-6 | BRN-LAS_100-T2-2-6-6.5-System | LAS_100 | 6.5 | Update relevant SOP | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_100 | BRN-LAS_100-T3-3-7 | BRN-LAS_100-T3-3-7-7.1-Generic | LAS_100 | 7.1 | If there is no Audit Trail Process fully compliant, issue and approve a fully compliant Audit Trail Review Working Instruction | Generic | 1 | 3 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_100 | BRN-LAS_100-T3-3-7 | BRN-LAS_100-T3-3-7-7.2-System | LAS_100 | 7.2 | Execute Audit Trail Review Working Instruction: - perform Data Assessment for Electronic Records managed by the system - update Operational Method SOP (Methods/Instrument) - update test documentation | System | 0.5 | 2.5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_100 | BRN-LAS_100-T3-3-7 | BRN-LAS_100-T3-3-7-7.3-System | LAS_100 | 7.3 | Setup of periodic task | System | 0.2 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_100 | BRN-LAS_100-VD1-2-8 | BRN-LAS_100-VD1-2-8-8.1-System | LAS_100 | 8.1 | Review the Computer System Validation in place and identify the missing/incomplete validation documents or testing protocols | System | 1 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started | Computerized system validation documentation is not complete for Systems (VP, URS, RA, VR and Traceability Matrix are not present), Global CSV SOPs not applied., See PL1, User Requirements, Functional/Process Risk Analysis or Configuration Specifications (included Security Matrix), is not included in the validation life-cycle., See SR1, See SR1, IQ/OQ/PQ not identified. The level of detail is not consistent with DI expectations, i.e. Security/Integrity/Traceability verifications. Missing tests for documental checks (e.g. Users List, SOPs, etc.), functional checks (Part 11 verifications), and missing performance checks (e.g. Method Creation, Data Acquisition, and Report Printing)
BRN | BRN-LAS_100 | BRN-LAS_100-VD1-2-8 | BRN-LAS_100-VD1-2-8-8.2-System | LAS_100 | 8.2 | Issue and approve the missing validation documentation | System | 2 | 3 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_100 | BRN-LAS_100-VD1-2-8 | BRN-LAS_100-VD1-2-8-8.3-System | LAS_100 | 8.3 | Perform and document the missing/incomplete tests | System | 3 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_100 | BRN-LAS_100-VD1-2-8 | BRN-LAS_100-VD1-2-8-8.4-System | LAS_100 | 8.4 | Assure the Traceability of the testing with coded requirements against coded test and update the documentation accordingly | System | 2 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_105 | BRN-LAS_105-S3-4-1 | BRN-LAS_105-S3-4-1-1.1-Generic | LAS_105 | 1.1 | Issue and approve a Security SOP with proper PW security features according to best practices (length, complexity, expiring) | Generic | 1 | 5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto |  | To be started
BRN | BRN-LAS_105 | BRN-LAS_105-S3-4-1 | BRN-LAS_105-S3-4-1-1.2-System | LAS_105 | 1.2 | Update all passwords according to the approved Security SOP | System | 1 | 0.1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto |  | To be started
BRN | BRN-LAS_105 | BRN-LAS_105-S3-4-1 | BRN-LAS_105-S3-4-1-1.3-System | LAS_105 | 1.3 | Test and document the Password policies | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto |  | To be started
BRN | BRN-LAS_105 | BRN-LAS_105-S4-3-2 | BRN-LAS_105-S4-3-2-2.1-System | LAS_105 | 2.1 | Issue a User List with the actual status of users | System | 0.1 | 0.5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto |  | To be started
BRN | BRN-LAS_105 | BRN-LAS_105-S4-3-2 | BRN-LAS_105-S4-3-2-2.2-Generic | LAS_105 | 2.2 | Issue and approve a Periodic Review for User List | Generic | 0.1 | 0.5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto |  | To be started
BRN | BRN-LAS_105 | BRN-LAS_105-S4-3-2 | BRN-LAS_105-S4-3-2-2.3-System | LAS_105 | 2.3 | Execute Periodic Review | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto |  | To be started
BRN | BRN-LAS_105 | BRN-LAS_105-S4-3-2 | BRN-LAS_105-S4-3-2-2.4-System | LAS_105 | 2.4 | Setup of periodic task in relevant system | System | 0.2 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto |  | To be started
BRN | BRN-LAS_105 | BRN-LAS_105-I2-2-3 | BRN-LAS_105-I2-2-3-3.1-System | LAS_105 | 3.1 | Change Control Management including impact assessment | System | 0.5 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2026-12-31 | To be started
BRN | BRN-LAS_105 | BRN-LAS_105-I2-2-3 | BRN-LAS_105-I2-2-3-3.2-System | LAS_105 | 3.2 | Change permissions for users not authorized to modify data, preventing the deletion or alteration. | System | 0.5 | 0 | NO | LES Lab Support | Valeria Geraci | Dario Ruberto | 2026-12-31 | To be started
BRN | BRN-LAS_105 | BRN-LAS_105-I2-2-3 | BRN-LAS_105-I2-2-3-3.3-System | LAS_105 | 3.3 | Test and document the configuration changes | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2026-12-31 | To be started
BRN | BRN-LAS_105 | BRN-LAS_105-I2-2-3 | BRN-LAS_105-I2-2-3-3.4-System | LAS_105 | 3.4 | Update relevant SOP | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2026-12-31 | To be started
BRN | BRN-LAS_105 | BRN-LAS_105-I3-2-4 | BRN-LAS_105-I3-2-4-4.1-System | LAS_105 | 4.1 | Change Control Management including impact assessment | System | 0.5 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2026-12-31 | To be started
BRN | BRN-LAS_105 | BRN-LAS_105-I3-2-4 | BRN-LAS_105-I3-2-4-4.2-System | LAS_105 | 4.2 | Configure the protection of input data through an automatic security policy or folder restrictions | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2026-12-31 | To be started
BRN | BRN-LAS_105 | BRN-LAS_105-I3-2-4 | BRN-LAS_105-I3-2-4-4.3-System | LAS_105 | 4.3 | Configure user privileges to prevent the deletion or alteration of input data | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2026-12-31 | To be started
BRN | BRN-LAS_105 | BRN-LAS_105-I3-2-4 | BRN-LAS_105-I3-2-4-4.4-System | LAS_105 | 4.4 | Test and document the configuration changes | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2026-12-31 | To be started
BRN | BRN-LAS_105 | BRN-LAS_105-I3-2-4 | BRN-LAS_105-I3-2-4-4.5-System | LAS_105 | 4.5 | Update relevant SOP | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2026-12-31 | To be started
BRN | BRN-LAS_105 | BRN-LAS_105-T1-2-5 | BRN-LAS_105-T1-2-5-5.1-System | LAS_105 | 5.1 | Change Control Management including impact assessment | System | 0.5 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2026-12-31 | To be started
BRN | BRN-LAS_105 | BRN-LAS_105-T1-2-5 | BRN-LAS_105-T1-2-5-5.2-System | LAS_105 | 5.2 | Update Audit Trail functionality in order to track and record modifications to ER | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2026-12-31 | To be started
BRN | BRN-LAS_105 | BRN-LAS_105-T1-2-5 | BRN-LAS_105-T1-2-5-5.3-Generic | LAS_105 | 5.3 | If Audit Trail is not compliant (e.g. does not track modifications to ER), implement a paper based management of system regulated input records (i.e. methods) with the following paper procedures: -user access log -verification log to be used by the Users before launching a method -traceability log to be used by the system administrators when changing a method | Generic | 2 | 3 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2026-12-31 | To be started
BRN | BRN-LAS_105 | BRN-LAS_105-T1-2-5 | BRN-LAS_105-T1-2-5-5.4-System | LAS_105 | 5.4 | Test and document that Audit Trail is fully compliant or, in case of paper Audit Trail, that the personnel is trained to use it | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2026-12-31 | To be started
BRN | BRN-LAS_105 | BRN-LAS_105-T1-2-5 | BRN-LAS_105-T1-2-5-5.5-System | LAS_105 | 5.5 | Update relevant SOP | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2026-12-31 | To be started
BRN | BRN-LAS_105 | BRN-LAS_105-T3-3-6 | BRN-LAS_105-T3-3-6-6.1-Generic | LAS_105 | 6.1 | Issue and approve a fully compliant Audit Trail Review Working Instruction | Generic | 0.5 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto |  | To be started
BRN | BRN-LAS_105 | BRN-LAS_105-T3-3-6 | BRN-LAS_105-T3-3-6-6.2-System | LAS_105 | 6.2 | Execute Audit Trail Review Working Instruction: - perform Data Assessment for Electronic Records managed by the system - update Operational Method SOP (Methods/Instrument) - update test documentation | System | 0.5 | 2.5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto |  | To be started
BRN | BRN-LAS_105 | BRN-LAS_105-T3-3-6 | BRN-LAS_105-T3-3-6-6.3-System | LAS_105 | 6.3 | Setup of periodic task | System | 0.2 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto |  | To be started
BRN | BRN-LAS_105 | BRN-LAS_105-VD1-2-7 | BRN-LAS_105-VD1-2-7-7.1-System | LAS_105 | 7.1 | Review the Computer System Validation in place and identify the missing/incomplete validation documents or testing protocols | System | 1 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2026-12-31 | To be started | Validation Plan not present, Global CSV SOPs not applied., Traceability Matrix is not present, VR (called Qualifizierungsbericht, eng. Qualification report) not complete, URS document present but it is missing Functional Process Requirements, Access Control and Security Roles partially covered, no reference to regulatory rules (e.g. Annex11 coverage), Configuration Specification not identified., Risk Assessment not present, Testing only for IQ/OQ for the Control System. The level of detail is not consistent with DI expectations, i.e. Security/Integrity/Traceability verifications. Missing tests for documental checks (e.g. Users List, SOPs, etc.), functional checks (Part 11 and Annex 11 verifications), PQ not identified.
BRN | BRN-LAS_105 | BRN-LAS_105-VD1-2-7 | BRN-LAS_105-VD1-2-7-7.2-System | LAS_105 | 7.2 | Issue and approve the missing validation documentation | System | 2 | 3 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2026-12-31 | To be started
BRN | BRN-LAS_105 | BRN-LAS_105-VD1-2-7 | BRN-LAS_105-VD1-2-7-7.3-System | LAS_105 | 7.3 | Perform and document the missing/incomplete tests | System | 3 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2026-12-31 | To be started
BRN | BRN-LAS_105 | BRN-LAS_105-VD1-2-7 | BRN-LAS_105-VD1-2-7-7.4-System | LAS_105 | 7.4 | Assure the Traceability of the testing with coded requirements against coded test and update the documentation accordingly | System | 2 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2026-12-31 | To be started
BRN | BRN-LAS_106 | BRN-LAS_106-S3-4-1 | BRN-LAS_106-S3-4-1-1.1-Generic | LAS_106 | 1.1 | Issue and approve a Security SOP with proper PW security features according to best practices (length, complexity, expiring) | Generic | 1 | 5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto |  | To be started
BRN | BRN-LAS_106 | BRN-LAS_106-S3-4-1 | BRN-LAS_106-S3-4-1-1.2-System | LAS_106 | 1.2 | Update all passwords according to the approved Security SOP | System | 1 | 0.1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto |  | To be started
BRN | BRN-LAS_106 | BRN-LAS_106-S3-4-1 | BRN-LAS_106-S3-4-1-1.3-System | LAS_106 | 1.3 | Test and document the Password policies | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto |  | To be started
BRN | BRN-LAS_106 | BRN-LAS_106-S4-3-2 | BRN-LAS_106-S4-3-2-2.1-System | LAS_106 | 2.1 | Issue a User List with the actual status of users | System | 0.1 | 0.5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto |  | To be started
BRN | BRN-LAS_106 | BRN-LAS_106-S4-3-2 | BRN-LAS_106-S4-3-2-2.2-Generic | LAS_106 | 2.2 | Issue and approve a Periodic Review for User List | Generic | 0.1 | 0.5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto |  | To be started
BRN | BRN-LAS_106 | BRN-LAS_106-S4-3-2 | BRN-LAS_106-S4-3-2-2.3-System | LAS_106 | 2.3 | Execute Periodic Review | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto |  | To be started
BRN | BRN-LAS_106 | BRN-LAS_106-S4-3-2 | BRN-LAS_106-S4-3-2-2.4-System | LAS_106 | 2.4 | Setup of periodic task in relevant system | System | 0.2 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto |  | To be started
BRN | BRN-LAS_106 | BRN-LAS_106-I2-2-3 | BRN-LAS_106-I2-2-3-3.1-System | LAS_106 | 3.1 | Change Control Management including impact assessment | System | 0.5 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2026-12-31 | To be started
BRN | BRN-LAS_106 | BRN-LAS_106-I2-2-3 | BRN-LAS_106-I2-2-3-3.2-System | LAS_106 | 3.2 | Change permissions for users not authorized to modify data, preventing the deletion or alteration. | System | 0.5 | 0 | NO | LES Lab Support | Valeria Geraci | Dario Ruberto | 2026-12-31 | To be started
BRN | BRN-LAS_106 | BRN-LAS_106-I2-2-3 | BRN-LAS_106-I2-2-3-3.3-System | LAS_106 | 3.3 | Test and document the configuration changes | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2026-12-31 | To be started
BRN | BRN-LAS_106 | BRN-LAS_106-I2-2-3 | BRN-LAS_106-I2-2-3-3.4-System | LAS_106 | 3.4 | Update relevant SOP | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2026-12-31 | To be started
BRN | BRN-LAS_106 | BRN-LAS_106-I3-2-4 | BRN-LAS_106-I3-2-4-4.1-System | LAS_106 | 4.1 | Change Control Management including impact assessment | System | 0.5 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2026-12-31 | To be started
BRN | BRN-LAS_106 | BRN-LAS_106-I3-2-4 | BRN-LAS_106-I3-2-4-4.2-System | LAS_106 | 4.2 | Configure the protection of input data through an automatic security policy or folder restrictions | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2026-12-31 | To be started
BRN | BRN-LAS_106 | BRN-LAS_106-I3-2-4 | BRN-LAS_106-I3-2-4-4.3-System | LAS_106 | 4.3 | Configure user privileges to prevent the deletion or alteration of input data | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2026-12-31 | To be started
BRN | BRN-LAS_106 | BRN-LAS_106-I3-2-4 | BRN-LAS_106-I3-2-4-4.4-System | LAS_106 | 4.4 | Test and document the configuration changes | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2026-12-31 | To be started
BRN | BRN-LAS_106 | BRN-LAS_106-I3-2-4 | BRN-LAS_106-I3-2-4-4.5-System | LAS_106 | 4.5 | Update relevant SOP | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2026-12-31 | To be started
BRN | BRN-LAS_106 | BRN-LAS_106-T1-2-5 | BRN-LAS_106-T1-2-5-5.1-System | LAS_106 | 5.1 | Change Control Management including impact assessment | System | 0.5 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2026-12-31 | To be started
BRN | BRN-LAS_106 | BRN-LAS_106-T1-2-5 | BRN-LAS_106-T1-2-5-5.2-System | LAS_106 | 5.2 | Update Audit Trail functionality in order to track and record modifications to ER | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2026-12-31 | To be started
BRN | BRN-LAS_106 | BRN-LAS_106-T1-2-5 | BRN-LAS_106-T1-2-5-5.3-Generic | LAS_106 | 5.3 | If Audit Trail is not compliant (e.g. does not track modifications to ER), implement a paper based management of system regulated input records (i.e. methods) with the following paper procedures: -user access log -verification log to be used by the Users before launching a method -traceability log to be used by the system administrators when changing a method | Generic | 2 | 3 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2026-12-31 | To be started
BRN | BRN-LAS_106 | BRN-LAS_106-T1-2-5 | BRN-LAS_106-T1-2-5-5.4-System | LAS_106 | 5.4 | Test and document that Audit Trail is fully compliant or, in case of paper Audit Trail, that the personnel is trained to use it | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2026-12-31 | To be started
BRN | BRN-LAS_106 | BRN-LAS_106-T1-2-5 | BRN-LAS_106-T1-2-5-5.5-System | LAS_106 | 5.5 | Update relevant SOP | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2026-12-31 | To be started
BRN | BRN-LAS_106 | BRN-LAS_106-T3-3-6 | BRN-LAS_106-T3-3-6-6.1-Generic | LAS_106 | 6.1 | Issue and approve a fully compliant Audit Trail Review Working Instruction | Generic | 0.5 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto |  | To be started
BRN | BRN-LAS_106 | BRN-LAS_106-T3-3-6 | BRN-LAS_106-T3-3-6-6.2-System | LAS_106 | 6.2 | Execute Audit Trail Review Working Instruction: - perform Data Assessment for Electronic Records managed by the system - update Operational Method SOP (Methods/Instrument) - update test documentation | System | 0.5 | 2.5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto |  | To be started
BRN | BRN-LAS_106 | BRN-LAS_106-T3-3-6 | BRN-LAS_106-T3-3-6-6.3-System | LAS_106 | 6.3 | Setup of periodic task | System | 0.2 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto |  | To be started
BRN | BRN-LAS_106 | BRN-LAS_106-VD1-2-7 | BRN-LAS_106-VD1-2-7-7.1-System | LAS_106 | 7.1 | Review the Computer System Validation in place and identify the missing/incomplete validation documents or testing protocols | System | 1 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2026-12-31 | To be started | Validation Plan not present, Global CSV SOPs not applied., Traceability Matrix is not present, VR (called Qualifizierungsbericht, eng. Qualification report) not complete, URS document present but it is missing Functional Process Requirements, Access Control and Security Roles partially covered, no reference to regulatory rules (e.g. Annex11 coverage), Configuration Specification not identified., Risk Assessment not present, Testing only for IQ/OQ for the Control System. The level of detail is not consistent with DI expectations, i.e. Security/Integrity/Traceability verifications. Missing tests for documental checks (e.g. Users List, SOPs, etc.), functional checks (Part 11 and Annex 11 verifications), PQ not identified.
BRN | BRN-LAS_106 | BRN-LAS_106-VD1-2-7 | BRN-LAS_106-VD1-2-7-7.2-System | LAS_106 | 7.2 | Issue and approve the missing validation documentation | System | 2 | 3 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2026-12-31 | To be started
BRN | BRN-LAS_106 | BRN-LAS_106-VD1-2-7 | BRN-LAS_106-VD1-2-7-7.3-System | LAS_106 | 7.3 | Perform and document the missing/incomplete tests | System | 3 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2026-12-31 | To be started
BRN | BRN-LAS_106 | BRN-LAS_106-VD1-2-7 | BRN-LAS_106-VD1-2-7-7.4-System | LAS_106 | 7.4 | Assure the Traceability of the testing with coded requirements against coded test and update the documentation accordingly | System | 2 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2026-12-31 | To be started
BRN | BRN-LAS_114 | BRN-LAS_114-S1-1-1 | BRN-LAS_114-S1-1-1-1.1-System | LAS_114 | 1.1 | Change Control Management including impact assessment | System | 0.5 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2026-06-30 | To be started | FMEA has been proposed by Dario and Julian. Potential tech limitation for GDIP. Ongoing communication with Vendor. Deadline to be defined and replaced once the remediation plan is set .
BRN | BRN-LAS_114 | BRN-LAS_114-S1-1-1 | BRN-LAS_114-S1-1-1-1.2-System | LAS_114 | 1.2 | Create personal and unique accounts in system | System | 1 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2026-06-30 | To be started | FMEA has been proposed by Dario and Julian. Potential tech limitation for GDIP. Ongoing communication with Vendor. Deadline to be defined and replaced once the remediation plan is set .
BRN | BRN-LAS_114 | BRN-LAS_114-S1-1-1 | BRN-LAS_114-S1-1-1-1.3-System | LAS_114 | 1.3 | Remove generic accounts from the system | System | 0.5 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2026-06-30 | To be started | FMEA has been proposed by Dario and Julian. Potential tech limitation for GDIP. Ongoing communication with Vendor. Deadline to be defined and replaced once the remediation plan is set .
BRN | BRN-LAS_114 | BRN-LAS_114-S1-1-1 | BRN-LAS_114-S1-1-1-1.4-System | LAS_114 | 1.4 | Issue and approve an updated User List | System | 0.1 | 0.5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2026-06-30 | To be started | FMEA has been proposed by Dario and Julian. Potential tech limitation for GDIP. Ongoing communication with Vendor. Deadline to be defined and replaced once the remediation plan is set .
BRN | BRN-LAS_114 | BRN-LAS_114-S1-1-1 | BRN-LAS_114-S1-1-1-1.5-System | LAS_114 | 1.5 | Update relevant SOPs and periodically review the User List according to procedure | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2026-06-30 | To be started | FMEA has been proposed by Dario and Julian. Potential tech limitation for GDIP. Ongoing communication with Vendor. Deadline to be defined and replaced once the remediation plan is set .
BRN | BRN-LAS_114 | BRN-LAS_114-S2-2-2 | BRN-LAS_114-S2-2-2-2.1-System | LAS_114 | 2.1 | Define the User Groups and the related privileges in an approved procedure | System | 2 | 3 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2026-06-30 | To be started | FMEA has been proposed by Dario and Julian. Potential tech limitation for GDIP. Ongoing communication with Vendor. Deadline to be defined and replaced once the remediation plan is set .
BRN | BRN-LAS_114 | BRN-LAS_114-S2-2-2 | BRN-LAS_114-S2-2-2-2.2-System | LAS_114 | 2.2 | Personnel training to access the system | System | 0.5 | 0.5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2026-06-30 | To be started | FMEA has been proposed by Dario and Julian. Potential tech limitation for GDIP. Ongoing communication with Vendor. Deadline to be defined and replaced once the remediation plan is set .
BRN | BRN-LAS_114 | BRN-LAS_114-S2-2-2 | BRN-LAS_114-S2-2-2-2.3-System | LAS_114 | 2.3 | Update relevant SOP | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2026-06-30 | To be started | FMEA has been proposed by Dario and Julian. Potential tech limitation for GDIP. Ongoing communication with Vendor. Deadline to be defined and replaced once the remediation plan is set .
BRN | BRN-LAS_114 | BRN-LAS_114-S4-2-3 | BRN-LAS_114-S4-2-3-3.1-System | LAS_114 | 3.1 | Updating the User List with the actual status of users | System | 0.1 | 0.5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2026-06-30 | To be started | FMEA has been proposed by Dario and Julian. Potential tech limitation for GDIP. Ongoing communication with Vendor. Deadline to be defined and replaced once the remediation plan is set .
BRN | BRN-LAS_114 | BRN-LAS_114-S4-2-3 | BRN-LAS_114-S4-2-3-3.2-Generic | LAS_114 | 3.2 | Issue and approve a Periodic Review for User List | Generic | 0.1 | 0.5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2026-06-30 | To be started | FMEA has been proposed by Dario and Julian. Potential tech limitation for GDIP. Ongoing communication with Vendor. Deadline to be defined and replaced once the remediation plan is set .
BRN | BRN-LAS_114 | BRN-LAS_114-S4-2-3 | BRN-LAS_114-S4-2-3-3.3-System | LAS_114 | 3.3 | Execute Periodic Review | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2026-06-30 | To be started | FMEA has been proposed by Dario and Julian. Potential tech limitation for GDIP. Ongoing communication with Vendor. Deadline to be defined and replaced once the remediation plan is set .
BRN | BRN-LAS_114 | BRN-LAS_114-S4-2-3 | BRN-LAS_114-S4-2-3-3.4-System | LAS_114 | 3.4 | Setup of periodic task in relevant system | System | 0.2 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2026-06-30 | To be started | FMEA has been proposed by Dario and Julian. Potential tech limitation for GDIP. Ongoing communication with Vendor. Deadline to be defined and replaced once the remediation plan is set .
BRN | BRN-LAS_114 | BRN-LAS_114-T1-2-4 | BRN-LAS_114-T1-2-4-4.1-System | LAS_114 | 4.1 | Change Control Management including impact assessment | System | 0.5 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2026-06-30 | To be started | FMEA has been proposed by Dario and Julian. Potential tech limitation for GDIP. Ongoing communication with Vendor. Deadline to be defined and replaced once the remediation plan is set .
BRN | BRN-LAS_114 | BRN-LAS_114-T1-2-4 | BRN-LAS_114-T1-2-4-4.2-System | LAS_114 | 4.2 | Update Audit Trail functionality in order to track and record modifications to ER | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2026-06-30 | To be started | FMEA has been proposed by Dario and Julian. Potential tech limitation for GDIP. Ongoing communication with Vendor. Deadline to be defined and replaced once the remediation plan is set .
BRN | BRN-LAS_114 | BRN-LAS_114-T1-2-4 | BRN-LAS_114-T1-2-4-4.3-Generic | LAS_114 | 4.3 | If Audit Trail is not compliant (e.g. does not track modifications to ER), implement a paper based management of system regulated input records (i.e. methods) with the following paper procedures: -user access log -verification log to be used by the Users before launching a method -traceability log to be used by the system administrators when changing a method | Generic | 2 | 3 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2026-06-30 | To be started | FMEA has been proposed by Dario and Julian. Potential tech limitation for GDIP. Ongoing communication with Vendor. Deadline to be defined and replaced once the remediation plan is set .
BRN | BRN-LAS_114 | BRN-LAS_114-T1-2-4 | BRN-LAS_114-T1-2-4-4.4-System | LAS_114 | 4.4 | Test and document that Audit Trail is fully compliant or, in case of paper Audit Trail, that the personnel is trained to use it | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2026-06-30 | To be started | FMEA has been proposed by Dario and Julian. Potential tech limitation for GDIP. Ongoing communication with Vendor. Deadline to be defined and replaced once the remediation plan is set .
BRN | BRN-LAS_114 | BRN-LAS_114-T1-2-4 | BRN-LAS_114-T1-2-4-4.5-System | LAS_114 | 4.5 | Update relevant SOP | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2026-06-30 | To be started | FMEA has been proposed by Dario and Julian. Potential tech limitation for GDIP. Ongoing communication with Vendor. Deadline to be defined and replaced once the remediation plan is set .
BRN | BRN-LAS_114 | BRN-LAS_114-T3-2-5 | BRN-LAS_114-T3-2-5-5.1-Generic | LAS_114 | 5.1 | Issue and approve a fully compliant Audit Trail Review Working Instruction | Generic | 0.5 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2026-06-30 | To be started | FMEA has been proposed by Dario and Julian. Potential tech limitation for GDIP. Ongoing communication with Vendor. Deadline to be defined and replaced once the remediation plan is set .
BRN | BRN-LAS_114 | BRN-LAS_114-T3-2-5 | BRN-LAS_114-T3-2-5-5.2-System | LAS_114 | 5.2 | Execute Audit Trail Review Working Instruction: - perform Data Assessment for Electronic Records managed by the system - update Operational Method SOP (Methods/Instrument) - update test documentation | System | 0.5 | 2.5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2026-06-30 | To be started | FMEA has been proposed by Dario and Julian. Potential tech limitation for GDIP. Ongoing communication with Vendor. Deadline to be defined and replaced once the remediation plan is set .
BRN | BRN-LAS_114 | BRN-LAS_114-T3-2-5 | BRN-LAS_114-T3-2-5-5.3-System | LAS_114 | 5.3 | Setup of periodic task | System | 0.2 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2026-06-30 | To be started | FMEA has been proposed by Dario and Julian. Potential tech limitation for GDIP. Ongoing communication with Vendor. Deadline to be defined and replaced once the remediation plan is set .
BRN | BRN-LAS_114 | BRN-LAS_114-VD1-1-6 | BRN-LAS_114-VD1-1-6-6.1-System | LAS_114 | 6.1 | Review the Computer System Validation in place and identify the missing/incomplete validation documents or testing protocols | System | 1 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2026-06-30 | To be started | FMEA has been proposed by Dario and Julian. Potential tech limitation for GDIP. Ongoing communication with Vendor. Deadline to be defined and replaced once the remediation plan is set .
BRN | BRN-LAS_114 | BRN-LAS_114-VD1-1-6 | BRN-LAS_114-VD1-1-6-6.2-System | LAS_114 | 6.2 | Issue and approve the missing validation documentation | System | 2 | 3 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2026-06-30 | To be started | FMEA has been proposed by Dario and Julian. Potential tech limitation for GDIP. Ongoing communication with Vendor. Deadline to be defined and replaced once the remediation plan is set .
BRN | BRN-LAS_114 | BRN-LAS_114-VD1-1-6 | BRN-LAS_114-VD1-1-6-6.3-System | LAS_114 | 6.3 | Perform and document the missing/incomplete tests | System | 3 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2026-06-30 | To be started | FMEA has been proposed by Dario and Julian. Potential tech limitation for GDIP. Ongoing communication with Vendor. Deadline to be defined and replaced once the remediation plan is set .
BRN | BRN-LAS_114 | BRN-LAS_114-VD1-1-6 | BRN-LAS_114-VD1-1-6-6.4-System | LAS_114 | 6.4 | Assure the Traceability of the testing with coded requirements against coded test and update the documentation accordingly | System | 2 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2026-06-30 | To be started | FMEA has been proposed by Dario and Julian. Potential tech limitation for GDIP. Ongoing communication with Vendor. Deadline to be defined and replaced once the remediation plan is set .
BRN | BRN-LAS_124 | BRN-LAS_124-S3-5-1 | BRN-LAS_124-S3-5-1-1.1-Generic | LAS_124 | 1.1 | Issue and approve a Security SOP with proper PW security features according to best practices (length, complexity, expiring) | Generic | 1 | 5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_124 | BRN-LAS_124-S3-5-1 | BRN-LAS_124-S3-5-1-1.2-System | LAS_124 | 1.2 | Update all passwords according to the approved Security SOP | System | 1 | 0.1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_124 | BRN-LAS_124-S3-5-1 | BRN-LAS_124-S3-5-1-1.3-System | LAS_124 | 1.3 | Test and document the Password policies | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_124 | BRN-LAS_124-S4-4-2 | BRN-LAS_124-S4-4-2-2.1-System | LAS_124 | 2.1 | Issue a User List with the actual status of users | System | 0.1 | 0.5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_124 | BRN-LAS_124-S4-4-2 | BRN-LAS_124-S4-4-2-2.2-Generic | LAS_124 | 2.2 | Issue and approve a Periodic Review for User List | Generic | 0.1 | 0.5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_124 | BRN-LAS_124-S4-4-2 | BRN-LAS_124-S4-4-2-2.3-System | LAS_124 | 2.3 | Execute Periodic Review | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_124 | BRN-LAS_124-S4-4-2 | BRN-LAS_124-S4-4-2-2.4-System | LAS_124 | 2.4 | Setup of periodic task in relevant system | System | 0.2 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_124 | BRN-LAS_124-I1-3-3 | BRN-LAS_124-I1-3-3-3.1-System | LAS_124 | 3.1 | Change Control Management including impact assessment | System | 0.5 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_124 | BRN-LAS_124-I1-3-3 | BRN-LAS_124-I1-3-3-3.2-System | LAS_124 | 3.2 | Implement a process of automatic data backup | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_124 | BRN-LAS_124-I1-3-3 | BRN-LAS_124-I1-3-3-3.3-Generic | LAS_124 | 3.3 | If automatic backup its not possible, document manual backups of system data with a proper frequency to be defined in a dedicated procedure | Generic | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_124 | BRN-LAS_124-I1-3-3 | BRN-LAS_124-I1-3-3-3.4-System | LAS_124 | 3.4 | Test and document the implemented changes | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_124 | BRN-LAS_124-I1-3-3 | BRN-LAS_124-I1-3-3-3.5-System | LAS_124 | 3.5 | Update relevant SOP | System | 0.2 | 0.2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_124 | BRN-LAS_124-I2-3-4 | BRN-LAS_124-I2-3-4-4.1-System | LAS_124 | 4.1 | Change Control Management including impact assessment | System | 0.5 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_124 | BRN-LAS_124-I2-3-4 | BRN-LAS_124-I2-3-4-4.2-System | LAS_124 | 4.2 | Change permissions for users not authorized to modify data, preventing the deletion or alteration. | System | 0.5 | 0 | NO | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_124 | BRN-LAS_124-I2-3-4 | BRN-LAS_124-I2-3-4-4.3-System | LAS_124 | 4.3 | Test and document the configuration changes | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_124 | BRN-LAS_124-I2-3-4 | BRN-LAS_124-I2-3-4-4.4-System | LAS_124 | 4.4 | Update relevant SOP | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_124 | BRN-LAS_124-I3-3-5 | BRN-LAS_124-I3-3-5-5.1-System | LAS_124 | 5.1 | Change Control Management including impact assessment | System | 0.5 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_124 | BRN-LAS_124-I3-3-5 | BRN-LAS_124-I3-3-5-5.2-System | LAS_124 | 5.2 | Configure the protection of input data through an automatic security policy or folder restrictions | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_124 | BRN-LAS_124-I3-3-5 | BRN-LAS_124-I3-3-5-5.3-System | LAS_124 | 5.3 | Configure user privileges to prevent the deletion or alteration of input data | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_124 | BRN-LAS_124-I3-3-5 | BRN-LAS_124-I3-3-5-5.4-System | LAS_124 | 5.4 | Test and document the configuration changes | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_124 | BRN-LAS_124-I3-3-5 | BRN-LAS_124-I3-3-5-5.5-System | LAS_124 | 5.5 | Update relevant SOP | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_124 | BRN-LAS_124-I4-3-6 | BRN-LAS_124-I4-3-6-6.1-System | LAS_124 | 6.1 | Check the system's behaviour towards all electronic records. If autosave is not enforced by the system, define a secure and protected location to save the output records | System | 1 | 1.5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_124 | BRN-LAS_124-I4-3-6 | BRN-LAS_124-I4-3-6-6.2-System | LAS_124 | 6.2 | Test and document the automatic process implemented or the manual workaround for saving output records | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_124 | BRN-LAS_124-I4-3-6 | BRN-LAS_124-I4-3-6-6.3-System | LAS_124 | 6.3 | Update relevant SOP and, if required, schedule a SW update to include autosave of output records | System | 0.5 | 0 | NO | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_124 | BRN-LAS_124-T3-4-7 | BRN-LAS_124-T3-4-7-7.1-Generic | LAS_124 | 7.1 | Issue and approve a fully compliant Audit Trail Review Working Instruction | Generic | 0.5 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_124 | BRN-LAS_124-T3-4-7 | BRN-LAS_124-T3-4-7-7.2-System | LAS_124 | 7.2 | Execute Audit Trail Review Working Instruction: - perform Data Assessment for Electronic Records managed by the system - update Operational Method SOP (Methods/Instrument) - update test documentation | System | 0.5 | 2.5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_124 | BRN-LAS_124-T3-4-7 | BRN-LAS_124-T3-4-7-7.3-System | LAS_124 | 7.3 | Setup of periodic task | System | 0.2 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_124 | BRN-LAS_124-VD1-3-8 | BRN-LAS_124-VD1-3-8-8.1-System | LAS_124 | 8.1 | Review the Computer System Validation in place and identify the missing/incomplete validation documents or testing protocols | System | 1 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started | Validation Plan not present, Global CSV SOPs not applied., Traceability Matrix is not present, VR (called Qualifizierungsbericht, eng. Qualification report) not complete, URS document present but it is missing Functional Process Requirements, Access Control and Security Roles partially covered, no reference to regulatory rules (e.g. Annex11 coverage), Configuration Specification not identified., Risk Assessment not present, Testing only for IQ/OQ for the Control System. The level of detail is not consistent with DI expectations, i.e. Security/Integrity/Traceability verifications. Missing tests for documental checks (e.g. Users List, SOPs, etc.), functional checks (Part 11 and Annex 11 verifications), PQ not identified.
BRN | BRN-LAS_124 | BRN-LAS_124-VD1-3-8 | BRN-LAS_124-VD1-3-8-8.2-System | LAS_124 | 8.2 | Issue and approve the missing validation documentation | System | 2 | 3 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_124 | BRN-LAS_124-VD1-3-8 | BRN-LAS_124-VD1-3-8-8.3-System | LAS_124 | 8.3 | Perform and document the missing/incomplete tests | System | 3 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_124 | BRN-LAS_124-VD1-3-8 | BRN-LAS_124-VD1-3-8-8.4-System | LAS_124 | 8.4 | Assure the Traceability of the testing with coded requirements against coded test and update the documentation accordingly | System | 2 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_127 | BRN-LAS_127-S3-5-1 | BRN-LAS_127-S3-5-1-1.1-Generic | LAS_127 | 1.1 | Issue and approve a Security SOP with proper PW security features according to best practices (length, complexity, expiring) | Generic | 1 | 5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_127 | BRN-LAS_127-S3-5-1 | BRN-LAS_127-S3-5-1-1.2-System | LAS_127 | 1.2 | Update all passwords according to the approved Security SOP | System | 1 | 0.1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_127 | BRN-LAS_127-S3-5-1 | BRN-LAS_127-S3-5-1-1.3-System | LAS_127 | 1.3 | Test and document the Password policies | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_127 | BRN-LAS_127-S4-4-2 | BRN-LAS_127-S4-4-2-2.1-System | LAS_127 | 2.1 | Issue a User List with the actual status of users | System | 0.1 | 0.5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_127 | BRN-LAS_127-S4-4-2 | BRN-LAS_127-S4-4-2-2.2-Generic | LAS_127 | 2.2 | Issue and approve a Periodic Review for User List | Generic | 0.1 | 0.5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_127 | BRN-LAS_127-S4-4-2 | BRN-LAS_127-S4-4-2-2.3-System | LAS_127 | 2.3 | Execute Periodic Review | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_127 | BRN-LAS_127-S4-4-2 | BRN-LAS_127-S4-4-2-2.4-System | LAS_127 | 2.4 | Setup of periodic task in relevant system | System | 0.2 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_127 | BRN-LAS_127-I1-3-3 | BRN-LAS_127-I1-3-3-3.1-System | LAS_127 | 3.1 | Change Control Management including impact assessment | System | 0.5 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_127 | BRN-LAS_127-I1-3-3 | BRN-LAS_127-I1-3-3-3.2-System | LAS_127 | 3.2 | Implement a process of automatic data backup | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_127 | BRN-LAS_127-I1-3-3 | BRN-LAS_127-I1-3-3-3.3-Generic | LAS_127 | 3.3 | If automatic backup its not possible, document manual backups of system data with a proper frequency to be defined in a dedicated procedure | Generic | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_127 | BRN-LAS_127-I1-3-3 | BRN-LAS_127-I1-3-3-3.4-System | LAS_127 | 3.4 | Test and document the implemented changes | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_127 | BRN-LAS_127-I1-3-3 | BRN-LAS_127-I1-3-3-3.5-System | LAS_127 | 3.5 | Update relevant SOP | System | 0.2 | 0.2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_127 | BRN-LAS_127-I2-3-4 | BRN-LAS_127-I2-3-4-4.1-System | LAS_127 | 4.1 | Change Control Management including impact assessment | System | 0.5 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_127 | BRN-LAS_127-I2-3-4 | BRN-LAS_127-I2-3-4-4.2-System | LAS_127 | 4.2 | Change permissions for users not authorized to modify data, preventing the deletion or alteration. | System | 0.5 | 0 | NO | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_127 | BRN-LAS_127-I2-3-4 | BRN-LAS_127-I2-3-4-4.3-System | LAS_127 | 4.3 | Test and document the configuration changes | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_127 | BRN-LAS_127-I2-3-4 | BRN-LAS_127-I2-3-4-4.4-System | LAS_127 | 4.4 | Update relevant SOP | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_127 | BRN-LAS_127-I3-3-5 | BRN-LAS_127-I3-3-5-5.1-System | LAS_127 | 5.1 | Change Control Management including impact assessment | System | 0.5 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_127 | BRN-LAS_127-I3-3-5 | BRN-LAS_127-I3-3-5-5.2-System | LAS_127 | 5.2 | Configure the protection of input data through an automatic security policy or folder restrictions | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_127 | BRN-LAS_127-I3-3-5 | BRN-LAS_127-I3-3-5-5.3-System | LAS_127 | 5.3 | Configure user privileges to prevent the deletion or alteration of input data | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_127 | BRN-LAS_127-I3-3-5 | BRN-LAS_127-I3-3-5-5.4-System | LAS_127 | 5.4 | Test and document the configuration changes | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_127 | BRN-LAS_127-I3-3-5 | BRN-LAS_127-I3-3-5-5.5-System | LAS_127 | 5.5 | Update relevant SOP | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_127 | BRN-LAS_127-I4-3-6 | BRN-LAS_127-I4-3-6-6.1-System | LAS_127 | 6.1 | Check the system's behaviour towards all electronic records. If autosave is not enforced by the system, define a secure and protected location to save the output records | System | 1 | 1.5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_127 | BRN-LAS_127-I4-3-6 | BRN-LAS_127-I4-3-6-6.2-System | LAS_127 | 6.2 | Test and document the automatic process implemented or the manual workaround for saving output records | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_127 | BRN-LAS_127-I4-3-6 | BRN-LAS_127-I4-3-6-6.3-System | LAS_127 | 6.3 | Update relevant SOP and, if required, schedule a SW update to include autosave of output records | System | 0.5 | 0 | NO | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_127 | BRN-LAS_127-T3-4-7 | BRN-LAS_127-T3-4-7-7.1-Generic | LAS_127 | 7.1 | Issue and approve a fully compliant Audit Trail Review Working Instruction | Generic | 0.5 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_127 | BRN-LAS_127-T3-4-7 | BRN-LAS_127-T3-4-7-7.2-System | LAS_127 | 7.2 | Execute Audit Trail Review Working Instruction: - perform Data Assessment for Electronic Records managed by the system - update Operational Method SOP (Methods/Instrument) - update test documentation | System | 0.5 | 2.5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_127 | BRN-LAS_127-T3-4-7 | BRN-LAS_127-T3-4-7-7.3-System | LAS_127 | 7.3 | Setup of periodic task | System | 0.2 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_127 | BRN-LAS_127-VD1-3-8 | BRN-LAS_127-VD1-3-8-8.1-System | LAS_127 | 8.1 | Review the Computer System Validation in place and identify the missing/incomplete validation documents or testing protocols | System | 1 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started | Validation Plan not present, Global CSV SOPs not applied., Traceability Matrix is not present, VR (called Qualifizierungsbericht, eng. Qualification report) not complete, URS document present but it is missing Functional Process Requirements, Access Control and Security Roles partially covered, no reference to regulatory rules (e.g. Annex11 coverage), Configuration Specification not identified., Risk Assessment not present, Testing only for IQ/OQ for the Control System. The level of detail is not consistent with DI expectations, i.e. Security/Integrity/Traceability verifications. Missing tests for documental checks (e.g. Users List, SOPs, etc.), functional checks (Part 11 and Annex 11 verifications), PQ not identified.
BRN | BRN-LAS_127 | BRN-LAS_127-VD1-3-8 | BRN-LAS_127-VD1-3-8-8.2-System | LAS_127 | 8.2 | Issue and approve the missing validation documentation | System | 2 | 3 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_127 | BRN-LAS_127-VD1-3-8 | BRN-LAS_127-VD1-3-8-8.3-System | LAS_127 | 8.3 | Perform and document the missing/incomplete tests | System | 3 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_127 | BRN-LAS_127-VD1-3-8 | BRN-LAS_127-VD1-3-8-8.4-System | LAS_127 | 8.4 | Assure the Traceability of the testing with coded requirements against coded test and update the documentation accordingly | System | 2 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_130 | BRN-LAS_130-S3-5-1 | BRN-LAS_130-S3-5-1-1.1-Generic | LAS_130 | 1.1 | Issue and approve a Security SOP with proper PW security features according to best practices (length, complexity, expiring) | Generic | 1 | 5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto |  | To be started
BRN | BRN-LAS_130 | BRN-LAS_130-S3-5-1 | BRN-LAS_130-S3-5-1-1.2-System | LAS_130 | 1.2 | Update all passwords according to the approved Security SOP | System | 1 | 0.1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto |  | To be started
BRN | BRN-LAS_130 | BRN-LAS_130-S3-5-1 | BRN-LAS_130-S3-5-1-1.3-System | LAS_130 | 1.3 | Test and document the Password policies | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto |  | To be started
BRN | BRN-LAS_130 | BRN-LAS_130-S4-4-2 | BRN-LAS_130-S4-4-2-2.1-System | LAS_130 | 2.1 | Issue a User List with the actual status of users | System | 0.1 | 0.5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto |  | To be started
BRN | BRN-LAS_130 | BRN-LAS_130-S4-4-2 | BRN-LAS_130-S4-4-2-2.2-Generic | LAS_130 | 2.2 | Issue and approve a Periodic Review for User List | Generic | 0.1 | 0.5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto |  | To be started
BRN | BRN-LAS_130 | BRN-LAS_130-S4-4-2 | BRN-LAS_130-S4-4-2-2.3-System | LAS_130 | 2.3 | Execute Periodic Review | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto |  | To be started
BRN | BRN-LAS_130 | BRN-LAS_130-S4-4-2 | BRN-LAS_130-S4-4-2-2.4-System | LAS_130 | 2.4 | Setup of periodic task in relevant system | System | 0.2 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto |  | To be started
BRN | BRN-LAS_130 | BRN-LAS_130-I1-3-3 | BRN-LAS_130-I1-3-3-3.1-System | LAS_130 | 3.1 | Change Control Management including impact assessment | System | 0.5 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto |  | To be started
BRN | BRN-LAS_130 | BRN-LAS_130-I1-3-3 | BRN-LAS_130-I1-3-3-3.2-System | LAS_130 | 3.2 | Implement a process of automatic data backup | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto |  | To be started
BRN | BRN-LAS_130 | BRN-LAS_130-I1-3-3 | BRN-LAS_130-I1-3-3-3.3-Generic | LAS_130 | 3.3 | If automatic backup its not possible, document manual backups of system data with a proper frequency to be defined in a dedicated procedure | Generic | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto |  | To be started
BRN | BRN-LAS_130 | BRN-LAS_130-I1-3-3 | BRN-LAS_130-I1-3-3-3.4-System | LAS_130 | 3.4 | Test and document the implemented changes | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto |  | To be started
BRN | BRN-LAS_130 | BRN-LAS_130-I1-3-3 | BRN-LAS_130-I1-3-3-3.5-System | LAS_130 | 3.5 | Update relevant SOP | System | 0.2 | 0.2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto |  | To be started
BRN | BRN-LAS_130 | BRN-LAS_130-I2-3-4 | BRN-LAS_130-I2-3-4-4.1-System | LAS_130 | 4.1 | Change Control Management including impact assessment | System | 0.5 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto |  | To be started
BRN | BRN-LAS_130 | BRN-LAS_130-I2-3-4 | BRN-LAS_130-I2-3-4-4.2-System | LAS_130 | 4.2 | Change permissions for users not authorized to modify data, preventing the deletion or alteration. | System | 0.5 | 0 | NO | LES Lab Support | Valeria Geraci | Dario Ruberto |  | To be started
BRN | BRN-LAS_130 | BRN-LAS_130-I2-3-4 | BRN-LAS_130-I2-3-4-4.3-System | LAS_130 | 4.3 | Test and document the configuration changes | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto |  | To be started
BRN | BRN-LAS_130 | BRN-LAS_130-I2-3-4 | BRN-LAS_130-I2-3-4-4.4-System | LAS_130 | 4.4 | Update relevant SOP | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto |  | To be started
BRN | BRN-LAS_130 | BRN-LAS_130-I3-3-5 | BRN-LAS_130-I3-3-5-5.1-System | LAS_130 | 5.1 | Change Control Management including impact assessment | System | 0.5 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto |  | To be started
BRN | BRN-LAS_130 | BRN-LAS_130-I3-3-5 | BRN-LAS_130-I3-3-5-5.2-System | LAS_130 | 5.2 | Configure the protection of input data through an automatic security policy or folder restrictions | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto |  | To be started
BRN | BRN-LAS_130 | BRN-LAS_130-I3-3-5 | BRN-LAS_130-I3-3-5-5.3-System | LAS_130 | 5.3 | Configure user privileges to prevent the deletion or alteration of input data | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto |  | To be started
BRN | BRN-LAS_130 | BRN-LAS_130-I3-3-5 | BRN-LAS_130-I3-3-5-5.4-System | LAS_130 | 5.4 | Test and document the configuration changes | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto |  | To be started
BRN | BRN-LAS_130 | BRN-LAS_130-I3-3-5 | BRN-LAS_130-I3-3-5-5.5-System | LAS_130 | 5.5 | Update relevant SOP | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto |  | To be started
BRN | BRN-LAS_130 | BRN-LAS_130-I4-3-6 | BRN-LAS_130-I4-3-6-6.1-System | LAS_130 | 6.1 | Check the system's behaviour towards all electronic records. If autosave is not enforced by the system, define a secure and protected location to save the output records | System | 1 | 1.5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto |  | To be started
BRN | BRN-LAS_130 | BRN-LAS_130-I4-3-6 | BRN-LAS_130-I4-3-6-6.2-System | LAS_130 | 6.2 | Test and document the automatic process implemented or the manual workaround for saving output records | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto |  | To be started
BRN | BRN-LAS_130 | BRN-LAS_130-I4-3-6 | BRN-LAS_130-I4-3-6-6.3-System | LAS_130 | 6.3 | Update relevant SOP and, if required, schedule a SW update to include autosave of output records | System | 0.5 | 0 | NO | LES Lab Support | Valeria Geraci | Dario Ruberto |  | To be started
BRN | BRN-LAS_130 | BRN-LAS_130-T3-4-7 | BRN-LAS_130-T3-4-7-7.1-Generic | LAS_130 | 7.1 | Issue and approve a fully compliant Audit Trail Review Working Instruction | Generic | 0.5 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto |  | To be started
BRN | BRN-LAS_130 | BRN-LAS_130-T3-4-7 | BRN-LAS_130-T3-4-7-7.2-System | LAS_130 | 7.2 | Execute Audit Trail Review Working Instruction: - perform Data Assessment for Electronic Records managed by the system - update Operational Method SOP (Methods/Instrument) - update test documentation | System | 0.5 | 2.5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto |  | To be started
BRN | BRN-LAS_130 | BRN-LAS_130-T3-4-7 | BRN-LAS_130-T3-4-7-7.3-System | LAS_130 | 7.3 | Setup of periodic task | System | 0.2 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto |  | To be started
BRN | BRN-LAS_130 | BRN-LAS_130-VD1-3-8 | BRN-LAS_130-VD1-3-8-8.1-System | LAS_130 | 8.1 | Review the Computer System Validation in place and identify the missing/incomplete validation documents or testing protocols | System | 1 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto |  | To be started | Computerized system validation documentation is not complete for Systems (VP, URS, RA, VR and Traceability Matrix are not present), Global CSV SOPs not applied., User Requirements, Functional/Process Risk Analysis or Configuration Specifications (included Security Matrix), is not included in the validation life-cycle., IQ/OQ/PQ not identified.
BRN | BRN-LAS_130 | BRN-LAS_130-VD1-3-8 | BRN-LAS_130-VD1-3-8-8.2-System | LAS_130 | 8.2 | Issue and approve the missing validation documentation | System | 2 | 3 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto |  | To be started
BRN | BRN-LAS_130 | BRN-LAS_130-VD1-3-8 | BRN-LAS_130-VD1-3-8-8.3-System | LAS_130 | 8.3 | Perform and document the missing/incomplete tests | System | 3 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto |  | To be started
BRN | BRN-LAS_130 | BRN-LAS_130-VD1-3-8 | BRN-LAS_130-VD1-3-8-8.4-System | LAS_130 | 8.4 | Assure the Traceability of the testing with coded requirements against coded test and update the documentation accordingly | System | 2 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto |  | To be started
BRN | BRN-LAS_131 | BRN-LAS_131-S3-5-1 | BRN-LAS_131-S3-5-1-1.1-Generic | LAS_131 | 1.1 | Issue and approve a Security SOP with proper PW security features according to best practices (length, complexity, expiring) | Generic | 1 | 5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto |  | To be started
BRN | BRN-LAS_131 | BRN-LAS_131-S3-5-1 | BRN-LAS_131-S3-5-1-1.2-System | LAS_131 | 1.2 | Update all passwords according to the approved Security SOP | System | 1 | 0.1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto |  | To be started
BRN | BRN-LAS_131 | BRN-LAS_131-S3-5-1 | BRN-LAS_131-S3-5-1-1.3-System | LAS_131 | 1.3 | Test and document the Password policies | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto |  | To be started
BRN | BRN-LAS_131 | BRN-LAS_131-S4-4-2 | BRN-LAS_131-S4-4-2-2.1-System | LAS_131 | 2.1 | Issue a User List with the actual status of users | System | 0.1 | 0.5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto |  | To be started
BRN | BRN-LAS_131 | BRN-LAS_131-S4-4-2 | BRN-LAS_131-S4-4-2-2.2-Generic | LAS_131 | 2.2 | Issue and approve a Periodic Review for User List | Generic | 0.1 | 0.5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto |  | To be started
BRN | BRN-LAS_131 | BRN-LAS_131-S4-4-2 | BRN-LAS_131-S4-4-2-2.3-System | LAS_131 | 2.3 | Execute Periodic Review | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto |  | To be started
BRN | BRN-LAS_131 | BRN-LAS_131-S4-4-2 | BRN-LAS_131-S4-4-2-2.4-System | LAS_131 | 2.4 | Setup of periodic task in relevant system | System | 0.2 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto |  | To be started
BRN | BRN-LAS_131 | BRN-LAS_131-I1-3-3 | BRN-LAS_131-I1-3-3-3.1-System | LAS_131 | 3.1 | Change Control Management including impact assessment | System | 0.5 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto |  | To be started
BRN | BRN-LAS_131 | BRN-LAS_131-I1-3-3 | BRN-LAS_131-I1-3-3-3.2-System | LAS_131 | 3.2 | Implement a process of automatic data backup | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto |  | To be started
BRN | BRN-LAS_131 | BRN-LAS_131-I1-3-3 | BRN-LAS_131-I1-3-3-3.3-Generic | LAS_131 | 3.3 | If automatic backup its not possible, document manual backups of system data with a proper frequency to be defined in a dedicated procedure | Generic | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto |  | To be started
BRN | BRN-LAS_131 | BRN-LAS_131-I1-3-3 | BRN-LAS_131-I1-3-3-3.4-System | LAS_131 | 3.4 | Test and document the implemented changes | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto |  | To be started
BRN | BRN-LAS_131 | BRN-LAS_131-I1-3-3 | BRN-LAS_131-I1-3-3-3.5-System | LAS_131 | 3.5 | Update relevant SOP | System | 0.2 | 0.2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto |  | To be started
BRN | BRN-LAS_131 | BRN-LAS_131-I2-3-4 | BRN-LAS_131-I2-3-4-4.1-System | LAS_131 | 4.1 | Change Control Management including impact assessment | System | 0.5 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto |  | To be started
BRN | BRN-LAS_131 | BRN-LAS_131-I2-3-4 | BRN-LAS_131-I2-3-4-4.2-System | LAS_131 | 4.2 | Change permissions for users not authorized to modify data, preventing the deletion or alteration. | System | 0.5 | 0 | NO | LES Lab Support | Valeria Geraci | Dario Ruberto |  | To be started
BRN | BRN-LAS_131 | BRN-LAS_131-I2-3-4 | BRN-LAS_131-I2-3-4-4.3-System | LAS_131 | 4.3 | Test and document the configuration changes | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto |  | To be started
BRN | BRN-LAS_131 | BRN-LAS_131-I2-3-4 | BRN-LAS_131-I2-3-4-4.4-System | LAS_131 | 4.4 | Update relevant SOP | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto |  | To be started
BRN | BRN-LAS_131 | BRN-LAS_131-I3-3-5 | BRN-LAS_131-I3-3-5-5.1-System | LAS_131 | 5.1 | Change Control Management including impact assessment | System | 0.5 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto |  | To be started
BRN | BRN-LAS_131 | BRN-LAS_131-I3-3-5 | BRN-LAS_131-I3-3-5-5.2-System | LAS_131 | 5.2 | Configure the protection of input data through an automatic security policy or folder restrictions | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto |  | To be started
BRN | BRN-LAS_131 | BRN-LAS_131-I3-3-5 | BRN-LAS_131-I3-3-5-5.3-System | LAS_131 | 5.3 | Configure user privileges to prevent the deletion or alteration of input data | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto |  | To be started
BRN | BRN-LAS_131 | BRN-LAS_131-I3-3-5 | BRN-LAS_131-I3-3-5-5.4-System | LAS_131 | 5.4 | Test and document the configuration changes | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto |  | To be started
BRN | BRN-LAS_131 | BRN-LAS_131-I3-3-5 | BRN-LAS_131-I3-3-5-5.5-System | LAS_131 | 5.5 | Update relevant SOP | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto |  | To be started
BRN | BRN-LAS_131 | BRN-LAS_131-I4-3-6 | BRN-LAS_131-I4-3-6-6.1-System | LAS_131 | 6.1 | Check the system's behaviour towards all electronic records. If autosave is not enforced by the system, define a secure and protected location to save the output records | System | 1 | 1.5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto |  | To be started
BRN | BRN-LAS_131 | BRN-LAS_131-I4-3-6 | BRN-LAS_131-I4-3-6-6.2-System | LAS_131 | 6.2 | Test and document the automatic process implemented or the manual workaround for saving output records | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto |  | To be started
BRN | BRN-LAS_131 | BRN-LAS_131-I4-3-6 | BRN-LAS_131-I4-3-6-6.3-System | LAS_131 | 6.3 | Update relevant SOP and, if required, schedule a SW update to include autosave of output records | System | 0.5 | 0 | NO | LES Lab Support | Valeria Geraci | Dario Ruberto |  | To be started
BRN | BRN-LAS_131 | BRN-LAS_131-T3-4-7 | BRN-LAS_131-T3-4-7-7.1-Generic | LAS_131 | 7.1 | Issue and approve a fully compliant Audit Trail Review Working Instruction | Generic | 0.5 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto |  | To be started
BRN | BRN-LAS_131 | BRN-LAS_131-T3-4-7 | BRN-LAS_131-T3-4-7-7.2-System | LAS_131 | 7.2 | Execute Audit Trail Review Working Instruction: - perform Data Assessment for Electronic Records managed by the system - update Operational Method SOP (Methods/Instrument) - update test documentation | System | 0.5 | 2.5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto |  | To be started
BRN | BRN-LAS_131 | BRN-LAS_131-T3-4-7 | BRN-LAS_131-T3-4-7-7.3-System | LAS_131 | 7.3 | Setup of periodic task | System | 0.2 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto |  | To be started
BRN | BRN-LAS_131 | BRN-LAS_131-VD1-3-8 | BRN-LAS_131-VD1-3-8-8.1-System | LAS_131 | 8.1 | Review the Computer System Validation in place and identify the missing/incomplete validation documents or testing protocols | System | 1 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto |  | To be started | Computerized system validation documentation is not complete for Systems (VP, URS, RA, VR and Traceability Matrix are not present), Global CSV SOPs not applied., User Requirements, Functional/Process Risk Analysis or Configuration Specifications (included Security Matrix), is not included in the validation life-cycle., IQ/OQ/PQ not identified. The level of detail is not consistent with DI expectations, i.e. Security/Integrity/Traceability verifications. Missing tests for documental checks (e.g. Users List, SOPs, etc.), functional checks (Part 11 verifications), and missing performance checks (e.g. Method Creation, Data Acquisition, and Report Printing)
BRN | BRN-LAS_131 | BRN-LAS_131-VD1-3-8 | BRN-LAS_131-VD1-3-8-8.2-System | LAS_131 | 8.2 | Issue and approve the missing validation documentation | System | 2 | 3 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto |  | To be started
BRN | BRN-LAS_131 | BRN-LAS_131-VD1-3-8 | BRN-LAS_131-VD1-3-8-8.3-System | LAS_131 | 8.3 | Perform and document the missing/incomplete tests | System | 3 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto |  | To be started
BRN | BRN-LAS_131 | BRN-LAS_131-VD1-3-8 | BRN-LAS_131-VD1-3-8-8.4-System | LAS_131 | 8.4 | Assure the Traceability of the testing with coded requirements against coded test and update the documentation accordingly | System | 2 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto |  | To be started
BRN | BRN-LAS_145 | BRN-LAS_145-S1-3-1 | BRN-LAS_145-S1-3-1-1.1-System | LAS_145 | 1.1 | Change Control Management including impact assessment | System | 0.5 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_145 | BRN-LAS_145-S1-3-1 | BRN-LAS_145-S1-3-1-1.2-System | LAS_145 | 1.2 | Create personal and unique accounts in system | System | 1 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_145 | BRN-LAS_145-S1-3-1 | BRN-LAS_145-S1-3-1-1.3-System | LAS_145 | 1.3 | Remove generic accounts from the system | System | 0.5 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_145 | BRN-LAS_145-S1-3-1 | BRN-LAS_145-S1-3-1-1.4-System | LAS_145 | 1.4 | Issue and approve an updated User List | System | 0.1 | 0.5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_145 | BRN-LAS_145-S1-3-1 | BRN-LAS_145-S1-3-1-1.5-System | LAS_145 | 1.5 | Update relevant SOPs and periodically review the User List according to procedure | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_145 | BRN-LAS_145-S2-4-2 | BRN-LAS_145-S2-4-2-2.1-System | LAS_145 | 2.1 | Change Control Management including impact assessment | System | 0.5 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_145 | BRN-LAS_145-S2-4-2 | BRN-LAS_145-S2-4-2-2.2-System | LAS_145 | 2.2 | Configure 3 user groups and define the role of each user | System | 1 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_145 | BRN-LAS_145-S2-4-2 | BRN-LAS_145-S2-4-2-2.3-System | LAS_145 | 2.3 | Configure user privileges according to a proper segregation of duties | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_145 | BRN-LAS_145-S2-4-2 | BRN-LAS_145-S2-4-2-2.4-System | LAS_145 | 2.4 | Test and document the configuration changes | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_145 | BRN-LAS_145-S2-4-2 | BRN-LAS_145-S2-4-2-2.5-System | LAS_145 | 2.5 | Update relevant SOP | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_145 | BRN-LAS_145-S3-5-3 | BRN-LAS_145-S3-5-3-3.1-System | LAS_145 | 3.1 | Investigate with the supplier if it is possible to upgrade the software to grant proper security features for user access | System | 1 | 0 | NO | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_145 | BRN-LAS_145-S3-5-3 | BRN-LAS_145-S3-5-3-3.2-Generic | LAS_145 | 3.2 | Define the Password features in an approved procedure | Generic | 1 | 3 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_145 | BRN-LAS_145-S3-5-3 | BRN-LAS_145-S3-5-3-3.3-System | LAS_145 | 3.3 | Personnel training to access the system | System | 0.5 | 0.5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_145 | BRN-LAS_145-S3-5-3 | BRN-LAS_145-S3-5-3-3.4-System | LAS_145 | 3.4 | Update relevant SOP | System | 0.2 | 0.2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_145 | BRN-LAS_145-S4-4-4 | BRN-LAS_145-S4-4-4-4.1-System | LAS_145 | 4.1 | Issue a User List with the actual status of users | System | 0.1 | 0.5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_145 | BRN-LAS_145-S4-4-4 | BRN-LAS_145-S4-4-4-4.2-Generic | LAS_145 | 4.2 | Issue and approve a Periodic Review for User List | Generic | 0.1 | 0.5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_145 | BRN-LAS_145-S4-4-4 | BRN-LAS_145-S4-4-4-4.3-System | LAS_145 | 4.3 | Execute Periodic Review | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_145 | BRN-LAS_145-S4-4-4 | BRN-LAS_145-S4-4-4-4.4-System | LAS_145 | 4.4 | Setup of periodic task in relevant system | System | 0.2 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_145 | BRN-LAS_145-I1-3-5 | BRN-LAS_145-I1-3-5-5.1-System | LAS_145 | 5.1 | Change Control Management including impact assessment | System | 0.5 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_145 | BRN-LAS_145-I1-3-5 | BRN-LAS_145-I1-3-5-5.2-System | LAS_145 | 5.2 | Implement a process of automatic data backup | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_145 | BRN-LAS_145-I1-3-5 | BRN-LAS_145-I1-3-5-5.3-Generic | LAS_145 | 5.3 | If automatic backup its not possible, document manual backups of system data with a proper frequency to be defined in a dedicated procedure | Generic | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_145 | BRN-LAS_145-I1-3-5 | BRN-LAS_145-I1-3-5-5.4-System | LAS_145 | 5.4 | Test and document the implemented changes | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_145 | BRN-LAS_145-I1-3-5 | BRN-LAS_145-I1-3-5-5.5-System | LAS_145 | 5.5 | Update relevant SOP | System | 0.2 | 0.2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_145 | BRN-LAS_145-I3-3-6 | BRN-LAS_145-I3-3-6-6.1-System | LAS_145 | 6.1 | Change Control Management including impact assessment | System | 0.5 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_145 | BRN-LAS_145-I3-3-6 | BRN-LAS_145-I3-3-6-6.2-System | LAS_145 | 6.2 | Configure the protection of input data through an automatic security policy or folder restrictions | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_145 | BRN-LAS_145-I3-3-6 | BRN-LAS_145-I3-3-6-6.3-System | LAS_145 | 6.3 | Configure user privileges to prevent the deletion or alteration of input data | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_145 | BRN-LAS_145-I3-3-6 | BRN-LAS_145-I3-3-6-6.4-System | LAS_145 | 6.4 | Test and document the configuration changes | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_145 | BRN-LAS_145-I3-3-6 | BRN-LAS_145-I3-3-6-6.5-System | LAS_145 | 6.5 | Update relevant SOP | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_145 | BRN-LAS_145-T1-3-7 | BRN-LAS_145-T1-3-7-7.1-System | LAS_145 | 7.1 | Change Control Management including impact assessment | System | 0.5 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_145 | BRN-LAS_145-T1-3-7 | BRN-LAS_145-T1-3-7-7.2-System | LAS_145 | 7.2 | Update Audit Trail functionality in order to track and record modifications to ER | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_145 | BRN-LAS_145-T1-3-7 | BRN-LAS_145-T1-3-7-7.3-Generic | LAS_145 | 7.3 | If Audit Trail is not compliant (e.g. does not track modifications to ER), implement a paper based management of system regulated input records (i.e. methods) with the following paper procedures: -user access log -verification log to be used by the Users before launching a method -traceability log to be used by the system administrators when changing a method | Generic | 2 | 3 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_145 | BRN-LAS_145-T1-3-7 | BRN-LAS_145-T1-3-7-7.4-System | LAS_145 | 7.4 | Test and document that Audit Trail is fully compliant or, in case of paper Audit Trail, that the personnel is trained to use it | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_145 | BRN-LAS_145-T1-3-7 | BRN-LAS_145-T1-3-7-7.5-System | LAS_145 | 7.5 | Update relevant SOP | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_145 | BRN-LAS_145-T2-3-8 | BRN-LAS_145-T2-3-8-8.1-System | LAS_145 | 8.1 | Change Control Management including impact assessment | System | 0.5 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_145 | BRN-LAS_145-T2-3-8 | BRN-LAS_145-T2-3-8-8.2-System | LAS_145 | 8.2 | Verify if Time Reference protection can be configured within the system | System | 0.5 | 0.5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_145 | BRN-LAS_145-T2-3-8 | BRN-LAS_145-T2-3-8-8.3-Generic | LAS_145 | 8.3 | If not possible, manage Date & Time protection through an approved procedure | Generic | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_145 | BRN-LAS_145-T2-3-8 | BRN-LAS_145-T2-3-8-8.4-System | LAS_145 | 8.4 | Test and document configuration changes | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_145 | BRN-LAS_145-T2-3-8 | BRN-LAS_145-T2-3-8-8.5-System | LAS_145 | 8.5 | Update relevant SOP | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_145 | BRN-LAS_145-T3-4-9 | BRN-LAS_145-T3-4-9-9.1-Generic | LAS_145 | 9.1 | If there is no Audit Trail Process fully compliant, issue and approve a fully compliant Audit Trail Review Working Instruction | Generic | 1 | 3 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_145 | BRN-LAS_145-T3-4-9 | BRN-LAS_145-T3-4-9-9.2-System | LAS_145 | 9.2 | Execute Audit Trail Review Working Instruction: - perform Data Assessment for Electronic Records managed by the system - update Operational Method SOP (Methods/Instrument) - update test documentation | System | 0.5 | 2.5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_145 | BRN-LAS_145-T3-4-9 | BRN-LAS_145-T3-4-9-9.3-System | LAS_145 | 9.3 | Setup of periodic task | System | 0.2 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_145 | BRN-LAS_145-VD1-3-10 | BRN-LAS_145-VD1-3-10-10.1-System | LAS_145 | 10.1 | Review the Computer System Validation in place and identify the missing/incomplete validation documents or testing protocols | System | 1 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started | Computerized system validation documentation is not complete for Systems (VP, URS, RA, VR and Traceability Matrix are not present), Global CSV SOPs not applied., User Requirements, Functional/Process Risk Analysis or Configuration Specifications (included Security Matrix), is not included in the validation life-cycle., IQ/OQ/PQ not identified. The level of detail is not consistent with DI expectations, i.e. Security/Integrity/Traceability verifications. Missing tests for documental checks (e.g. Users List, SOPs, etc.), functional checks (Part 11 verifications), and missing performance checks (e.g. Method Creation, Data Acquisition, and Report Printing)
BRN | BRN-LAS_145 | BRN-LAS_145-VD1-3-10 | BRN-LAS_145-VD1-3-10-10.2-System | LAS_145 | 10.2 | Issue and approve the missing validation documentation | System | 2 | 3 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_145 | BRN-LAS_145-VD1-3-10 | BRN-LAS_145-VD1-3-10-10.3-System | LAS_145 | 10.3 | Perform and document the missing/incomplete tests | System | 3 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_145 | BRN-LAS_145-VD1-3-10 | BRN-LAS_145-VD1-3-10-10.4-System | LAS_145 | 10.4 | Assure the Traceability of the testing with coded requirements against coded test and update the documentation accordingly | System | 2 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_168 | BRN-LAS_168-S1-1-1 | BRN-LAS_168-S1-1-1-1.1-System | LAS_168 | 1.1 | Change Control Management including impact assessment | System | 0.5 | 0 | YES | LES Supporting Systems | Valeria Geraci | Amit Krishna | 30/06/2026 | To be started
BRN | BRN-LAS_168 | BRN-LAS_168-S1-1-1 | BRN-LAS_168-S1-1-1-1.2-System | LAS_168 | 1.2 | Update system administration SOP to describe generic account's access mode and functionalities, and how to keep track of its actions | System | 1 | 2 | YES | LES Supporting Systems | Valeria Geraci | Amit Krishna | 30/06/2026 | To be started
BRN | BRN-LAS_168 | BRN-LAS_168-S2-2-2 | BRN-LAS_168-S2-2-2-2.1-System | LAS_168 | 2.1 | Define the User Groups and the related privileges in an approved procedure | System | 2 | 3 | YES | LES Supporting Systems | Valeria Geraci | Amit Krishna | 30/06/2026 | To be started
BRN | BRN-LAS_168 | BRN-LAS_168-S2-2-2 | BRN-LAS_168-S2-2-2-2.2-System | LAS_168 | 2.2 | Personnel training to access the system | System | 0.5 | 0.5 | YES | LES Supporting Systems | Valeria Geraci | Amit Krishna | 30/06/2026 | To be started
BRN | BRN-LAS_168 | BRN-LAS_168-S2-2-2 | BRN-LAS_168-S2-2-2-2.3-System | LAS_168 | 2.3 | Update relevant SOP | System | 1 | 2 | YES | LES Supporting Systems | Valeria Geraci | Amit Krishna | 30/06/2026 | To be started
BRN | BRN-LAS_168 | BRN-LAS_168-S4-2-3 | BRN-LAS_168-S4-2-3-3.1-System | LAS_168 | 3.1 | Updating the User List with the actual status of users | System | 0.1 | 0.5 | YES | LES Supporting Systems | Valeria Geraci | Amit Krishna | 30/06/2026 | To be started
BRN | BRN-LAS_168 | BRN-LAS_168-S4-2-3 | BRN-LAS_168-S4-2-3-3.2-Generic | LAS_168 | 3.2 | Issue and approve a Periodic Review for User List | Generic | 0.1 | 0.5 | YES | LES Supporting Systems | Valeria Geraci | Amit Krishna | 30/06/2026 | To be started
BRN | BRN-LAS_168 | BRN-LAS_168-S4-2-3 | BRN-LAS_168-S4-2-3-3.3-System | LAS_168 | 3.3 | Execute Periodic Review | System | 1 | 2 | YES | LES Supporting Systems | Valeria Geraci | Amit Krishna | 30/06/2026 | To be started
BRN | BRN-LAS_168 | BRN-LAS_168-S4-2-3 | BRN-LAS_168-S4-2-3-3.4-System | LAS_168 | 3.4 | Setup of periodic task in relevant system | System | 0.2 | 0 | YES | LES Supporting Systems | Valeria Geraci | Amit Krishna | 30/06/2026 | To be started
BRN | BRN-LAS_168 | BRN-LAS_168-I2-1-4 | BRN-LAS_168-I2-1-4-4.1-System | LAS_168 | 4.1 | Change Control Management including impact assessment | System | 0.5 | 0 | YES | LES Supporting Systems | Valeria Geraci | Amit Krishna | 30/06/2026 | To be started
BRN | BRN-LAS_168 | BRN-LAS_168-I2-1-4 | BRN-LAS_168-I2-1-4-4.2-System | LAS_168 | 4.2 | Change permissions for users not authorized to modify data, preventing the deletion or alteration. | System | 0.5 | 0 | NO | LES Supporting Systems | Valeria Geraci | Amit Krishna | 30/06/2026 | To be started
BRN | BRN-LAS_168 | BRN-LAS_168-I2-1-4 | BRN-LAS_168-I2-1-4-4.3-System | LAS_168 | 4.3 | Test and document the configuration changes | System | 1 | 2 | YES | LES Supporting Systems | Valeria Geraci | Amit Krishna | 30/06/2026 | To be started
BRN | BRN-LAS_168 | BRN-LAS_168-I2-1-4 | BRN-LAS_168-I2-1-4-4.4-System | LAS_168 | 4.4 | Update relevant SOP | System | 0.5 | 1 | YES | LES Supporting Systems | Valeria Geraci | Amit Krishna | 30/06/2026 | To be started
BRN | BRN-LAS_168 | BRN-LAS_168-T3-2-5 | BRN-LAS_168-T3-2-5-5.1-Generic | LAS_168 | 5.1 | Issue and approve a fully compliant Audit Trail Review Working Instruction | Generic | 0.5 | 2 | YES | LES Supporting Systems | Valeria Geraci | Amit Krishna | 30/06/2026 | To be started
BRN | BRN-LAS_168 | BRN-LAS_168-T3-2-5 | BRN-LAS_168-T3-2-5-5.2-System | LAS_168 | 5.2 | Execute Audit Trail Review Working Instruction: - perform Data Assessment for Electronic Records managed by the system - update Operational Method SOP (Methods/Instrument) - update test documentation | System | 0.5 | 2.5 | YES | LES Supporting Systems | Valeria Geraci | Amit Krishna | 30/06/2026 | To be started
BRN | BRN-LAS_168 | BRN-LAS_168-T3-2-5 | BRN-LAS_168-T3-2-5-5.3-System | LAS_168 | 5.3 | Setup of periodic task | System | 0.2 | 0 | YES | LES Supporting Systems | Valeria Geraci | Amit Krishna | 30/06/2026 | To be started
BRN | BRN-LAS_168 | BRN-LAS_168-ES1-1-6 | BRN-LAS_168-ES1-1-6-6.1-System | LAS_168 | 6.1 | Issue and approve a procedure for the review of Electronic Signatures execution | System | 1 | 2 | YES | LES Supporting Systems | Valeria Geraci | Amit Krishna | 30/06/2026 | To be started
BRN | BRN-LAS_168 | BRN-LAS_168-ES1-1-6 | BRN-LAS_168-ES1-1-6-6.2-System | LAS_168 | 6.2 | Perform the ES review in order to check the failed attempts or suspicious patterns | System | 1 | 1 | YES | LES Supporting Systems | Valeria Geraci | Amit Krishna | 30/06/2026 | To be started
BRN | BRN-LAS_168 | BRN-LAS_168-ES1-1-6 | BRN-LAS_168-ES1-1-6-6.3-System | LAS_168 | 6.3 | Setup of periodic task | System | 0.2 | 0 | YES | LES Supporting Systems | Valeria Geraci | Amit Krishna | 30/06/2026 | To be started
BRN | BRN-LAS_168 | BRN-LAS_168-ES2-1-7 | BRN-LAS_168-ES2-1-7-7.1-System | LAS_168 | 7.1 | Issue and approve a procedure for the review of e-signed reports | System | 1 | 2 | YES | LES Supporting Systems | Valeria Geraci | Amit Krishna | 30/06/2026 | To be started
BRN | BRN-LAS_168 | BRN-LAS_168-ES2-1-7 | BRN-LAS_168-ES2-1-7-7.2-System | LAS_168 | 7.2 | Perform the ES review in order to check that all reports are properly signed | System | 1 | 1 | YES | LES Supporting Systems | Valeria Geraci | Amit Krishna | 30/06/2026 | To be started
BRN | BRN-LAS_168 | BRN-LAS_168-ES2-1-7 | BRN-LAS_168-ES2-1-7-7.3-System | LAS_168 | 7.3 | Setup of periodic task | System | 0.2 | 0 | YES | LES Supporting Systems | Valeria Geraci | Amit Krishna | 30/06/2026 | To be started
BRN | BRN-LAS_168 | BRN-LAS_168-ES3-1-8 | BRN-LAS_168-ES3-1-8-8.1-System | LAS_168 | 8.1 | Verify if reports are configured with all required ES components. If not, configure the report or implement a procedural control of the ES changes | System | 0.5 | 1 | YES | LES Supporting Systems | Valeria Geraci | Amit Krishna | 30/06/2026 | To be started
BRN | BRN-LAS_168 | BRN-LAS_168-ES3-1-8 | BRN-LAS_168-ES3-1-8-8.2-System | LAS_168 | 8.2 | Test and document configuration changes | System | 1 | 2 | YES | LES Supporting Systems | Valeria Geraci | Amit Krishna | 30/06/2026 | To be started
BRN | BRN-LAS_168 | BRN-LAS_168-VD1-1-9 | BRN-LAS_168-VD1-1-9-9.1-System | LAS_168 | 9.1 | Review the Computer System Validation in place and identify the missing/incomplete validation documents or testing protocols | System | 1 | 1 | YES | LES Supporting Systems | Valeria Geraci | Amit Krishna | 30/06/2026 | To be started | Documentation not present, Global CSV SOPs not applied., Present IQ from supplier. Some tests can be leveraged, however should be double checked with the system, Present OQ from supplier. Some tests can be leveraged, however should be double checked with the system, Documentation not present
BRN | BRN-LAS_168 | BRN-LAS_168-VD1-1-9 | BRN-LAS_168-VD1-1-9-9.2-System | LAS_168 | 9.2 | Issue and approve the missing validation documentation | System | 2 | 3 | YES | LES Supporting Systems | Valeria Geraci | Amit Krishna | 30/06/2026 | To be started
BRN | BRN-LAS_168 | BRN-LAS_168-VD1-1-9 | BRN-LAS_168-VD1-1-9-9.3-System | LAS_168 | 9.3 | Perform and document the missing/incomplete tests | System | 3 | 0 | YES | LES Supporting Systems | Valeria Geraci | Amit Krishna | 30/06/2026 | To be started
BRN | BRN-LAS_168 | BRN-LAS_168-VD1-1-9 | BRN-LAS_168-VD1-1-9-9.4-System | LAS_168 | 9.4 | Assure the Traceability of the testing with coded requirements against coded test and update the documentation accordingly | System | 2 | 2 | YES | LES Supporting Systems | Valeria Geraci | Amit Krishna | 30/06/2026 | To be started
BRN | BRN-LAS_201 | BRN-LAS_201-S3-4-1 | BRN-LAS_201-S3-4-1-1.1-Generic | LAS_201 | 1.1 | Issue and approve a Security SOP with proper PW security features according to best practices (length, complexity, expiring) | Generic | 1 | 5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto |  | To be started
BRN | BRN-LAS_201 | BRN-LAS_201-S3-4-1 | BRN-LAS_201-S3-4-1-1.2-System | LAS_201 | 1.2 | Update all passwords according to the approved Security SOP | System | 1 | 0.1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto |  | To be started
BRN | BRN-LAS_201 | BRN-LAS_201-S3-4-1 | BRN-LAS_201-S3-4-1-1.3-System | LAS_201 | 1.3 | Test and document the Password policies | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto |  | To be started
BRN | BRN-LAS_201 | BRN-LAS_201-S4-3-2 | BRN-LAS_201-S4-3-2-2.1-System | LAS_201 | 2.1 | Issue a User List with the actual status of users | System | 0.1 | 0.5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto |  | To be started
BRN | BRN-LAS_201 | BRN-LAS_201-S4-3-2 | BRN-LAS_201-S4-3-2-2.2-Generic | LAS_201 | 2.2 | Issue and approve a Periodic Review for User List | Generic | 0.1 | 0.5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto |  | To be started
BRN | BRN-LAS_201 | BRN-LAS_201-S4-3-2 | BRN-LAS_201-S4-3-2-2.3-System | LAS_201 | 2.3 | Execute Periodic Review | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto |  | To be started
BRN | BRN-LAS_201 | BRN-LAS_201-S4-3-2 | BRN-LAS_201-S4-3-2-2.4-System | LAS_201 | 2.4 | Setup of periodic task in relevant system | System | 0.2 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto |  | To be started
BRN | BRN-LAS_201 | BRN-LAS_201-I2-2-3 | BRN-LAS_201-I2-2-3-3.1-System | LAS_201 | 3.1 | Change Control Management including impact assessment | System | 0.5 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2026-12-31 | To be started
BRN | BRN-LAS_201 | BRN-LAS_201-I2-2-3 | BRN-LAS_201-I2-2-3-3.2-System | LAS_201 | 3.2 | Change permissions for users not authorized to modify data, preventing the deletion or alteration. | System | 0.5 | 0 | NO | LES Lab Support | Valeria Geraci | Dario Ruberto | 2026-12-31 | To be started
BRN | BRN-LAS_201 | BRN-LAS_201-I2-2-3 | BRN-LAS_201-I2-2-3-3.3-System | LAS_201 | 3.3 | Test and document the configuration changes | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2026-12-31 | To be started
BRN | BRN-LAS_201 | BRN-LAS_201-I2-2-3 | BRN-LAS_201-I2-2-3-3.4-System | LAS_201 | 3.4 | Update relevant SOP | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2026-12-31 | To be started
BRN | BRN-LAS_201 | BRN-LAS_201-I3-2-4 | BRN-LAS_201-I3-2-4-4.1-System | LAS_201 | 4.1 | Change Control Management including impact assessment | System | 0.5 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2026-12-31 | To be started
BRN | BRN-LAS_201 | BRN-LAS_201-I3-2-4 | BRN-LAS_201-I3-2-4-4.2-System | LAS_201 | 4.2 | Configure the protection of input data through an automatic security policy or folder restrictions | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2026-12-31 | To be started
BRN | BRN-LAS_201 | BRN-LAS_201-I3-2-4 | BRN-LAS_201-I3-2-4-4.3-System | LAS_201 | 4.3 | Configure user privileges to prevent the deletion or alteration of input data | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2026-12-31 | To be started
BRN | BRN-LAS_201 | BRN-LAS_201-I3-2-4 | BRN-LAS_201-I3-2-4-4.4-System | LAS_201 | 4.4 | Test and document the configuration changes | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2026-12-31 | To be started
BRN | BRN-LAS_201 | BRN-LAS_201-I3-2-4 | BRN-LAS_201-I3-2-4-4.5-System | LAS_201 | 4.5 | Update relevant SOP | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2026-12-31 | To be started
BRN | BRN-LAS_201 | BRN-LAS_201-T3-3-5 | BRN-LAS_201-T3-3-5-5.1-Generic | LAS_201 | 5.1 | Issue and approve a fully compliant Audit Trail Review Working Instruction | Generic | 0.5 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto |  | To be started
BRN | BRN-LAS_201 | BRN-LAS_201-T3-3-5 | BRN-LAS_201-T3-3-5-5.2-System | LAS_201 | 5.2 | Execute Audit Trail Review Working Instruction: - perform Data Assessment for Electronic Records managed by the system - update Operational Method SOP (Methods/Instrument) - update test documentation | System | 0.5 | 2.5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto |  | To be started
BRN | BRN-LAS_201 | BRN-LAS_201-T3-3-5 | BRN-LAS_201-T3-3-5-5.3-System | LAS_201 | 5.3 | Setup of periodic task | System | 0.2 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto |  | To be started
BRN | BRN-LAS_201 | BRN-LAS_201-VD1-2-6 | BRN-LAS_201-VD1-2-6-6.1-System | LAS_201 | 6.1 | Review the Computer System Validation in place and identify the missing/incomplete validation documents or testing protocols | System | 1 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2026-12-31 | To be started | Validation Plan not present, Global CSV SOPs not applied., VR (called Qualifizierungsbericht, eng. Qualification report) not complete, URS document present but it is missing Functional Process Requirements, Access Control and Security Roles partially covered, no reference to regulatory rules (e.g. Annex11 coverage), Not complete, Risk Assessment not present, Testing only for IQ/OQ for the Control System. The level of detail is not consistent with DI expectations, i.e. Security/Integrity/Traceability verifications. Missing tests for documental checks (e.g. Users List, SOPs, etc.), functional checks (Part 11 and Annex 11 verifications), PQ protocol not identified.
BRN | BRN-LAS_201 | BRN-LAS_201-VD1-2-6 | BRN-LAS_201-VD1-2-6-6.2-System | LAS_201 | 6.2 | Issue and approve the missing validation documentation | System | 2 | 3 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2026-12-31 | To be started
BRN | BRN-LAS_201 | BRN-LAS_201-VD1-2-6 | BRN-LAS_201-VD1-2-6-6.3-System | LAS_201 | 6.3 | Perform and document the missing/incomplete tests | System | 3 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2026-12-31 | To be started
BRN | BRN-LAS_201 | BRN-LAS_201-VD1-2-6 | BRN-LAS_201-VD1-2-6-6.4-System | LAS_201 | 6.4 | Assure the Traceability of the testing with coded requirements against coded test and update the documentation accordingly | System | 2 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2026-12-31 | To be started
BRN | BRN-LAS_206 | BRN-LAS_206-S3-4-7 | BRN-LAS_206-S3-4-7-7.1-Generic | LAS_206 | 7.1 | Issue and approve a Security SOP with proper PW security features according to best practices (length, complexity, expiring) | Generic | 1 | 5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto |  | To be started
BRN | BRN-LAS_206 | BRN-LAS_206-S3-4-7 | BRN-LAS_206-S3-4-7-7.2-System | LAS_206 | 7.2 | Update all passwords according to the approved Security SOP | System | 1 | 0.1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto |  | To be started
BRN | BRN-LAS_206 | BRN-LAS_206-S3-4-7 | BRN-LAS_206-S3-4-7-7.3-System | LAS_206 | 7.3 | Test and document the Password policies | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto |  | To be started
BRN | BRN-LAS_206 | BRN-LAS_206-S4-3-8 | BRN-LAS_206-S4-3-8-8.1-System | LAS_206 | 8.1 | Issue a User List with the actual status of users | System | 0.1 | 0.5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto |  | To be started
BRN | BRN-LAS_206 | BRN-LAS_206-S4-3-8 | BRN-LAS_206-S4-3-8-8.2-Generic | LAS_206 | 8.2 | Issue and approve a Periodic Review for User List | Generic | 0.1 | 0.5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto |  | To be started
BRN | BRN-LAS_206 | BRN-LAS_206-S4-3-8 | BRN-LAS_206-S4-3-8-8.3-System | LAS_206 | 8.3 | Execute Periodic Review | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto |  | To be started
BRN | BRN-LAS_206 | BRN-LAS_206-S4-3-8 | BRN-LAS_206-S4-3-8-8.4-System | LAS_206 | 8.4 | Setup of periodic task in relevant system | System | 0.2 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto |  | To be started
BRN | BRN-LAS_206 | BRN-LAS_206-I2-2-9 | BRN-LAS_206-I2-2-9-9.1-System | LAS_206 | 9.1 | Change Control Management including impact assessment | System | 0.5 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2026-12-31 | To be started
BRN | BRN-LAS_206 | BRN-LAS_206-I2-2-9 | BRN-LAS_206-I2-2-9-9.2-System | LAS_206 | 9.2 | Change permissions for users not authorized to modify data, preventing the deletion or alteration. | System | 0.5 | 0 | NO | LES Lab Support | Valeria Geraci | Dario Ruberto | 2026-12-31 | To be started
BRN | BRN-LAS_206 | BRN-LAS_206-I2-2-9 | BRN-LAS_206-I2-2-9-9.3-System | LAS_206 | 9.3 | Test and document the configuration changes | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2026-12-31 | To be started
BRN | BRN-LAS_206 | BRN-LAS_206-I2-2-9 | BRN-LAS_206-I2-2-9-9.4-System | LAS_206 | 9.4 | Update relevant SOP | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2026-12-31 | To be started
BRN | BRN-LAS_206 | BRN-LAS_206-I3-2-10 | BRN-LAS_206-I3-2-10-10.1-System | LAS_206 | 10.1 | Change Control Management including impact assessment | System | 0.5 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2026-12-31 | To be started
BRN | BRN-LAS_206 | BRN-LAS_206-I3-2-10 | BRN-LAS_206-I3-2-10-10.2-System | LAS_206 | 10.2 | Configure the protection of input data through an automatic security policy or folder restrictions | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2026-12-31 | To be started
BRN | BRN-LAS_206 | BRN-LAS_206-I3-2-10 | BRN-LAS_206-I3-2-10-10.3-System | LAS_206 | 10.3 | Configure user privileges to prevent the deletion or alteration of input data | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2026-12-31 | To be started
BRN | BRN-LAS_206 | BRN-LAS_206-I3-2-10 | BRN-LAS_206-I3-2-10-10.4-System | LAS_206 | 10.4 | Test and document the configuration changes | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2026-12-31 | To be started
BRN | BRN-LAS_206 | BRN-LAS_206-I3-2-10 | BRN-LAS_206-I3-2-10-10.5-System | LAS_206 | 10.5 | Update relevant SOP | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2026-12-31 | To be started
BRN | BRN-LAS_206 | BRN-LAS_206-T3-3-11 | BRN-LAS_206-T3-3-11-11.1-Generic | LAS_206 | 11.1 | Issue and approve a fully compliant Audit Trail Review Working Instruction | Generic | 0.5 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto |  | To be started
BRN | BRN-LAS_206 | BRN-LAS_206-T3-3-11 | BRN-LAS_206-T3-3-11-11.2-System | LAS_206 | 11.2 | Execute Audit Trail Review Working Instruction: - perform Data Assessment for Electronic Records managed by the system - update Operational Method SOP (Methods/Instrument) - update test documentation | System | 0.5 | 2.5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto |  | To be started
BRN | BRN-LAS_206 | BRN-LAS_206-T3-3-11 | BRN-LAS_206-T3-3-11-11.3-System | LAS_206 | 11.3 | Setup of periodic task | System | 0.2 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto |  | To be started
BRN | BRN-LAS_206 | BRN-LAS_206-VD1-2-12 | BRN-LAS_206-VD1-2-12-12.1-System | LAS_206 | 12.1 | Review the Computer System Validation in place and identify the missing/incomplete validation documents or testing protocols | System | 1 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2026-12-31 | To be started | Validation Plan not present, Global CSV SOPs not applied., VR (called Qualifizierungsbericht, eng. Qualification report) not complete, URS document present but it is missing Functional Process Requirements, Access Control and Security Roles partially covered, no reference to regulatory rules (e.g. Annex11 coverage), Not complete, Risk Assessment not present, Testing only for IQ/OQ for the Control System. The level of detail is not consistent with DI expectations, i.e. Security/Integrity/Traceability verifications. Missing tests for documental checks (e.g. Users List, SOPs, etc.), functional checks (Part 11 and Annex 11 verifications), PQ not identified.
BRN | BRN-LAS_206 | BRN-LAS_206-VD1-2-12 | BRN-LAS_206-VD1-2-12-12.2-System | LAS_206 | 12.2 | Issue and approve the missing validation documentation | System | 2 | 3 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2026-12-31 | To be started
BRN | BRN-LAS_206 | BRN-LAS_206-VD1-2-12 | BRN-LAS_206-VD1-2-12-12.3-System | LAS_206 | 12.3 | Perform and document the missing/incomplete tests | System | 3 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2026-12-31 | To be started
BRN | BRN-LAS_206 | BRN-LAS_206-VD1-2-12 | BRN-LAS_206-VD1-2-12-12.4-System | LAS_206 | 12.4 | Assure the Traceability of the testing with coded requirements against coded test and update the documentation accordingly | System | 2 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2026-12-31 | To be started
BRN | BRN-LAS_207 | BRN-LAS_207-S3-4-1 | BRN-LAS_207-S3-4-1-1.1-Generic | LAS_207 | 1.1 | Issue and approve a Security SOP with proper PW security features according to best practices (length, complexity, expiring) | Generic | 1 | 5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto |  | To be started
BRN | BRN-LAS_207 | BRN-LAS_207-S3-4-1 | BRN-LAS_207-S3-4-1-1.2-System | LAS_207 | 1.2 | Update all passwords according to the approved Security SOP | System | 1 | 0.1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto |  | To be started
BRN | BRN-LAS_207 | BRN-LAS_207-S3-4-1 | BRN-LAS_207-S3-4-1-1.3-System | LAS_207 | 1.3 | Test and document the Password policies | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto |  | To be started
BRN | BRN-LAS_207 | BRN-LAS_207-S4-3-2 | BRN-LAS_207-S4-3-2-2.1-System | LAS_207 | 2.1 | Issue a User List with the actual status of users | System | 0.1 | 0.5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto |  | To be started
BRN | BRN-LAS_207 | BRN-LAS_207-S4-3-2 | BRN-LAS_207-S4-3-2-2.2-Generic | LAS_207 | 2.2 | Issue and approve a Periodic Review for User List | Generic | 0.1 | 0.5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto |  | To be started
BRN | BRN-LAS_207 | BRN-LAS_207-S4-3-2 | BRN-LAS_207-S4-3-2-2.3-System | LAS_207 | 2.3 | Execute Periodic Review | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto |  | To be started
BRN | BRN-LAS_207 | BRN-LAS_207-S4-3-2 | BRN-LAS_207-S4-3-2-2.4-System | LAS_207 | 2.4 | Setup of periodic task in relevant system | System | 0.2 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto |  | To be started
BRN | BRN-LAS_207 | BRN-LAS_207-I2-2-3 | BRN-LAS_207-I2-2-3-3.1-System | LAS_207 | 3.1 | Change Control Management including impact assessment | System | 0.5 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2026-12-31 | To be started
BRN | BRN-LAS_207 | BRN-LAS_207-I2-2-3 | BRN-LAS_207-I2-2-3-3.2-System | LAS_207 | 3.2 | Change permissions for users not authorized to modify data, preventing the deletion or alteration. | System | 0.5 | 0 | NO | LES Lab Support | Valeria Geraci | Dario Ruberto | 2026-12-31 | To be started
BRN | BRN-LAS_207 | BRN-LAS_207-I2-2-3 | BRN-LAS_207-I2-2-3-3.3-System | LAS_207 | 3.3 | Test and document the configuration changes | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2026-12-31 | To be started
BRN | BRN-LAS_207 | BRN-LAS_207-I2-2-3 | BRN-LAS_207-I2-2-3-3.4-System | LAS_207 | 3.4 | Update relevant SOP | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2026-12-31 | To be started
BRN | BRN-LAS_207 | BRN-LAS_207-I3-2-4 | BRN-LAS_207-I3-2-4-4.1-System | LAS_207 | 4.1 | Change Control Management including impact assessment | System | 0.5 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2026-12-31 | To be started
BRN | BRN-LAS_207 | BRN-LAS_207-I3-2-4 | BRN-LAS_207-I3-2-4-4.2-System | LAS_207 | 4.2 | Configure the protection of input data through an automatic security policy or folder restrictions | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2026-12-31 | To be started
BRN | BRN-LAS_207 | BRN-LAS_207-I3-2-4 | BRN-LAS_207-I3-2-4-4.3-System | LAS_207 | 4.3 | Configure user privileges to prevent the deletion or alteration of input data | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2026-12-31 | To be started
BRN | BRN-LAS_207 | BRN-LAS_207-I3-2-4 | BRN-LAS_207-I3-2-4-4.4-System | LAS_207 | 4.4 | Test and document the configuration changes | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2026-12-31 | To be started
BRN | BRN-LAS_207 | BRN-LAS_207-I3-2-4 | BRN-LAS_207-I3-2-4-4.5-System | LAS_207 | 4.5 | Update relevant SOP | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2026-12-31 | To be started
BRN | BRN-LAS_207 | BRN-LAS_207-T3-3-5 | BRN-LAS_207-T3-3-5-5.1-Generic | LAS_207 | 5.1 | Issue and approve a fully compliant Audit Trail Review Working Instruction | Generic | 0.5 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto |  | To be started
BRN | BRN-LAS_207 | BRN-LAS_207-T3-3-5 | BRN-LAS_207-T3-3-5-5.2-System | LAS_207 | 5.2 | Execute Audit Trail Review Working Instruction: - perform Data Assessment for Electronic Records managed by the system - update Operational Method SOP (Methods/Instrument) - update test documentation | System | 0.5 | 2.5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto |  | To be started
BRN | BRN-LAS_207 | BRN-LAS_207-T3-3-5 | BRN-LAS_207-T3-3-5-5.3-System | LAS_207 | 5.3 | Setup of periodic task | System | 0.2 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto |  | To be started
BRN | BRN-LAS_207 | BRN-LAS_207-VD1-2-6 | BRN-LAS_207-VD1-2-6-6.1-System | LAS_207 | 6.1 | Review the Computer System Validation in place and identify the missing/incomplete validation documents or testing protocols | System | 1 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2026-12-31 | To be started | Validation Plan not present, Global CSV SOPs not applied., VR (called Qualifizierungsbericht, eng. Qualification report) not complete, URS document present but it is missing Functional Process Requirements, Access Control and Security Roles partially covered, no reference to regulatory rules (e.g. Annex11 coverage), Not complete, Risk Assessment not present, Testing only for IQ/OQ for the Control System. The level of detail is not consistent with DI expectations, i.e. Security/Integrity/Traceability verifications. Missing tests for documental checks (e.g. Users List, SOPs, etc.), functional checks (Part 11 and Annex 11 verifications), PQ not identified.
BRN | BRN-LAS_207 | BRN-LAS_207-VD1-2-6 | BRN-LAS_207-VD1-2-6-6.2-System | LAS_207 | 6.2 | Issue and approve the missing validation documentation | System | 2 | 3 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2026-12-31 | To be started
BRN | BRN-LAS_207 | BRN-LAS_207-VD1-2-6 | BRN-LAS_207-VD1-2-6-6.3-System | LAS_207 | 6.3 | Perform and document the missing/incomplete tests | System | 3 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2026-12-31 | To be started
BRN | BRN-LAS_207 | BRN-LAS_207-VD1-2-6 | BRN-LAS_207-VD1-2-6-6.4-System | LAS_207 | 6.4 | Assure the Traceability of the testing with coded requirements against coded test and update the documentation accordingly | System | 2 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2026-12-31 | To be started
BRN | BRN-LAS_208 | BRN-LAS_208-S1-3-1 | BRN-LAS_208-S1-3-1-1.1-System | LAS_208 | 1.1 | Change Control Management including impact assessment | System | 0.5 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_208 | BRN-LAS_208-S1-3-1 | BRN-LAS_208-S1-3-1-1.2-System | LAS_208 | 1.2 | Verify the system's access capability and user management compliance | System | 0.5 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_208 | BRN-LAS_208-S1-3-1 | BRN-LAS_208-S1-3-1-1.3-System | LAS_208 | 1.3 | Create personal and unique accounts in system | System | 1 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_208 | BRN-LAS_208-S1-3-1 | BRN-LAS_208-S1-3-1-1.4-System | LAS_208 | 1.4 | Issue and approve an updated User List | System | 0.1 | 0.5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_208 | BRN-LAS_208-S1-3-1 | BRN-LAS_208-S1-3-1-1.5-System | LAS_208 | 1.5 | Update relevant SOPs and periodically review the User List according to procedure | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_208 | BRN-LAS_208-S2-4-2 | BRN-LAS_208-S2-4-2-2.1-System | LAS_208 | 2.1 | Define the User Groups and the related privileges in an approved procedure | System | 2 | 3 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_208 | BRN-LAS_208-S2-4-2 | BRN-LAS_208-S2-4-2-2.2-System | LAS_208 | 2.2 | Configure 3 user groups and define the role of each user | System | 1 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_208 | BRN-LAS_208-S2-4-2 | BRN-LAS_208-S2-4-2-2.3-System | LAS_208 | 2.3 | Configure user privileges according to a proper segregation of duties | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_208 | BRN-LAS_208-S2-4-2 | BRN-LAS_208-S2-4-2-2.4-System | LAS_208 | 2.4 | Test and document the configuration changes | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_208 | BRN-LAS_208-S2-4-2 | BRN-LAS_208-S2-4-2-2.5-System | LAS_208 | 2.5 | Update relevant SOP | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_208 | BRN-LAS_208-S3-5-3 | BRN-LAS_208-S3-5-3-3.1-Generic | LAS_208 | 3.1 | Issue and approve a Security SOP with proper PW security features according to best practices (length, complexity, expiring) | Generic | 1 | 5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_208 | BRN-LAS_208-S3-5-3 | BRN-LAS_208-S3-5-3-3.2-System | LAS_208 | 3.2 | Update all passwords according to the approved Security SOP | System | 1 | 0.1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_208 | BRN-LAS_208-S3-5-3 | BRN-LAS_208-S3-5-3-3.3-System | LAS_208 | 3.3 | Test and document the Password policies | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_208 | BRN-LAS_208-S4-4-4 | BRN-LAS_208-S4-4-4-4.1-System | LAS_208 | 4.1 | Issue a User List with the actual status of users | System | 0.1 | 0.5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_208 | BRN-LAS_208-S4-4-4 | BRN-LAS_208-S4-4-4-4.2-Generic | LAS_208 | 4.2 | Issue and approve a Periodic Review for User List | Generic | 0.1 | 0.5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_208 | BRN-LAS_208-S4-4-4 | BRN-LAS_208-S4-4-4-4.3-System | LAS_208 | 4.3 | Execute Periodic Review | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_208 | BRN-LAS_208-S4-4-4 | BRN-LAS_208-S4-4-4-4.4-System | LAS_208 | 4.4 | Setup of periodic task in relevant system | System | 0.2 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_208 | BRN-LAS_208-I3-3-5 | BRN-LAS_208-I3-3-5-5.1-System | LAS_208 | 5.1 | Change Control Management including impact assessment | System | 0.5 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_208 | BRN-LAS_208-I3-3-5 | BRN-LAS_208-I3-3-5-5.2-System | LAS_208 | 5.2 | Configure the protection of input data through an automatic security policy or folder restrictions | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_208 | BRN-LAS_208-I3-3-5 | BRN-LAS_208-I3-3-5-5.3-System | LAS_208 | 5.3 | Configure user privileges to prevent the deletion or alteration of input data | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_208 | BRN-LAS_208-I3-3-5 | BRN-LAS_208-I3-3-5-5.4-System | LAS_208 | 5.4 | Test and document the configuration changes | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_208 | BRN-LAS_208-I3-3-5 | BRN-LAS_208-I3-3-5-5.5-System | LAS_208 | 5.5 | Update relevant SOP | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_208 | BRN-LAS_208-T1-3-6 | BRN-LAS_208-T1-3-6-6.1-System | LAS_208 | 6.1 | Change Control Management including impact assessment | System | 0.5 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_208 | BRN-LAS_208-T1-3-6 | BRN-LAS_208-T1-3-6-6.2-System | LAS_208 | 6.2 | Update Audit Trail functionality in order to track and record modifications to ER | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_208 | BRN-LAS_208-T1-3-6 | BRN-LAS_208-T1-3-6-6.3-Generic | LAS_208 | 6.3 | If Audit Trail is not compliant (e.g. does not track modifications to ER), implement a paper based management of system regulated input records (i.e. methods) with the following paper procedures: -user access log -verification log to be used by the Users before launching a method -traceability log to be used by the system administrators when changing a method | Generic | 2 | 3 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_208 | BRN-LAS_208-T1-3-6 | BRN-LAS_208-T1-3-6-6.4-System | LAS_208 | 6.4 | Test and document that Audit Trail is fully compliant or, in case of paper Audit Trail, that the personnel is trained to use it | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_208 | BRN-LAS_208-T1-3-6 | BRN-LAS_208-T1-3-6-6.5-System | LAS_208 | 6.5 | Update relevant SOP | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_208 | BRN-LAS_208-T2-3-7 | BRN-LAS_208-T2-3-7-7.1-System | LAS_208 | 7.1 | Change Control Management including impact assessment | System | 0.5 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_208 | BRN-LAS_208-T2-3-7 | BRN-LAS_208-T2-3-7-7.2-System | LAS_208 | 7.2 | Verify if Time Reference protection can be configured within the system | System | 0.5 | 0.5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_208 | BRN-LAS_208-T2-3-7 | BRN-LAS_208-T2-3-7-7.3-Generic | LAS_208 | 7.3 | If not possible, manage Date & Time protection through an approved procedure | Generic | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_208 | BRN-LAS_208-T2-3-7 | BRN-LAS_208-T2-3-7-7.4-System | LAS_208 | 7.4 | Test and document configuration changes | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_208 | BRN-LAS_208-T2-3-7 | BRN-LAS_208-T2-3-7-7.5-System | LAS_208 | 7.5 | Update relevant SOP | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_208 | BRN-LAS_208-T3-4-8 | BRN-LAS_208-T3-4-8-8.1-Generic | LAS_208 | 8.1 | If there is no Audit Trail Process fully compliant, issue and approve a fully compliant Audit Trail Review Working Instruction | Generic | 1 | 3 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_208 | BRN-LAS_208-T3-4-8 | BRN-LAS_208-T3-4-8-8.2-System | LAS_208 | 8.2 | Execute Audit Trail Review Working Instruction: - perform Data Assessment for Electronic Records managed by the system - update Operational Method SOP (Methods/Instrument) - update test documentation | System | 0.5 | 2.5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_208 | BRN-LAS_208-T3-4-8 | BRN-LAS_208-T3-4-8-8.3-System | LAS_208 | 8.3 | Setup of periodic task | System | 0.2 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_208 | BRN-LAS_208-VD1-3-9 | BRN-LAS_208-VD1-3-9-9.1-System | LAS_208 | 9.1 | Review the Computer System Validation in place and identify the missing/incomplete validation documents or testing protocols | System | 1 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started | Validation Plan has been identified, however it has been issued by the vendor and it is not covering the validation strategy regarding the Regulatory and ERES definition, Global CSV SOPs not applied., Traceability Matrix present, VR (called Qualifizierungsbericht, eng. Qualification report) does not address the procedures., URS document present but it is missing Functional Process Requirements, Access Control and Security Roles partially covered, no reference to regulatory rules (e.g. Annex11 coverage), Not present, partially covered in delivered vendor documentation, RA is identified but does not cover the risk associated to Regulatory Requirements and ERES definition., IQ/OQ has been identified, but the level of detail is not consistent with DI expectations, i.e. Security/Integrity/Traceability verifications. Missing tests for documental checks (e.g. Users List, SOPs, etc.), functional checks (Part 11 and Annex 11 verifications), PQ protocol is not identified
BRN | BRN-LAS_208 | BRN-LAS_208-VD1-3-9 | BRN-LAS_208-VD1-3-9-9.2-System | LAS_208 | 9.2 | Issue and approve the missing validation documentation | System | 2 | 3 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_208 | BRN-LAS_208-VD1-3-9 | BRN-LAS_208-VD1-3-9-9.3-System | LAS_208 | 9.3 | Perform and document the missing/incomplete tests | System | 3 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_208 | BRN-LAS_208-VD1-3-9 | BRN-LAS_208-VD1-3-9-9.4-System | LAS_208 | 9.4 | Assure the Traceability of the testing with coded requirements against coded test and update the documentation accordingly | System | 2 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_216 | BRN-LAS_216-S1-2-1 | BRN-LAS_216-S1-2-1-1.1-System | LAS_216 | 1.1 | Change Control Management including impact assessment | System | 0.5 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_216 | BRN-LAS_216-S1-2-1 | BRN-LAS_216-S1-2-1-1.2-System | LAS_216 | 1.2 | Create personal and unique accounts in system | System | 1 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_216 | BRN-LAS_216-S1-2-1 | BRN-LAS_216-S1-2-1-1.3-System | LAS_216 | 1.3 | Remove generic accounts from the system | System | 0.5 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_216 | BRN-LAS_216-S1-2-1 | BRN-LAS_216-S1-2-1-1.4-System | LAS_216 | 1.4 | Issue and approve an updated User List | System | 0.1 | 0.5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_216 | BRN-LAS_216-S1-2-1 | BRN-LAS_216-S1-2-1-1.5-System | LAS_216 | 1.5 | Update relevant SOPs and periodically review the User List according to procedure | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_216 | BRN-LAS_216-S2-3-2 | BRN-LAS_216-S2-3-2-2.1-System | LAS_216 | 2.1 | Change Control Management including impact assessment | System | 0.5 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_216 | BRN-LAS_216-S2-3-2 | BRN-LAS_216-S2-3-2-2.2-System | LAS_216 | 2.2 | Configure 3 user groups and define the role of each user | System | 1 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_216 | BRN-LAS_216-S2-3-2 | BRN-LAS_216-S2-3-2-2.3-System | LAS_216 | 2.3 | Configure user privileges according to a proper segregation of duties | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_216 | BRN-LAS_216-S2-3-2 | BRN-LAS_216-S2-3-2-2.4-System | LAS_216 | 2.4 | Test and document the configuration changes | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_216 | BRN-LAS_216-S2-3-2 | BRN-LAS_216-S2-3-2-2.5-System | LAS_216 | 2.5 | Update relevant SOP | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_216 | BRN-LAS_216-S3-4-3 | BRN-LAS_216-S3-4-3-3.1-Generic | LAS_216 | 3.1 | Issue and approve a Security SOP with proper PW security features according to best practices (length, complexity, expiring) | Generic | 1 | 5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_216 | BRN-LAS_216-S3-4-3 | BRN-LAS_216-S3-4-3-3.2-System | LAS_216 | 3.2 | Update all passwords according to the approved Security SOP | System | 1 | 0.1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_216 | BRN-LAS_216-S3-4-3 | BRN-LAS_216-S3-4-3-3.3-System | LAS_216 | 3.3 | Test and document the Password policies | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_216 | BRN-LAS_216-S4-3-4 | BRN-LAS_216-S4-3-4-4.1-System | LAS_216 | 4.1 | Issue a User List with the actual status of users | System | 0.1 | 0.5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_216 | BRN-LAS_216-S4-3-4 | BRN-LAS_216-S4-3-4-4.2-Generic | LAS_216 | 4.2 | Issue and approve a Periodic Review for User List | Generic | 0.1 | 0.5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_216 | BRN-LAS_216-S4-3-4 | BRN-LAS_216-S4-3-4-4.3-System | LAS_216 | 4.3 | Execute Periodic Review | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_216 | BRN-LAS_216-S4-3-4 | BRN-LAS_216-S4-3-4-4.4-System | LAS_216 | 4.4 | Setup of periodic task in relevant system | System | 0.2 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_216 | BRN-LAS_216-I3-2-5 | BRN-LAS_216-I3-2-5-5.1-System | LAS_216 | 5.1 | Change Control Management including impact assessment | System | 0.5 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_216 | BRN-LAS_216-I3-2-5 | BRN-LAS_216-I3-2-5-5.2-System | LAS_216 | 5.2 | Configure the protection of input data through an automatic security policy or folder restrictions | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_216 | BRN-LAS_216-I3-2-5 | BRN-LAS_216-I3-2-5-5.3-System | LAS_216 | 5.3 | Configure user privileges to prevent the deletion or alteration of input data | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_216 | BRN-LAS_216-I3-2-5 | BRN-LAS_216-I3-2-5-5.4-System | LAS_216 | 5.4 | Test and document the configuration changes | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_216 | BRN-LAS_216-I3-2-5 | BRN-LAS_216-I3-2-5-5.5-System | LAS_216 | 5.5 | Update relevant SOP | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_216 | BRN-LAS_216-T1-2-6 | BRN-LAS_216-T1-2-6-6.1-System | LAS_216 | 6.1 | Investigate with the supplier if it is possible to implement a proper configuration of the AT | System | 1 | 0 | NO | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_216 | BRN-LAS_216-T1-2-6 | BRN-LAS_216-T1-2-6-6.2-System | LAS_216 | 6.2 | Change Control Management including impact assessment | System | 0.5 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_216 | BRN-LAS_216-T1-2-6 | BRN-LAS_216-T1-2-6-6.3-System | LAS_216 | 6.3 | Configure Audit Trail functionality within the SW or, if not applicable, implement a paper based management for tracking relevant operation (i.e. old&new value, reason for change) to relevant data | System | 2 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_216 | BRN-LAS_216-T1-2-6 | BRN-LAS_216-T1-2-6-6.4-System | LAS_216 | 6.4 | Test and document configuration changes or the procedural changes | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_216 | BRN-LAS_216-T1-2-6 | BRN-LAS_216-T1-2-6-6.5-System | LAS_216 | 6.5 | Update relevant SOP | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_216 | BRN-LAS_216-T2-2-7 | BRN-LAS_216-T2-2-7-7.1-System | LAS_216 | 7.1 | Change Control Management including impact assessment | System | 0.5 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_216 | BRN-LAS_216-T2-2-7 | BRN-LAS_216-T2-2-7-7.2-System | LAS_216 | 7.2 | Verify if Time Reference protection can be configured within the system | System | 0.5 | 0.5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_216 | BRN-LAS_216-T2-2-7 | BRN-LAS_216-T2-2-7-7.3-Generic | LAS_216 | 7.3 | If not possible, manage Date & Time protection through an approved procedure | Generic | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_216 | BRN-LAS_216-T2-2-7 | BRN-LAS_216-T2-2-7-7.4-System | LAS_216 | 7.4 | Test and document configuration changes | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_216 | BRN-LAS_216-T2-2-7 | BRN-LAS_216-T2-2-7-7.5-System | LAS_216 | 7.5 | Update relevant SOP | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_216 | BRN-LAS_216-T3-3-8 | BRN-LAS_216-T3-3-8-8.1-Generic | LAS_216 | 8.1 | Issue and approve a fully compliant Audit Trail Review Working Instruction | Generic | 0.5 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_216 | BRN-LAS_216-T3-3-8 | BRN-LAS_216-T3-3-8-8.2-System | LAS_216 | 8.2 | Execute Audit Trail Review Working Instruction: - perform Data Assessment for Electronic Records managed by the system - update Operational Method SOP (Methods/Instrument) - update test documentation | System | 0.5 | 2.5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_216 | BRN-LAS_216-T3-3-8 | BRN-LAS_216-T3-3-8-8.3-System | LAS_216 | 8.3 | Setup of periodic task | System | 0.2 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_216 | BRN-LAS_216-VD1-2-9 | BRN-LAS_216-VD1-2-9-9.1-System | LAS_216 | 9.1 | Review the Computer System Validation in place and identify the missing/incomplete validation documents or testing protocols | System | 1 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started | Validation Plan not present, Global CSV SOPs not applied., Traceability Matrix present, VR (called Qualifizierungsbericht, eng. Qualification report) not complete, URS document not identified, Configuration Specification not identified., Risk Assessment not present, IQ/OQ identified, however the level of detail is not consistent with DI expectations, i.e. Security/Integrity/Traceability verifications. Missing tests for documental checks (e.g. Users List, SOPs, etc.), functional checks (Part 11 and Annex 11 verifications), PQ not identified.
BRN | BRN-LAS_216 | BRN-LAS_216-VD1-2-9 | BRN-LAS_216-VD1-2-9-9.2-System | LAS_216 | 9.2 | Issue and approve the missing validation documentation | System | 2 | 3 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_216 | BRN-LAS_216-VD1-2-9 | BRN-LAS_216-VD1-2-9-9.3-System | LAS_216 | 9.3 | Perform and document the missing/incomplete tests | System | 3 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_216 | BRN-LAS_216-VD1-2-9 | BRN-LAS_216-VD1-2-9-9.4-System | LAS_216 | 9.4 | Assure the Traceability of the testing with coded requirements against coded test and update the documentation accordingly | System | 2 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_217 | BRN-LAS_217-S1-2-1 | BRN-LAS_217-S1-2-1-1.1-System | LAS_217 | 1.1 | Change Control Management including impact assessment | System | 0.5 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_217 | BRN-LAS_217-S1-2-1 | BRN-LAS_217-S1-2-1-1.2-System | LAS_217 | 1.2 | Create personal and unique accounts in system | System | 1 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_217 | BRN-LAS_217-S1-2-1 | BRN-LAS_217-S1-2-1-1.3-System | LAS_217 | 1.3 | Remove generic accounts from the system | System | 0.5 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_217 | BRN-LAS_217-S1-2-1 | BRN-LAS_217-S1-2-1-1.4-System | LAS_217 | 1.4 | Issue and approve an updated User List | System | 0.1 | 0.5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_217 | BRN-LAS_217-S1-2-1 | BRN-LAS_217-S1-2-1-1.5-System | LAS_217 | 1.5 | Update relevant SOPs and periodically review the User List according to procedure | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_217 | BRN-LAS_217-S2-3-2 | BRN-LAS_217-S2-3-2-2.1-System | LAS_217 | 2.1 | Change Control Management including impact assessment | System | 0.5 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_217 | BRN-LAS_217-S2-3-2 | BRN-LAS_217-S2-3-2-2.2-System | LAS_217 | 2.2 | Configure 3 user groups and define the role of each user | System | 1 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_217 | BRN-LAS_217-S2-3-2 | BRN-LAS_217-S2-3-2-2.3-System | LAS_217 | 2.3 | Configure user privileges according to a proper segregation of duties | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_217 | BRN-LAS_217-S2-3-2 | BRN-LAS_217-S2-3-2-2.4-System | LAS_217 | 2.4 | Test and document the configuration changes | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_217 | BRN-LAS_217-S2-3-2 | BRN-LAS_217-S2-3-2-2.5-System | LAS_217 | 2.5 | Update relevant SOP | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_217 | BRN-LAS_217-S3-4-3 | BRN-LAS_217-S3-4-3-3.1-Generic | LAS_217 | 3.1 | Issue and approve a Security SOP with proper PW security features according to best practices (length, complexity, expiring) | Generic | 1 | 5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_217 | BRN-LAS_217-S3-4-3 | BRN-LAS_217-S3-4-3-3.2-System | LAS_217 | 3.2 | Update all passwords according to the approved Security SOP | System | 1 | 0.1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_217 | BRN-LAS_217-S3-4-3 | BRN-LAS_217-S3-4-3-3.3-System | LAS_217 | 3.3 | Test and document the Password policies | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_217 | BRN-LAS_217-S4-3-4 | BRN-LAS_217-S4-3-4-4.1-System | LAS_217 | 4.1 | Issue a User List with the actual status of users | System | 0.1 | 0.5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_217 | BRN-LAS_217-S4-3-4 | BRN-LAS_217-S4-3-4-4.2-Generic | LAS_217 | 4.2 | Issue and approve a Periodic Review for User List | Generic | 0.1 | 0.5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_217 | BRN-LAS_217-S4-3-4 | BRN-LAS_217-S4-3-4-4.3-System | LAS_217 | 4.3 | Execute Periodic Review | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_217 | BRN-LAS_217-S4-3-4 | BRN-LAS_217-S4-3-4-4.4-System | LAS_217 | 4.4 | Setup of periodic task in relevant system | System | 0.2 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_217 | BRN-LAS_217-I3-2-5 | BRN-LAS_217-I3-2-5-5.1-System | LAS_217 | 5.1 | Change Control Management including impact assessment | System | 0.5 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_217 | BRN-LAS_217-I3-2-5 | BRN-LAS_217-I3-2-5-5.2-System | LAS_217 | 5.2 | Configure the protection of input data through an automatic security policy or folder restrictions | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_217 | BRN-LAS_217-I3-2-5 | BRN-LAS_217-I3-2-5-5.3-System | LAS_217 | 5.3 | Configure user privileges to prevent the deletion or alteration of input data | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_217 | BRN-LAS_217-I3-2-5 | BRN-LAS_217-I3-2-5-5.4-System | LAS_217 | 5.4 | Test and document the configuration changes | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_217 | BRN-LAS_217-I3-2-5 | BRN-LAS_217-I3-2-5-5.5-System | LAS_217 | 5.5 | Update relevant SOP | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_217 | BRN-LAS_217-T1-2-6 | BRN-LAS_217-T1-2-6-6.1-System | LAS_217 | 6.1 | Investigate with the supplier if it is possible to implement a proper configuration of the AT | System | 1 | 0 | NO | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_217 | BRN-LAS_217-T1-2-6 | BRN-LAS_217-T1-2-6-6.2-System | LAS_217 | 6.2 | Change Control Management including impact assessment | System | 0.5 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_217 | BRN-LAS_217-T1-2-6 | BRN-LAS_217-T1-2-6-6.3-System | LAS_217 | 6.3 | Configure Audit Trail functionality within the SW or, if not applicable, implement a paper based management for tracking relevant operation (i.e. old&new value, reason for change) to relevant data | System | 2 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_217 | BRN-LAS_217-T1-2-6 | BRN-LAS_217-T1-2-6-6.4-System | LAS_217 | 6.4 | Test and document configuration changes or the procedural changes | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_217 | BRN-LAS_217-T1-2-6 | BRN-LAS_217-T1-2-6-6.5-System | LAS_217 | 6.5 | Update relevant SOP | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_217 | BRN-LAS_217-T2-2-7 | BRN-LAS_217-T2-2-7-7.1-System | LAS_217 | 7.1 | Change Control Management including impact assessment | System | 0.5 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_217 | BRN-LAS_217-T2-2-7 | BRN-LAS_217-T2-2-7-7.2-System | LAS_217 | 7.2 | Verify if Time Reference protection can be configured within the system | System | 0.5 | 0.5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_217 | BRN-LAS_217-T2-2-7 | BRN-LAS_217-T2-2-7-7.3-Generic | LAS_217 | 7.3 | If not possible, manage Date & Time protection through an approved procedure | Generic | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_217 | BRN-LAS_217-T2-2-7 | BRN-LAS_217-T2-2-7-7.4-System | LAS_217 | 7.4 | Test and document configuration changes | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_217 | BRN-LAS_217-T2-2-7 | BRN-LAS_217-T2-2-7-7.5-System | LAS_217 | 7.5 | Update relevant SOP | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_217 | BRN-LAS_217-T3-3-8 | BRN-LAS_217-T3-3-8-8.1-Generic | LAS_217 | 8.1 | Issue and approve a fully compliant Audit Trail Review Working Instruction | Generic | 0.5 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_217 | BRN-LAS_217-T3-3-8 | BRN-LAS_217-T3-3-8-8.2-System | LAS_217 | 8.2 | Execute Audit Trail Review Working Instruction: - perform Data Assessment for Electronic Records managed by the system - update Operational Method SOP (Methods/Instrument) - update test documentation | System | 0.5 | 2.5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_217 | BRN-LAS_217-T3-3-8 | BRN-LAS_217-T3-3-8-8.3-System | LAS_217 | 8.3 | Setup of periodic task | System | 0.2 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_217 | BRN-LAS_217-VD1-2-9 | BRN-LAS_217-VD1-2-9-9.1-System | LAS_217 | 9.1 | Review the Computer System Validation in place and identify the missing/incomplete validation documents or testing protocols | System | 1 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started | Validation Plan not present, Global CSV SOPs not applied., Traceability Matrix present, VR (called Qualifizierungsbericht, eng. Qualification report) not complete, URS document not identified, Configuration Specification not identified., Risk Assessment not present, IQ/OQ identified, however the level of detail is not consistent with DI expectations, i.e. Security/Integrity/Traceability verifications. Missing tests for documental checks (e.g. Users List, SOPs, etc.), functional checks (Part 11 and Annex 11 verifications), PQ not identified.
BRN | BRN-LAS_217 | BRN-LAS_217-VD1-2-9 | BRN-LAS_217-VD1-2-9-9.2-System | LAS_217 | 9.2 | Issue and approve the missing validation documentation | System | 2 | 3 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_217 | BRN-LAS_217-VD1-2-9 | BRN-LAS_217-VD1-2-9-9.3-System | LAS_217 | 9.3 | Perform and document the missing/incomplete tests | System | 3 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_217 | BRN-LAS_217-VD1-2-9 | BRN-LAS_217-VD1-2-9-9.4-System | LAS_217 | 9.4 | Assure the Traceability of the testing with coded requirements against coded test and update the documentation accordingly | System | 2 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_218 | BRN-LAS_218-S1-2-1 | BRN-LAS_218-S1-2-1-1.1-System | LAS_218 | 1.1 | Change Control Management including impact assessment | System | 0.5 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_218 | BRN-LAS_218-S1-2-1 | BRN-LAS_218-S1-2-1-1.2-System | LAS_218 | 1.2 | Create personal and unique accounts in system | System | 1 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_218 | BRN-LAS_218-S1-2-1 | BRN-LAS_218-S1-2-1-1.3-System | LAS_218 | 1.3 | Remove generic accounts from the system | System | 0.5 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_218 | BRN-LAS_218-S1-2-1 | BRN-LAS_218-S1-2-1-1.4-System | LAS_218 | 1.4 | Issue and approve an updated User List | System | 0.1 | 0.5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_218 | BRN-LAS_218-S1-2-1 | BRN-LAS_218-S1-2-1-1.5-System | LAS_218 | 1.5 | Update relevant SOPs and periodically review the User List according to procedure | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_218 | BRN-LAS_218-S2-3-2 | BRN-LAS_218-S2-3-2-2.1-System | LAS_218 | 2.1 | Change Control Management including impact assessment | System | 0.5 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_218 | BRN-LAS_218-S2-3-2 | BRN-LAS_218-S2-3-2-2.2-System | LAS_218 | 2.2 | Configure 3 user groups and define the role of each user | System | 1 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_218 | BRN-LAS_218-S2-3-2 | BRN-LAS_218-S2-3-2-2.3-System | LAS_218 | 2.3 | Configure user privileges according to a proper segregation of duties | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_218 | BRN-LAS_218-S2-3-2 | BRN-LAS_218-S2-3-2-2.4-System | LAS_218 | 2.4 | Test and document the configuration changes | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_218 | BRN-LAS_218-S2-3-2 | BRN-LAS_218-S2-3-2-2.5-System | LAS_218 | 2.5 | Update relevant SOP | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_218 | BRN-LAS_218-S3-4-3 | BRN-LAS_218-S3-4-3-3.1-Generic | LAS_218 | 3.1 | Issue and approve a Security SOP with proper PW security features according to best practices (length, complexity, expiring) | Generic | 1 | 5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_218 | BRN-LAS_218-S3-4-3 | BRN-LAS_218-S3-4-3-3.2-System | LAS_218 | 3.2 | Update all passwords according to the approved Security SOP | System | 1 | 0.1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_218 | BRN-LAS_218-S3-4-3 | BRN-LAS_218-S3-4-3-3.3-System | LAS_218 | 3.3 | Test and document the Password policies | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_218 | BRN-LAS_218-S4-3-4 | BRN-LAS_218-S4-3-4-4.1-System | LAS_218 | 4.1 | Issue a User List with the actual status of users | System | 0.1 | 0.5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_218 | BRN-LAS_218-S4-3-4 | BRN-LAS_218-S4-3-4-4.2-Generic | LAS_218 | 4.2 | Issue and approve a Periodic Review for User List | Generic | 0.1 | 0.5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_218 | BRN-LAS_218-S4-3-4 | BRN-LAS_218-S4-3-4-4.3-System | LAS_218 | 4.3 | Execute Periodic Review | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_218 | BRN-LAS_218-S4-3-4 | BRN-LAS_218-S4-3-4-4.4-System | LAS_218 | 4.4 | Setup of periodic task in relevant system | System | 0.2 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_218 | BRN-LAS_218-I3-2-5 | BRN-LAS_218-I3-2-5-5.1-System | LAS_218 | 5.1 | Change Control Management including impact assessment | System | 0.5 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_218 | BRN-LAS_218-I3-2-5 | BRN-LAS_218-I3-2-5-5.2-System | LAS_218 | 5.2 | Configure the protection of input data through an automatic security policy or folder restrictions | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_218 | BRN-LAS_218-I3-2-5 | BRN-LAS_218-I3-2-5-5.3-System | LAS_218 | 5.3 | Configure user privileges to prevent the deletion or alteration of input data | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_218 | BRN-LAS_218-I3-2-5 | BRN-LAS_218-I3-2-5-5.4-System | LAS_218 | 5.4 | Test and document the configuration changes | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_218 | BRN-LAS_218-I3-2-5 | BRN-LAS_218-I3-2-5-5.5-System | LAS_218 | 5.5 | Update relevant SOP | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_218 | BRN-LAS_218-T1-2-6 | BRN-LAS_218-T1-2-6-6.1-System | LAS_218 | 6.1 | Investigate with the supplier if it is possible to implement a proper configuration of the AT | System | 1 | 0 | NO | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_218 | BRN-LAS_218-T1-2-6 | BRN-LAS_218-T1-2-6-6.2-System | LAS_218 | 6.2 | Change Control Management including impact assessment | System | 0.5 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_218 | BRN-LAS_218-T1-2-6 | BRN-LAS_218-T1-2-6-6.3-System | LAS_218 | 6.3 | Configure Audit Trail functionality within the SW or, if not applicable, implement a paper based management for tracking relevant operation (i.e. old&new value, reason for change) to relevant data | System | 2 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_218 | BRN-LAS_218-T1-2-6 | BRN-LAS_218-T1-2-6-6.4-System | LAS_218 | 6.4 | Test and document configuration changes or the procedural changes | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_218 | BRN-LAS_218-T1-2-6 | BRN-LAS_218-T1-2-6-6.5-System | LAS_218 | 6.5 | Update relevant SOP | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_218 | BRN-LAS_218-T2-2-7 | BRN-LAS_218-T2-2-7-7.1-System | LAS_218 | 7.1 | Change Control Management including impact assessment | System | 0.5 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_218 | BRN-LAS_218-T2-2-7 | BRN-LAS_218-T2-2-7-7.2-System | LAS_218 | 7.2 | Verify if Time Reference protection can be configured within the system | System | 0.5 | 0.5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_218 | BRN-LAS_218-T2-2-7 | BRN-LAS_218-T2-2-7-7.3-Generic | LAS_218 | 7.3 | If not possible, manage Date & Time protection through an approved procedure | Generic | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_218 | BRN-LAS_218-T2-2-7 | BRN-LAS_218-T2-2-7-7.4-System | LAS_218 | 7.4 | Test and document configuration changes | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_218 | BRN-LAS_218-T2-2-7 | BRN-LAS_218-T2-2-7-7.5-System | LAS_218 | 7.5 | Update relevant SOP | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_218 | BRN-LAS_218-T3-3-8 | BRN-LAS_218-T3-3-8-8.1-Generic | LAS_218 | 8.1 | Issue and approve a fully compliant Audit Trail Review Working Instruction | Generic | 0.5 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_218 | BRN-LAS_218-T3-3-8 | BRN-LAS_218-T3-3-8-8.2-System | LAS_218 | 8.2 | Execute Audit Trail Review Working Instruction: - perform Data Assessment for Electronic Records managed by the system - update Operational Method SOP (Methods/Instrument) - update test documentation | System | 0.5 | 2.5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_218 | BRN-LAS_218-T3-3-8 | BRN-LAS_218-T3-3-8-8.3-System | LAS_218 | 8.3 | Setup of periodic task | System | 0.2 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_218 | BRN-LAS_218-VD1-2-9 | BRN-LAS_218-VD1-2-9-9.1-System | LAS_218 | 9.1 | Review the Computer System Validation in place and identify the missing/incomplete validation documents or testing protocols | System | 1 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started | Validation Plan not present, Global CSV SOPs not applied., Traceability Matrix present, VR (called Qualifizierungsbericht, eng. Qualification report) not complete, URS document not identified, Configuration Specification not identified., Risk Assessment not present, IQ/OQ identified, however the level of detail is not consistent with DI expectations, i.e. Security/Integrity/Traceability verifications. Missing tests for documental checks (e.g. Users List, SOPs, etc.), functional checks (Part 11 and Annex 11 verifications), PQ not identified.
BRN | BRN-LAS_218 | BRN-LAS_218-VD1-2-9 | BRN-LAS_218-VD1-2-9-9.2-System | LAS_218 | 9.2 | Issue and approve the missing validation documentation | System | 2 | 3 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_218 | BRN-LAS_218-VD1-2-9 | BRN-LAS_218-VD1-2-9-9.3-System | LAS_218 | 9.3 | Perform and document the missing/incomplete tests | System | 3 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_218 | BRN-LAS_218-VD1-2-9 | BRN-LAS_218-VD1-2-9-9.4-System | LAS_218 | 9.4 | Assure the Traceability of the testing with coded requirements against coded test and update the documentation accordingly | System | 2 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_223 | BRN-LAS_223-S1-2-1 | BRN-LAS_223-S1-2-1-1.1-System | LAS_223 | 1.1 | Change Control Management including impact assessment | System | 0.5 | 0 | YES | LES Supporting Systems | Valeria Geraci | Amit Krishna | 30/06/2026 | To be started
BRN | BRN-LAS_223 | BRN-LAS_223-S1-2-1 | BRN-LAS_223-S1-2-1-1.2-System | LAS_223 | 1.2 | Update system administration SOP to describe generic account's access mode and functionalities, and how to keep track of its actions | System | 1 | 2 | YES | LES Supporting Systems | Valeria Geraci | Amit Krishna | 30/06/2026 | To be started
BRN | BRN-LAS_223 | BRN-LAS_223-I1-1-2 | BRN-LAS_223-I1-1-2-2.1-System | LAS_223 | 2.1 | Change Control Management including impact assessment | System | 0.5 | 0 | YES | LES Supporting Systems | Valeria Geraci | Amit Krishna | 30/06/2026 | To be started
BRN | BRN-LAS_223 | BRN-LAS_223-I1-1-2 | BRN-LAS_223-I1-1-2-2.2-System | LAS_223 | 2.2 | Implement a process of automatic data backup | System | 1 | 2 | YES | LES Supporting Systems | Valeria Geraci | Amit Krishna | 30/06/2026 | To be started
BRN | BRN-LAS_223 | BRN-LAS_223-I1-1-2 | BRN-LAS_223-I1-1-2-2.3-Generic | LAS_223 | 2.3 | If automatic backup its not possible, document manual backups of system data with a proper frequency to be defined in a dedicated procedure | Generic | 1 | 2 | YES | LES Supporting Systems | Valeria Geraci | Amit Krishna | 30/06/2026 | To be started
BRN | BRN-LAS_223 | BRN-LAS_223-I1-1-2 | BRN-LAS_223-I1-1-2-2.4-System | LAS_223 | 2.4 | Test and document the implemented changes | System | 1 | 2 | YES | LES Supporting Systems | Valeria Geraci | Amit Krishna | 30/06/2026 | To be started
BRN | BRN-LAS_223 | BRN-LAS_223-I1-1-2 | BRN-LAS_223-I1-1-2-2.5-System | LAS_223 | 2.5 | Update relevant SOP | System | 0.2 | 0.2 | YES | LES Supporting Systems | Valeria Geraci | Amit Krishna | 30/06/2026 | To be started
BRN | BRN-LAS_223 | BRN-LAS_223-T3-2-3 | BRN-LAS_223-T3-2-3-3.1-Generic | LAS_223 | 3.1 | Issue and approve a fully compliant Audit Trail Review Working Instruction | Generic | 0.5 | 2 | YES | LES Supporting Systems | Valeria Geraci | Amit Krishna | 30/06/2026 | To be started
BRN | BRN-LAS_223 | BRN-LAS_223-T3-2-3 | BRN-LAS_223-T3-2-3-3.2-System | LAS_223 | 3.2 | Execute Audit Trail Review Working Instruction: - perform Data Assessment for Electronic Records managed by the system - update Operational Method SOP (Methods/Instrument) - update test documentation | System | 0.5 | 2.5 | YES | LES Supporting Systems | Valeria Geraci | Amit Krishna | 30/06/2026 | To be started
BRN | BRN-LAS_223 | BRN-LAS_223-T3-2-3 | BRN-LAS_223-T3-2-3-3.3-System | LAS_223 | 3.3 | Setup of periodic task | System | 0.2 | 0 | YES | LES Supporting Systems | Valeria Geraci | Amit Krishna | 30/06/2026 | To be started
BRN | BRN-LAS_223 | BRN-LAS_223-ES1-1-4 | BRN-LAS_223-ES1-1-4-4.1-System | LAS_223 | 4.1 | Issue and approve a procedure for the review of Electronic Signatures execution | System | 1 | 2 | YES | LES Supporting Systems | Valeria Geraci | Amit Krishna | 30/06/2026 | To be started
BRN | BRN-LAS_223 | BRN-LAS_223-ES1-1-4 | BRN-LAS_223-ES1-1-4-4.2-System | LAS_223 | 4.2 | Perform the ES review in order to check the failed attempts or suspicious patterns | System | 1 | 1 | YES | LES Supporting Systems | Valeria Geraci | Amit Krishna | 30/06/2026 | To be started
BRN | BRN-LAS_223 | BRN-LAS_223-ES1-1-4 | BRN-LAS_223-ES1-1-4-4.3-System | LAS_223 | 4.3 | Setup of periodic task | System | 0.2 | 0 | YES | LES Supporting Systems | Valeria Geraci | Amit Krishna | 30/06/2026 | To be started
BRN | BRN-LAS_223 | BRN-LAS_223-ES2-1-5 | BRN-LAS_223-ES2-1-5-5.1-System | LAS_223 | 5.1 | Issue and approve a procedure for the review of e-signed reports | System | 1 | 2 | YES | LES Supporting Systems | Valeria Geraci | Amit Krishna | 30/06/2026 | To be started
BRN | BRN-LAS_223 | BRN-LAS_223-ES2-1-5 | BRN-LAS_223-ES2-1-5-5.2-System | LAS_223 | 5.2 | Perform the ES review in order to check that all reports are properly signed | System | 1 | 1 | YES | LES Supporting Systems | Valeria Geraci | Amit Krishna | 30/06/2026 | To be started
BRN | BRN-LAS_223 | BRN-LAS_223-ES2-1-5 | BRN-LAS_223-ES2-1-5-5.3-System | LAS_223 | 5.3 | Setup of periodic task | System | 0.2 | 0 | YES | LES Supporting Systems | Valeria Geraci | Amit Krishna | 30/06/2026 | To be started
BRN | BRN-LAS_223 | BRN-LAS_223-ES3-1-6 | BRN-LAS_223-ES3-1-6-6.1-System | LAS_223 | 6.1 | Verify if reports are configured with all required ES components. If not, configure the report or implement a procedural control of the ES changes | System | 0.5 | 1 | YES | LES Supporting Systems | Valeria Geraci | Amit Krishna | 30/06/2026 | To be started
BRN | BRN-LAS_223 | BRN-LAS_223-ES3-1-6 | BRN-LAS_223-ES3-1-6-6.2-System | LAS_223 | 6.2 | Test and document configuration changes | System | 1 | 2 | YES | LES Supporting Systems | Valeria Geraci | Amit Krishna | 30/06/2026 | To be started
BRN | BRN-LAS_223 | BRN-LAS_223-VD1-1-7 | BRN-LAS_223-VD1-1-7-7.1-System | LAS_223 | 7.1 | Review the Computer System Validation in place and identify the missing/incomplete validation documents or testing protocols | System | 1 | 1 | YES | LES Supporting Systems | Valeria Geraci | Amit Krishna | 30/06/2026 | To be started | Information not found for each ER. This should be evaluated as part of LARA system and all ERs managed
BRN | BRN-LAS_223 | BRN-LAS_223-VD1-1-7 | BRN-LAS_223-VD1-1-7-7.2-System | LAS_223 | 7.2 | Issue and approve the missing validation documentation | System | 2 | 3 | YES | LES Supporting Systems | Valeria Geraci | Amit Krishna | 30/06/2026 | To be started
BRN | BRN-LAS_223 | BRN-LAS_223-VD1-1-7 | BRN-LAS_223-VD1-1-7-7.3-System | LAS_223 | 7.3 | Perform and document the missing/incomplete tests | System | 3 | 0 | YES | LES Supporting Systems | Valeria Geraci | Amit Krishna | 30/06/2026 | To be started
BRN | BRN-LAS_223 | BRN-LAS_223-VD1-1-7 | BRN-LAS_223-VD1-1-7-7.4-System | LAS_223 | 7.4 | Assure the Traceability of the testing with coded requirements against coded test and update the documentation accordingly | System | 2 | 2 | YES | LES Supporting Systems | Valeria Geraci | Amit Krishna | 30/06/2026 | To be started
BRN | BRN-LAS_283 | BRN-LAS_283-S3-5-1 | BRN-LAS_283-S3-5-1-1.1-System | LAS_283 | 1.1 | Investigate with the supplier if it is possible to upgrade the software to grant proper security features for user access | System | 1 | 0 | NO | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_283 | BRN-LAS_283-S3-5-1 | BRN-LAS_283-S3-5-1-1.2-Generic | LAS_283 | 1.2 | Define the Password features in an approved procedure | Generic | 1 | 3 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_283 | BRN-LAS_283-S3-5-1 | BRN-LAS_283-S3-5-1-1.3-System | LAS_283 | 1.3 | Personnel training to access the system | System | 0.5 | 0.5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_283 | BRN-LAS_283-S3-5-1 | BRN-LAS_283-S3-5-1-1.4-System | LAS_283 | 1.4 | Update relevant SOP | System | 0.2 | 0.2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_283 | BRN-LAS_283-S4-4-2 | BRN-LAS_283-S4-4-2-2.1-System | LAS_283 | 2.1 | Issue a User List with the actual status of users | System | 0.1 | 0.5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_283 | BRN-LAS_283-S4-4-2 | BRN-LAS_283-S4-4-2-2.2-Generic | LAS_283 | 2.2 | Issue and approve a Periodic Review for User List | Generic | 0.1 | 0.5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_283 | BRN-LAS_283-S4-4-2 | BRN-LAS_283-S4-4-2-2.3-System | LAS_283 | 2.3 | Execute Periodic Review | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_283 | BRN-LAS_283-S4-4-2 | BRN-LAS_283-S4-4-2-2.4-System | LAS_283 | 2.4 | Setup of periodic task in relevant system | System | 0.2 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_283 | BRN-LAS_283-I1-3-3 | BRN-LAS_283-I1-3-3-3.1-System | LAS_283 | 3.1 | Change Control Management including impact assessment | System | 0.5 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_283 | BRN-LAS_283-I1-3-3 | BRN-LAS_283-I1-3-3-3.2-System | LAS_283 | 3.2 | Implement a process of automatic data backup | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_283 | BRN-LAS_283-I1-3-3 | BRN-LAS_283-I1-3-3-3.3-Generic | LAS_283 | 3.3 | If automatic backup its not possible, document manual backups of system data with a proper frequency to be defined in a dedicated procedure | Generic | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_283 | BRN-LAS_283-I1-3-3 | BRN-LAS_283-I1-3-3-3.4-System | LAS_283 | 3.4 | Test and document the implemented changes | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_283 | BRN-LAS_283-I1-3-3 | BRN-LAS_283-I1-3-3-3.5-System | LAS_283 | 3.5 | Update relevant SOP | System | 0.2 | 0.2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_283 | BRN-LAS_283-I3-3-4 | BRN-LAS_283-I3-3-4-4.1-System | LAS_283 | 4.1 | Change Control Management including impact assessment | System | 0.5 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_283 | BRN-LAS_283-I3-3-4 | BRN-LAS_283-I3-3-4-4.2-System | LAS_283 | 4.2 | Configure the protection of input data through an automatic security policy or folder restrictions | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_283 | BRN-LAS_283-I3-3-4 | BRN-LAS_283-I3-3-4-4.3-System | LAS_283 | 4.3 | Configure user privileges to prevent the deletion or alteration of input data | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_283 | BRN-LAS_283-I3-3-4 | BRN-LAS_283-I3-3-4-4.4-System | LAS_283 | 4.4 | Test and document the configuration changes | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_283 | BRN-LAS_283-I3-3-4 | BRN-LAS_283-I3-3-4-4.5-System | LAS_283 | 4.5 | Update relevant SOP | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_283 | BRN-LAS_283-T1-3-5 | BRN-LAS_283-T1-3-5-5.1-System | LAS_283 | 5.1 | Investigate with the supplier if it is possible to implement a proper configuration of the AT | System | 1 | 0 | NO | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_283 | BRN-LAS_283-T1-3-5 | BRN-LAS_283-T1-3-5-5.2-System | LAS_283 | 5.2 | Change Control Management including impact assessment | System | 0.5 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_283 | BRN-LAS_283-T1-3-5 | BRN-LAS_283-T1-3-5-5.3-System | LAS_283 | 5.3 | Configure Audit Trail functionality within the SW or, if not applicable, implement a paper based management for tracking relevant operation (i.e. old&new value, reason for change) to relevant data | System | 2 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_283 | BRN-LAS_283-T1-3-5 | BRN-LAS_283-T1-3-5-5.4-System | LAS_283 | 5.4 | Test and document configuration changes or the procedural changes | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_283 | BRN-LAS_283-T1-3-5 | BRN-LAS_283-T1-3-5-5.5-System | LAS_283 | 5.5 | Update relevant SOP | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_283 | BRN-LAS_283-T2-3-6 | BRN-LAS_283-T2-3-6-6.1-System | LAS_283 | 6.1 | Change Control Management including impact assessment | System | 0.5 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_283 | BRN-LAS_283-T2-3-6 | BRN-LAS_283-T2-3-6-6.2-System | LAS_283 | 6.2 | Verify if Time Reference protection can be configured within the system | System | 0.5 | 0.5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_283 | BRN-LAS_283-T2-3-6 | BRN-LAS_283-T2-3-6-6.3-Generic | LAS_283 | 6.3 | If not possible, manage Date & Time protection through an approved procedure | Generic | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_283 | BRN-LAS_283-T2-3-6 | BRN-LAS_283-T2-3-6-6.4-System | LAS_283 | 6.4 | Test and document configuration changes | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_283 | BRN-LAS_283-T2-3-6 | BRN-LAS_283-T2-3-6-6.5-System | LAS_283 | 6.5 | Update relevant SOP | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_283 | BRN-LAS_283-T3-4-7 | BRN-LAS_283-T3-4-7-7.1-Generic | LAS_283 | 7.1 | Issue and approve a fully compliant Audit Trail Review Working Instruction | Generic | 0.5 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_283 | BRN-LAS_283-T3-4-7 | BRN-LAS_283-T3-4-7-7.2-System | LAS_283 | 7.2 | Execute Audit Trail Review Working Instruction: - perform Data Assessment for Electronic Records managed by the system - update Operational Method SOP (Methods/Instrument) - update test documentation | System | 0.5 | 2.5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_283 | BRN-LAS_283-T3-4-7 | BRN-LAS_283-T3-4-7-7.3-System | LAS_283 | 7.3 | Setup of periodic task | System | 0.2 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_283 | BRN-LAS_283-VD1-3-8 | BRN-LAS_283-VD1-3-8-8.1-System | LAS_283 | 8.1 | Review the Computer System Validation in place and identify the missing/incomplete validation documents or testing protocols | System | 1 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started | Validation Plan has been identified, however it has been issued by the vendor and it is not covering the validation strategy regarding the Regulatory and ERES definition, Global CSV SOPs not applied., Traceability Matrix present, VR (called Qualifizierungsbericht, eng. Qualification report) not complete., URS document present but it is missing Functional Process Requirements, Access Control and Security Roles partially covered, no reference to regulatory rules (e.g. Annex11 coverage), Not present, partially covered in delivered vendor documentation, RA is identified but does not cover the risk associated to Regulatory Requirements and ERES definition., IQ/OQ has been identified, but the level of detail is not consistent with DI expectations, i.e. Security/Integrity/Traceability verifications. Missing tests for documental checks (e.g. Users List, SOPs, etc.), functional checks (Part 11 and Annex 11 verifications), PQ protocol is not identified
BRN | BRN-LAS_283 | BRN-LAS_283-VD1-3-8 | BRN-LAS_283-VD1-3-8-8.2-System | LAS_283 | 8.2 | Issue and approve the missing validation documentation | System | 2 | 3 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_283 | BRN-LAS_283-VD1-3-8 | BRN-LAS_283-VD1-3-8-8.3-System | LAS_283 | 8.3 | Perform and document the missing/incomplete tests | System | 3 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_283 | BRN-LAS_283-VD1-3-8 | BRN-LAS_283-VD1-3-8-8.4-System | LAS_283 | 8.4 | Assure the Traceability of the testing with coded requirements against coded test and update the documentation accordingly | System | 2 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_293 | BRN-LAS_293-S3-4-1 | BRN-LAS_293-S3-4-1-1.1-System | LAS_293 | 1.1 | Investigate with the supplier if it is possible to upgrade the software to grant proper security features for user access | System | 1 | 0 | NO | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_293 | BRN-LAS_293-S3-4-1 | BRN-LAS_293-S3-4-1-1.2-Generic | LAS_293 | 1.2 | Define the Password features in an approved procedure | Generic | 1 | 3 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_293 | BRN-LAS_293-S3-4-1 | BRN-LAS_293-S3-4-1-1.3-System | LAS_293 | 1.3 | Personnel training to access the system | System | 0.5 | 0.5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_293 | BRN-LAS_293-S3-4-1 | BRN-LAS_293-S3-4-1-1.4-System | LAS_293 | 1.4 | Update relevant SOP | System | 0.2 | 0.2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_293 | BRN-LAS_293-S4-3-2 | BRN-LAS_293-S4-3-2-2.1-System | LAS_293 | 2.1 | Issue a User List with the actual status of users | System | 0.1 | 0.5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_293 | BRN-LAS_293-S4-3-2 | BRN-LAS_293-S4-3-2-2.2-Generic | LAS_293 | 2.2 | Issue and approve a Periodic Review for User List | Generic | 0.1 | 0.5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_293 | BRN-LAS_293-S4-3-2 | BRN-LAS_293-S4-3-2-2.3-System | LAS_293 | 2.3 | Execute Periodic Review | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_293 | BRN-LAS_293-S4-3-2 | BRN-LAS_293-S4-3-2-2.4-System | LAS_293 | 2.4 | Setup of periodic task in relevant system | System | 0.2 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_293 | BRN-LAS_293-I1-2-3 | BRN-LAS_293-I1-2-3-3.1-Generic | LAS_293 | 3.1 | Verify if an automatic backup is applicable. If not, verify that the modality and frequency of the backups are defined in an official document with a risk-based approach | Generic | 1 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_293 | BRN-LAS_293-I1-2-3 | BRN-LAS_293-I1-2-3-3.2-System | LAS_293 | 3.2 | If not, execute the risk analyses and reconfigure the backup | System | 0.1 | 0.5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_293 | BRN-LAS_293-I1-2-3 | BRN-LAS_293-I1-2-3-3.3-System | LAS_293 | 3.3 | Test and document the configuration changes | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_293 | BRN-LAS_293-I1-2-3 | BRN-LAS_293-I1-2-3-3.4-System | LAS_293 | 3.4 | Update relevant SOP | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_293 | BRN-LAS_293-I2-2-4 | BRN-LAS_293-I2-2-4-4.1-System | LAS_293 | 4.1 | Change Control Management including impact assessment | System | 0.5 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_293 | BRN-LAS_293-I2-2-4 | BRN-LAS_293-I2-2-4-4.2-System | LAS_293 | 4.2 | Change permissions for users not authorized to modify data, preventing the deletion or alteration. | System | 0.5 | 0 | NO | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_293 | BRN-LAS_293-I2-2-4 | BRN-LAS_293-I2-2-4-4.3-System | LAS_293 | 4.3 | Test and document the configuration changes | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_293 | BRN-LAS_293-I2-2-4 | BRN-LAS_293-I2-2-4-4.4-System | LAS_293 | 4.4 | Update relevant SOP | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_293 | BRN-LAS_293-I3-2-5 | BRN-LAS_293-I3-2-5-5.1-System | LAS_293 | 5.1 | Change Control Management including impact assessment | System | 0.5 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_293 | BRN-LAS_293-I3-2-5 | BRN-LAS_293-I3-2-5-5.2-System | LAS_293 | 5.2 | Configure the protection of input data through an automatic security policy or folder restrictions | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_293 | BRN-LAS_293-I3-2-5 | BRN-LAS_293-I3-2-5-5.3-System | LAS_293 | 5.3 | Configure user privileges to prevent the deletion or alteration of input data | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_293 | BRN-LAS_293-I3-2-5 | BRN-LAS_293-I3-2-5-5.4-System | LAS_293 | 5.4 | Test and document the configuration changes | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_293 | BRN-LAS_293-I3-2-5 | BRN-LAS_293-I3-2-5-5.5-System | LAS_293 | 5.5 | Update relevant SOP | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_293 | BRN-LAS_293-T2-2-6 | BRN-LAS_293-T2-2-6-6.1-System | LAS_293 | 6.1 | Change Control Management including impact assessment | System | 0.5 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_293 | BRN-LAS_293-T2-2-6 | BRN-LAS_293-T2-2-6-6.2-System | LAS_293 | 6.2 | Verify if Time Reference protection can be configured within the system | System | 0.5 | 0.5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_293 | BRN-LAS_293-T2-2-6 | BRN-LAS_293-T2-2-6-6.3-Generic | LAS_293 | 6.3 | If not possible, manage Date & Time protection through an approved procedure | Generic | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_293 | BRN-LAS_293-T2-2-6 | BRN-LAS_293-T2-2-6-6.4-System | LAS_293 | 6.4 | Test and document configuration changes | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_293 | BRN-LAS_293-T2-2-6 | BRN-LAS_293-T2-2-6-6.5-System | LAS_293 | 6.5 | Update relevant SOP | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_293 | BRN-LAS_293-T3-3-7 | BRN-LAS_293-T3-3-7-7.1-Generic | LAS_293 | 7.1 | Issue and approve a fully compliant Audit Trail Review Working Instruction | Generic | 0.5 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_293 | BRN-LAS_293-T3-3-7 | BRN-LAS_293-T3-3-7-7.2-System | LAS_293 | 7.2 | Execute Audit Trail Review Working Instruction: - perform Data Assessment for Electronic Records managed by the system - update Operational Method SOP (Methods/Instrument) - update test documentation | System | 0.5 | 2.5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_293 | BRN-LAS_293-T3-3-7 | BRN-LAS_293-T3-3-7-7.3-System | LAS_293 | 7.3 | Setup of periodic task | System | 0.2 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_293 | BRN-LAS_293-VD1-2-8 | BRN-LAS_293-VD1-2-8-8.1-System | LAS_293 | 8.1 | Review the Computer System Validation in place and identify the missing/incomplete validation documents or testing protocols | System | 1 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started | Validation Plan not present, Global CSV SOPs not applied., Traceability Matrix is not present, VR (called Qualifizierungsbericht, eng. Qualification report) not complete, URS document present but it is missing Functional Process Requirements, Access Control and Security Roles partially covered, no reference to regulatory rules (e.g. Annex11 coverage), Not present, partially covered in delivered vendor documentation, Risk Assessment not present, Testing only for IQ/OQ for the Control System. The level of detail is not consistent with DI expectations, i.e. Security/Integrity/Traceability verifications. Missing tests for documental checks (e.g. Users List, SOPs, etc.), functional checks (Part 11 and Annex 11 verifications), PQ not identified.
BRN | BRN-LAS_293 | BRN-LAS_293-VD1-2-8 | BRN-LAS_293-VD1-2-8-8.2-System | LAS_293 | 8.2 | Issue and approve the missing validation documentation | System | 2 | 3 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_293 | BRN-LAS_293-VD1-2-8 | BRN-LAS_293-VD1-2-8-8.3-System | LAS_293 | 8.3 | Perform and document the missing/incomplete tests | System | 3 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_293 | BRN-LAS_293-VD1-2-8 | BRN-LAS_293-VD1-2-8-8.4-System | LAS_293 | 8.4 | Assure the Traceability of the testing with coded requirements against coded test and update the documentation accordingly | System | 2 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_294 | BRN-LAS_294-S3-4-1 | BRN-LAS_294-S3-4-1-1.1-System | LAS_294 | 1.1 | Investigate with the supplier if it is possible to upgrade the software to grant proper security features for user access | System | 1 | 0 | NO | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_294 | BRN-LAS_294-S3-4-1 | BRN-LAS_294-S3-4-1-1.2-Generic | LAS_294 | 1.2 | Define the Password features in an approved procedure | Generic | 1 | 3 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_294 | BRN-LAS_294-S3-4-1 | BRN-LAS_294-S3-4-1-1.3-System | LAS_294 | 1.3 | Personnel training to access the system | System | 0.5 | 0.5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_294 | BRN-LAS_294-S3-4-1 | BRN-LAS_294-S3-4-1-1.4-System | LAS_294 | 1.4 | Update relevant SOP | System | 0.2 | 0.2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_294 | BRN-LAS_294-S4-3-2 | BRN-LAS_294-S4-3-2-2.1-System | LAS_294 | 2.1 | Issue a User List with the actual status of users | System | 0.1 | 0.5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_294 | BRN-LAS_294-S4-3-2 | BRN-LAS_294-S4-3-2-2.2-Generic | LAS_294 | 2.2 | Issue and approve a Periodic Review for User List | Generic | 0.1 | 0.5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_294 | BRN-LAS_294-S4-3-2 | BRN-LAS_294-S4-3-2-2.3-System | LAS_294 | 2.3 | Execute Periodic Review | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_294 | BRN-LAS_294-S4-3-2 | BRN-LAS_294-S4-3-2-2.4-System | LAS_294 | 2.4 | Setup of periodic task in relevant system | System | 0.2 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_294 | BRN-LAS_294-I1-2-3 | BRN-LAS_294-I1-2-3-3.1-Generic | LAS_294 | 3.1 | Verify if modality and frequency of the backups are defined in an official document with a risk-based approach | Generic | 1 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_294 | BRN-LAS_294-I1-2-3 | BRN-LAS_294-I1-2-3-3.2-System | LAS_294 | 3.2 | If not, execute the risk analyses and reconfigure the backup | System | 0.1 | 0.5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_294 | BRN-LAS_294-I1-2-3 | BRN-LAS_294-I1-2-3-3.3-System | LAS_294 | 3.3 | Test and document the configuration changes | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_294 | BRN-LAS_294-I1-2-3 | BRN-LAS_294-I1-2-3-3.4-System | LAS_294 | 3.4 | Update relevant SOP | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_294 | BRN-LAS_294-I2-2-4 | BRN-LAS_294-I2-2-4-4.1-System | LAS_294 | 4.1 | Change Control Management including impact assessment | System | 0.5 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_294 | BRN-LAS_294-I2-2-4 | BRN-LAS_294-I2-2-4-4.2-System | LAS_294 | 4.2 | Change permissions for users not authorized to modify data, preventing the deletion or alteration. | System | 0.5 | 0 | NO | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_294 | BRN-LAS_294-I2-2-4 | BRN-LAS_294-I2-2-4-4.3-System | LAS_294 | 4.3 | Test and document the configuration changes | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_294 | BRN-LAS_294-I2-2-4 | BRN-LAS_294-I2-2-4-4.4-System | LAS_294 | 4.4 | Update relevant SOP | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_294 | BRN-LAS_294-I3-2-5 | BRN-LAS_294-I3-2-5-5.1-System | LAS_294 | 5.1 | Change Control Management including impact assessment | System | 0.5 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_294 | BRN-LAS_294-I3-2-5 | BRN-LAS_294-I3-2-5-5.2-System | LAS_294 | 5.2 | Configure the protection of input data through an automatic security policy or folder restrictions | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_294 | BRN-LAS_294-I3-2-5 | BRN-LAS_294-I3-2-5-5.3-System | LAS_294 | 5.3 | Configure user privileges to prevent the deletion or alteration of input data | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_294 | BRN-LAS_294-I3-2-5 | BRN-LAS_294-I3-2-5-5.4-System | LAS_294 | 5.4 | Test and document the configuration changes | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_294 | BRN-LAS_294-I3-2-5 | BRN-LAS_294-I3-2-5-5.5-System | LAS_294 | 5.5 | Update relevant SOP | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_294 | BRN-LAS_294-T2-2-6 | BRN-LAS_294-T2-2-6-6.1-System | LAS_294 | 6.1 | Change Control Management including impact assessment | System | 0.5 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_294 | BRN-LAS_294-T2-2-6 | BRN-LAS_294-T2-2-6-6.2-System | LAS_294 | 6.2 | Verify if Time Reference protection can be configured within the system | System | 0.5 | 0.5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_294 | BRN-LAS_294-T2-2-6 | BRN-LAS_294-T2-2-6-6.3-Generic | LAS_294 | 6.3 | If not possible, manage Date & Time protection through an approved procedure | Generic | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_294 | BRN-LAS_294-T2-2-6 | BRN-LAS_294-T2-2-6-6.4-System | LAS_294 | 6.4 | Test and document configuration changes | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_294 | BRN-LAS_294-T2-2-6 | BRN-LAS_294-T2-2-6-6.5-System | LAS_294 | 6.5 | Update relevant SOP | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_294 | BRN-LAS_294-T3-3-7 | BRN-LAS_294-T3-3-7-7.1-Generic | LAS_294 | 7.1 | Issue and approve a fully compliant Audit Trail Review Working Instruction | Generic | 0.5 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_294 | BRN-LAS_294-T3-3-7 | BRN-LAS_294-T3-3-7-7.2-System | LAS_294 | 7.2 | Execute Audit Trail Review Working Instruction: - perform Data Assessment for Electronic Records managed by the system - update Operational Method SOP (Methods/Instrument) - update test documentation | System | 0.5 | 2.5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_294 | BRN-LAS_294-T3-3-7 | BRN-LAS_294-T3-3-7-7.3-System | LAS_294 | 7.3 | Setup of periodic task | System | 0.2 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_294 | BRN-LAS_294-VD1-2-8 | BRN-LAS_294-VD1-2-8-8.1-System | LAS_294 | 8.1 | Review the Computer System Validation in place and identify the missing/incomplete validation documents or testing protocols | System | 1 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started | Validation Plan not present, Global CSV SOPs not applied., VR (called Qualifizierungsbericht, eng. Qualification report) not complete, URS document present but it is missing Functional Process Requirements, Access Control and Security Roles partially covered, no reference to regulatory rules (e.g. Annex11 coverage), Not present, partially covered in delivered vendor documentation, Risk Assessment not present, Testing only for IQ/OQ for the Control System. The level of detail is not consistent with DI expectations, i.e. Security/Integrity/Traceability verifications. Missing tests for documental checks (e.g. Users List, SOPs, etc.), functional checks (Part 11 and Annex 11 verifications), PQ not identified.
BRN | BRN-LAS_294 | BRN-LAS_294-VD1-2-8 | BRN-LAS_294-VD1-2-8-8.2-System | LAS_294 | 8.2 | Issue and approve the missing validation documentation | System | 2 | 3 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_294 | BRN-LAS_294-VD1-2-8 | BRN-LAS_294-VD1-2-8-8.3-System | LAS_294 | 8.3 | Perform and document the missing/incomplete tests | System | 3 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_294 | BRN-LAS_294-VD1-2-8 | BRN-LAS_294-VD1-2-8-8.4-System | LAS_294 | 8.4 | Assure the Traceability of the testing with coded requirements against coded test and update the documentation accordingly | System | 2 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_299 | BRN-LAS_299-S1-1-1 | BRN-LAS_299-S1-1-1-1.1-System | LAS_299 | 1.1 | Change Control Management including impact assessment | System | 0.5 | 0 | YES | LES Supporting Systems | Valeria Geraci | Amit Krishna | 31/12/2026 | To be started
BRN | BRN-LAS_299 | BRN-LAS_299-S1-1-1 | BRN-LAS_299-S1-1-1-1.2-System | LAS_299 | 1.2 | Update the application SW in order to configure unique and personal accounts. If it is not possible to configure personal account within application SW, implement a proper user management within OS accounts | System | 3 | 3 | YES | LES Supporting Systems | Valeria Geraci | Amit Krishna | 31/12/2026 | To be started
BRN | BRN-LAS_299 | BRN-LAS_299-S1-1-1 | BRN-LAS_299-S1-1-1-1.3-System | LAS_299 | 1.3 | Test and document the configuration changes or procedural changes | System | 1 | 2 | YES | LES Supporting Systems | Valeria Geraci | Amit Krishna | 31/12/2026 | To be started
BRN | BRN-LAS_299 | BRN-LAS_299-S1-1-1 | BRN-LAS_299-S1-1-1-1.4-System | LAS_299 | 1.4 | Issue and approve a User List | System | 0.1 | 0.5 | YES | LES Supporting Systems | Valeria Geraci | Amit Krishna | 31/12/2026 | To be started
BRN | BRN-LAS_299 | BRN-LAS_299-S1-1-1 | BRN-LAS_299-S1-1-1-1.5-System | LAS_299 | 1.5 | Update relevant SOPs and periodically review the User List according to procedure | System | 1 | 2 | YES | LES Supporting Systems | Valeria Geraci | Amit Krishna | 31/12/2026 | To be started
BRN | BRN-LAS_299 | BRN-LAS_299-S2-2-2 | BRN-LAS_299-S2-2-2-2.1-System | LAS_299 | 2.1 | Define the User Groups and the related privileges in an approved procedure | System | 2 | 3 | YES | LES Supporting Systems | Valeria Geraci | Amit Krishna | 31/12/2026 | To be started
BRN | BRN-LAS_299 | BRN-LAS_299-S2-2-2 | BRN-LAS_299-S2-2-2-2.2-System | LAS_299 | 2.2 | Configure 3 user groups and define the role of each user | System | 1 | 1 | YES | LES Supporting Systems | Valeria Geraci | Amit Krishna | 31/12/2026 | To be started
BRN | BRN-LAS_299 | BRN-LAS_299-S2-2-2 | BRN-LAS_299-S2-2-2-2.3-System | LAS_299 | 2.3 | Configure user privileges according to a proper segregation of duties | System | 1 | 2 | YES | LES Supporting Systems | Valeria Geraci | Amit Krishna | 31/12/2026 | To be started
BRN | BRN-LAS_299 | BRN-LAS_299-S2-2-2 | BRN-LAS_299-S2-2-2-2.4-System | LAS_299 | 2.4 | Test and document the configuration changes | System | 1 | 2 | YES | LES Supporting Systems | Valeria Geraci | Amit Krishna | 31/12/2026 | To be started
BRN | BRN-LAS_299 | BRN-LAS_299-S2-2-2 | BRN-LAS_299-S2-2-2-2.5-System | LAS_299 | 2.5 | Update relevant SOP | System | 1 | 2 | YES | LES Supporting Systems | Valeria Geraci | Amit Krishna | 31/12/2026 | To be started
BRN | BRN-LAS_299 | BRN-LAS_299-S3-3-3 | BRN-LAS_299-S3-3-3-3.1-Generic | LAS_299 | 3.1 | Issue and approve a Security SOP with proper PW security features according to best practices (length, complexity, expiring) | Generic | 1 | 5 | YES | LES Supporting Systems | Valeria Geraci | Amit Krishna | 31/12/2026 | To be started
BRN | BRN-LAS_299 | BRN-LAS_299-S3-3-3 | BRN-LAS_299-S3-3-3-3.2-System | LAS_299 | 3.2 | Update all passwords according to the approved Security SOP | System | 1 | 0.1 | YES | LES Supporting Systems | Valeria Geraci | Amit Krishna | 31/12/2026 | To be started
BRN | BRN-LAS_299 | BRN-LAS_299-S3-3-3 | BRN-LAS_299-S3-3-3-3.3-System | LAS_299 | 3.3 | Test and document the Password policies | System | 0.5 | 1 | YES | LES Supporting Systems | Valeria Geraci | Amit Krishna | 31/12/2026 | To be started
BRN | BRN-LAS_299 | BRN-LAS_299-S4-2-4 | BRN-LAS_299-S4-2-4-4.1-System | LAS_299 | 4.1 | Issue a User List with the actual status of users | System | 0.1 | 0.5 | YES | LES Supporting Systems | Valeria Geraci | Amit Krishna | 31/12/2026 | To be started
BRN | BRN-LAS_299 | BRN-LAS_299-S4-2-4 | BRN-LAS_299-S4-2-4-4.2-Generic | LAS_299 | 4.2 | Issue and approve a Periodic Review for User List | Generic | 0.1 | 0.5 | YES | LES Supporting Systems | Valeria Geraci | Amit Krishna | 31/12/2026 | To be started
BRN | BRN-LAS_299 | BRN-LAS_299-S4-2-4 | BRN-LAS_299-S4-2-4-4.3-System | LAS_299 | 4.3 | Execute Periodic Review | System | 1 | 2 | YES | LES Supporting Systems | Valeria Geraci | Amit Krishna | 31/12/2026 | To be started
BRN | BRN-LAS_299 | BRN-LAS_299-S4-2-4 | BRN-LAS_299-S4-2-4-4.4-System | LAS_299 | 4.4 | Setup of periodic task in relevant system | System | 0.2 | 0 | YES | LES Supporting Systems | Valeria Geraci | Amit Krishna | 31/12/2026 | To be started
BRN | BRN-LAS_299 | BRN-LAS_299-I1-1-5 | BRN-LAS_299-I1-1-5-5.1-System | LAS_299 | 5.1 | Change Control Management including impact assessment | System | 0.5 | 0 | YES | LES Supporting Systems | Valeria Geraci | Amit Krishna | 31/12/2026 | To be started
BRN | BRN-LAS_299 | BRN-LAS_299-I1-1-5 | BRN-LAS_299-I1-1-5-5.2-System | LAS_299 | 5.2 | Implement a process of automatic data backup | System | 1 | 2 | YES | LES Supporting Systems | Valeria Geraci | Amit Krishna | 31/12/2026 | To be started
BRN | BRN-LAS_299 | BRN-LAS_299-I1-1-5 | BRN-LAS_299-I1-1-5-5.3-Generic | LAS_299 | 5.3 | If automatic backup its not possible, document manual backups of system data with a proper frequency to be defined in a dedicated procedure | Generic | 1 | 2 | YES | LES Supporting Systems | Valeria Geraci | Amit Krishna | 31/12/2026 | To be started
BRN | BRN-LAS_299 | BRN-LAS_299-I1-1-5 | BRN-LAS_299-I1-1-5-5.4-System | LAS_299 | 5.4 | Test and document the implemented changes | System | 1 | 2 | YES | LES Supporting Systems | Valeria Geraci | Amit Krishna | 31/12/2026 | To be started
BRN | BRN-LAS_299 | BRN-LAS_299-I1-1-5 | BRN-LAS_299-I1-1-5-5.5-System | LAS_299 | 5.5 | Update relevant SOP | System | 0.2 | 0.2 | YES | LES Supporting Systems | Valeria Geraci | Amit Krishna | 31/12/2026 | To be started
BRN | BRN-LAS_299 | BRN-LAS_299-T1-1-6 | BRN-LAS_299-T1-1-6-6.1-System | LAS_299 | 6.1 | Change Control Management including impact assessment | System | 0.5 | 0 | YES | LES Supporting Systems | Valeria Geraci | Amit Krishna | 31/12/2026 | To be started
BRN | BRN-LAS_299 | BRN-LAS_299-T1-1-6 | BRN-LAS_299-T1-1-6-6.2-System | LAS_299 | 6.2 | Update Audit Trail functionality in order to track and record modifications to ER | System | 1 | 2 | YES | LES Supporting Systems | Valeria Geraci | Amit Krishna | 31/12/2026 | To be started
BRN | BRN-LAS_299 | BRN-LAS_299-T1-1-6 | BRN-LAS_299-T1-1-6-6.3-Generic | LAS_299 | 6.3 | If Audit Trail is not compliant (e.g. does not track modifications to ER), implement a paper based management of system regulated input records (i.e. methods) with the following paper procedures: -user access log -verification log to be used by the Users before launching a method -traceability log to be used by the system administrators when changing a method | Generic | 2 | 3 | YES | LES Supporting Systems | Valeria Geraci | Amit Krishna | 31/12/2026 | To be started
BRN | BRN-LAS_299 | BRN-LAS_299-T1-1-6 | BRN-LAS_299-T1-1-6-6.4-System | LAS_299 | 6.4 | Test and document that Audit Trail is fully compliant or, in case of paper Audit Trail, that the personnel is trained to use it | System | 0.5 | 1 | YES | LES Supporting Systems | Valeria Geraci | Amit Krishna | 31/12/2026 | To be started
BRN | BRN-LAS_299 | BRN-LAS_299-T1-1-6 | BRN-LAS_299-T1-1-6-6.5-System | LAS_299 | 6.5 | Update relevant SOP | System | 0.5 | 1 | YES | LES Supporting Systems | Valeria Geraci | Amit Krishna | 31/12/2026 | To be started
BRN | BRN-LAS_299 | BRN-LAS_299-T3-2-7 | BRN-LAS_299-T3-2-7-7.1-Generic | LAS_299 | 7.1 | If there is no Audit Trail Process fully compliant, issue and approve a fully compliant Audit Trail Review Working Instruction | Generic | 1 | 3 | YES | LES Supporting Systems | Valeria Geraci | Amit Krishna | 31/12/2026 | To be started
BRN | BRN-LAS_299 | BRN-LAS_299-T3-2-7 | BRN-LAS_299-T3-2-7-7.2-System | LAS_299 | 7.2 | Execute Audit Trail Review Working Instruction: - perform Data Assessment for Electronic Records managed by the system - update Operational Method SOP (Methods/Instrument) - update test documentation | System | 0.5 | 2.5 | YES | LES Supporting Systems | Valeria Geraci | Amit Krishna | 31/12/2026 | To be started
BRN | BRN-LAS_299 | BRN-LAS_299-T3-2-7 | BRN-LAS_299-T3-2-7-7.3-System | LAS_299 | 7.3 | Setup of periodic task | System | 0.2 | 0 | YES | LES Supporting Systems | Valeria Geraci | Amit Krishna | 31/12/2026 | To be started
BRN | BRN-LAS_299 | BRN-LAS_299-VD1-1-8 | BRN-LAS_299-VD1-1-8-8.1-System | LAS_299 | 8.1 | Review the Computer System Validation in place and identify the missing/incomplete validation documents or testing protocols | System | 1 | 1 | YES | LES Supporting Systems | Valeria Geraci | Amit Krishna | 31/12/2026 | To be started | Validation Plan not present, Global CSV SOPs not applied., VR (called Qualifizierungsbericht, eng. Qualification report) not complete, URS document present but it is missing Functional Process Requirements, Access Control and Security Roles partially covered, no reference to regulatory rules (e.g. Annex11 coverage), Not present, partially covered in delivered vendor documentation, Risk Assessment not present, Testing only for IQ/OQ for the Control System. The level of detail is not consistent with DI expectations, i.e. Security/Integrity/Traceability verifications. Missing tests for documental checks (e.g. Users List, SOPs, etc.), functional checks (Part 11 and Annex 11 verifications), PQ not identified.
BRN | BRN-LAS_299 | BRN-LAS_299-VD1-1-8 | BRN-LAS_299-VD1-1-8-8.2-System | LAS_299 | 8.2 | Issue and approve the missing validation documentation | System | 2 | 3 | YES | LES Supporting Systems | Valeria Geraci | Amit Krishna | 31/12/2026 | To be started
BRN | BRN-LAS_299 | BRN-LAS_299-VD1-1-8 | BRN-LAS_299-VD1-1-8-8.3-System | LAS_299 | 8.3 | Perform and document the missing/incomplete tests | System | 3 | 0 | YES | LES Supporting Systems | Valeria Geraci | Amit Krishna | 31/12/2026 | To be started
BRN | BRN-LAS_299 | BRN-LAS_299-VD1-1-8 | BRN-LAS_299-VD1-1-8-8.4-System | LAS_299 | 8.4 | Assure the Traceability of the testing with coded requirements against coded test and update the documentation accordingly | System | 2 | 2 | YES | LES Supporting Systems | Valeria Geraci | Amit Krishna | 31/12/2026 | To be started
BRN | BRN-LAS_302 | BRN-LAS_302-S1-1-1 | BRN-LAS_302-S1-1-1-1.1-System | LAS_302 | 1.1 | Change Control Management including impact assessment | System | 0.5 | 0 | YES | LES Supporting Systems | Valeria Geraci | Amit Krishna | 31/12/2026 | To be started
BRN | BRN-LAS_302 | BRN-LAS_302-S1-1-1 | BRN-LAS_302-S1-1-1-1.2-System | LAS_302 | 1.2 | Create personal and unique accounts in system | System | 1 | 0 | YES | LES Supporting Systems | Valeria Geraci | Amit Krishna | 31/12/2026 | To be started
BRN | BRN-LAS_302 | BRN-LAS_302-S1-1-1 | BRN-LAS_302-S1-1-1-1.3-System | LAS_302 | 1.3 | Remove generic accounts from the system | System | 0.5 | 0 | YES | LES Supporting Systems | Valeria Geraci | Amit Krishna | 31/12/2026 | To be started
BRN | BRN-LAS_302 | BRN-LAS_302-S1-1-1 | BRN-LAS_302-S1-1-1-1.4-System | LAS_302 | 1.4 | Issue and approve an updated User List | System | 0.1 | 0.5 | YES | LES Supporting Systems | Valeria Geraci | Amit Krishna | 31/12/2026 | To be started
BRN | BRN-LAS_302 | BRN-LAS_302-S1-1-1 | BRN-LAS_302-S1-1-1-1.5-System | LAS_302 | 1.5 | Update relevant SOPs and periodically review the User List according to procedure | System | 1 | 2 | YES | LES Supporting Systems | Valeria Geraci | Amit Krishna | 31/12/2026 | To be started
BRN | BRN-LAS_302 | BRN-LAS_302-S2-2-2 | BRN-LAS_302-S2-2-2-2.1-System | LAS_302 | 2.1 | Change Control Management including impact assessment | System | 0.5 | 0 | YES | LES Supporting Systems | Valeria Geraci | Amit Krishna | 31/12/2026 | To be started
BRN | BRN-LAS_302 | BRN-LAS_302-S2-2-2 | BRN-LAS_302-S2-2-2-2.2-System | LAS_302 | 2.2 | Configure 3 user groups and define the role of each user | System | 1 | 1 | YES | LES Supporting Systems | Valeria Geraci | Amit Krishna | 31/12/2026 | To be started
BRN | BRN-LAS_302 | BRN-LAS_302-S2-2-2 | BRN-LAS_302-S2-2-2-2.3-System | LAS_302 | 2.3 | Configure user privileges according to a proper segregation of duties | System | 1 | 2 | YES | LES Supporting Systems | Valeria Geraci | Amit Krishna | 31/12/2026 | To be started
BRN | BRN-LAS_302 | BRN-LAS_302-S2-2-2 | BRN-LAS_302-S2-2-2-2.4-System | LAS_302 | 2.4 | Test and document the configuration changes | System | 1 | 2 | YES | LES Supporting Systems | Valeria Geraci | Amit Krishna | 31/12/2026 | To be started
BRN | BRN-LAS_302 | BRN-LAS_302-S2-2-2 | BRN-LAS_302-S2-2-2-2.5-System | LAS_302 | 2.5 | Update relevant SOP | System | 1 | 2 | YES | LES Supporting Systems | Valeria Geraci | Amit Krishna | 31/12/2026 | To be started
BRN | BRN-LAS_302 | BRN-LAS_302-S3-3-3 | BRN-LAS_302-S3-3-3-3.1-Generic | LAS_302 | 3.1 | Issue and approve a Security SOP with proper PW security features according to best practices (length, complexity, expiring) | Generic | 1 | 5 | YES | LES Supporting Systems | Valeria Geraci | Amit Krishna | 31/12/2026 | To be started
BRN | BRN-LAS_302 | BRN-LAS_302-S3-3-3 | BRN-LAS_302-S3-3-3-3.2-System | LAS_302 | 3.2 | Update all passwords according to the approved Security SOP | System | 1 | 0.1 | YES | LES Supporting Systems | Valeria Geraci | Amit Krishna | 31/12/2026 | To be started
BRN | BRN-LAS_302 | BRN-LAS_302-S3-3-3 | BRN-LAS_302-S3-3-3-3.3-System | LAS_302 | 3.3 | Test and document the Password policies | System | 0.5 | 1 | YES | LES Supporting Systems | Valeria Geraci | Amit Krishna | 31/12/2026 | To be started
BRN | BRN-LAS_302 | BRN-LAS_302-S4-2-4 | BRN-LAS_302-S4-2-4-4.1-System | LAS_302 | 4.1 | Issue a User List with the actual status of users | System | 0.1 | 0.5 | YES | LES Supporting Systems | Valeria Geraci | Amit Krishna | 31/12/2026 | To be started
BRN | BRN-LAS_302 | BRN-LAS_302-S4-2-4 | BRN-LAS_302-S4-2-4-4.2-Generic | LAS_302 | 4.2 | Issue and approve a Periodic Review for User List | Generic | 0.1 | 0.5 | YES | LES Supporting Systems | Valeria Geraci | Amit Krishna | 31/12/2026 | To be started
BRN | BRN-LAS_302 | BRN-LAS_302-S4-2-4 | BRN-LAS_302-S4-2-4-4.3-System | LAS_302 | 4.3 | Execute Periodic Review | System | 1 | 2 | YES | LES Supporting Systems | Valeria Geraci | Amit Krishna | 31/12/2026 | To be started
BRN | BRN-LAS_302 | BRN-LAS_302-S4-2-4 | BRN-LAS_302-S4-2-4-4.4-System | LAS_302 | 4.4 | Setup of periodic task in relevant system | System | 0.2 | 0 | YES | LES Supporting Systems | Valeria Geraci | Amit Krishna | 31/12/2026 | To be started
BRN | BRN-LAS_302 | BRN-LAS_302-I1-1-5 | BRN-LAS_302-I1-1-5-5.1-System | LAS_302 | 5.1 | Change Control Management including impact assessment | System | 0.5 | 0 | YES | LES Supporting Systems | Valeria Geraci | Amit Krishna | 31/12/2026 | To be started
BRN | BRN-LAS_302 | BRN-LAS_302-I1-1-5 | BRN-LAS_302-I1-1-5-5.2-System | LAS_302 | 5.2 | Implement a process of automatic data backup | System | 1 | 2 | YES | LES Supporting Systems | Valeria Geraci | Amit Krishna | 31/12/2026 | To be started
BRN | BRN-LAS_302 | BRN-LAS_302-I1-1-5 | BRN-LAS_302-I1-1-5-5.3-Generic | LAS_302 | 5.3 | If automatic backup its not possible, document manual backups of system data with a proper frequency to be defined in a dedicated procedure | Generic | 1 | 2 | YES | LES Supporting Systems | Valeria Geraci | Amit Krishna | 31/12/2026 | To be started
BRN | BRN-LAS_302 | BRN-LAS_302-I1-1-5 | BRN-LAS_302-I1-1-5-5.4-System | LAS_302 | 5.4 | Test and document the implemented changes | System | 1 | 2 | YES | LES Supporting Systems | Valeria Geraci | Amit Krishna | 31/12/2026 | To be started
BRN | BRN-LAS_302 | BRN-LAS_302-I1-1-5 | BRN-LAS_302-I1-1-5-5.5-System | LAS_302 | 5.5 | Update relevant SOP | System | 0.2 | 0.2 | YES | LES Supporting Systems | Valeria Geraci | Amit Krishna | 31/12/2026 | To be started
BRN | BRN-LAS_302 | BRN-LAS_302-I2-1-6 | BRN-LAS_302-I2-1-6-6.1-System | LAS_302 | 6.1 | Change Control Management including impact assessment | System | 0.5 | 0 | YES | LES Supporting Systems | Valeria Geraci | Amit Krishna | 31/12/2026 | To be started
BRN | BRN-LAS_302 | BRN-LAS_302-I2-1-6 | BRN-LAS_302-I2-1-6-6.2-System | LAS_302 | 6.2 | Change permissions for users not authorized to modify data, preventing the deletion or alteration. | System | 0.5 | 0 | NO | LES Supporting Systems | Valeria Geraci | Amit Krishna | 31/12/2026 | To be started
BRN | BRN-LAS_302 | BRN-LAS_302-I2-1-6 | BRN-LAS_302-I2-1-6-6.3-System | LAS_302 | 6.3 | Test and document the configuration changes | System | 1 | 2 | YES | LES Supporting Systems | Valeria Geraci | Amit Krishna | 31/12/2026 | To be started
BRN | BRN-LAS_302 | BRN-LAS_302-I2-1-6 | BRN-LAS_302-I2-1-6-6.4-System | LAS_302 | 6.4 | Update relevant SOP | System | 0.5 | 1 | YES | LES Supporting Systems | Valeria Geraci | Amit Krishna | 31/12/2026 | To be started
BRN | BRN-LAS_302 | BRN-LAS_302-I3-1-7 | BRN-LAS_302-I3-1-7-7.1-System | LAS_302 | 7.1 | Change Control Management including impact assessment | System | 0.5 | 0 | YES | LES Supporting Systems | Valeria Geraci | Amit Krishna | 31/12/2026 | To be started
BRN | BRN-LAS_302 | BRN-LAS_302-I3-1-7 | BRN-LAS_302-I3-1-7-7.2-System | LAS_302 | 7.2 | Configure the protection of input data through an automatic security policy or folder restrictions | System | 0.5 | 1 | YES | LES Supporting Systems | Valeria Geraci | Amit Krishna | 31/12/2026 | To be started
BRN | BRN-LAS_302 | BRN-LAS_302-I3-1-7 | BRN-LAS_302-I3-1-7-7.3-System | LAS_302 | 7.3 | Configure user privileges to prevent the deletion or alteration of input data | System | 1 | 2 | YES | LES Supporting Systems | Valeria Geraci | Amit Krishna | 31/12/2026 | To be started
BRN | BRN-LAS_302 | BRN-LAS_302-I3-1-7 | BRN-LAS_302-I3-1-7-7.4-System | LAS_302 | 7.4 | Test and document the configuration changes | System | 1 | 2 | YES | LES Supporting Systems | Valeria Geraci | Amit Krishna | 31/12/2026 | To be started
BRN | BRN-LAS_302 | BRN-LAS_302-I3-1-7 | BRN-LAS_302-I3-1-7-7.5-System | LAS_302 | 7.5 | Update relevant SOP | System | 0.5 | 1 | YES | LES Supporting Systems | Valeria Geraci | Amit Krishna | 31/12/2026 | To be started
BRN | BRN-LAS_302 | BRN-LAS_302-I4-1-8 | BRN-LAS_302-I4-1-8-8.1-System | LAS_302 | 8.1 | Check the system's behaviour towards all electronic records. If autosave is not enforced by the system, define a secure and protected location to save the output records | System | 1 | 1.5 | YES | LES Supporting Systems | Valeria Geraci | Amit Krishna | 31/12/2026 | To be started
BRN | BRN-LAS_302 | BRN-LAS_302-I4-1-8 | BRN-LAS_302-I4-1-8-8.2-System | LAS_302 | 8.2 | Test and document the automatic process implemented or the manual workaround for saving output records | System | 0.5 | 1 | YES | LES Supporting Systems | Valeria Geraci | Amit Krishna | 31/12/2026 | To be started
BRN | BRN-LAS_302 | BRN-LAS_302-I4-1-8 | BRN-LAS_302-I4-1-8-8.3-System | LAS_302 | 8.3 | Update relevant SOP and, if required, schedule a SW update to include autosave of output records | System | 0.5 | 0 | NO | LES Supporting Systems | Valeria Geraci | Amit Krishna | 31/12/2026 | To be started
BRN | BRN-LAS_302 | BRN-LAS_302-T1-1-9 | BRN-LAS_302-T1-1-9-9.1-System | LAS_302 | 9.1 | Change Control Management including impact assessment | System | 0.5 | 0 | YES | LES Supporting Systems | Valeria Geraci | Amit Krishna | 31/12/2026 | To be started
BRN | BRN-LAS_302 | BRN-LAS_302-T1-1-9 | BRN-LAS_302-T1-1-9-9.2-System | LAS_302 | 9.2 | Update Audit Trail functionality in order to track and record modifications to ER | System | 1 | 2 | YES | LES Supporting Systems | Valeria Geraci | Amit Krishna | 31/12/2026 | To be started
BRN | BRN-LAS_302 | BRN-LAS_302-T1-1-9 | BRN-LAS_302-T1-1-9-9.3-Generic | LAS_302 | 9.3 | If Audit Trail is not compliant (e.g. does not track modifications to ER), implement a paper based management of system regulated input records (i.e. methods) with the following paper procedures: -user access log -verification log to be used by the Users before launching a method -traceability log to be used by the system administrators when changing a method | Generic | 2 | 3 | YES | LES Supporting Systems | Valeria Geraci | Amit Krishna | 31/12/2026 | To be started
BRN | BRN-LAS_302 | BRN-LAS_302-T1-1-9 | BRN-LAS_302-T1-1-9-9.4-System | LAS_302 | 9.4 | Test and document that Audit Trail is fully compliant or, in case of paper Audit Trail, that the personnel is trained to use it | System | 0.5 | 1 | YES | LES Supporting Systems | Valeria Geraci | Amit Krishna | 31/12/2026 | To be started
BRN | BRN-LAS_302 | BRN-LAS_302-T1-1-9 | BRN-LAS_302-T1-1-9-9.5-System | LAS_302 | 9.5 | Update relevant SOP | System | 0.5 | 1 | YES | LES Supporting Systems | Valeria Geraci | Amit Krishna | 31/12/2026 | To be started
BRN | BRN-LAS_302 | BRN-LAS_302-T2-1-10 | BRN-LAS_302-T2-1-10-10.1-System | LAS_302 | 10.1 | Change Control Management including impact assessment | System | 0.5 | 0 | YES | LES Supporting Systems | Valeria Geraci | Amit Krishna | 31/12/2026 | To be started
BRN | BRN-LAS_302 | BRN-LAS_302-T2-1-10 | BRN-LAS_302-T2-1-10-10.2-System | LAS_302 | 10.2 | Verify if Time Reference protection can be configured within the system | System | 0.5 | 0.5 | YES | LES Supporting Systems | Valeria Geraci | Amit Krishna | 31/12/2026 | To be started
BRN | BRN-LAS_302 | BRN-LAS_302-T2-1-10 | BRN-LAS_302-T2-1-10-10.3-Generic | LAS_302 | 10.3 | If not possible, manage Date & Time protection through an approved procedure | Generic | 0.5 | 1 | YES | LES Supporting Systems | Valeria Geraci | Amit Krishna | 31/12/2026 | To be started
BRN | BRN-LAS_302 | BRN-LAS_302-T2-1-10 | BRN-LAS_302-T2-1-10-10.4-System | LAS_302 | 10.4 | Test and document configuration changes | System | 1 | 2 | YES | LES Supporting Systems | Valeria Geraci | Amit Krishna | 31/12/2026 | To be started
BRN | BRN-LAS_302 | BRN-LAS_302-T2-1-10 | BRN-LAS_302-T2-1-10-10.5-System | LAS_302 | 10.5 | Update relevant SOP | System | 0.5 | 1 | YES | LES Supporting Systems | Valeria Geraci | Amit Krishna | 31/12/2026 | To be started
BRN | BRN-LAS_302 | BRN-LAS_302-T3-2-11 | BRN-LAS_302-T3-2-11-11.1-Generic | LAS_302 | 11.1 | If there is no Audit Trail Process fully compliant, issue and approve a fully compliant Audit Trail Review Working Instruction | Generic | 1 | 3 | YES | LES Supporting Systems | Valeria Geraci | Amit Krishna | 31/12/2026 | To be started
BRN | BRN-LAS_302 | BRN-LAS_302-T3-2-11 | BRN-LAS_302-T3-2-11-11.2-System | LAS_302 | 11.2 | Execute Audit Trail Review Working Instruction: - perform Data Assessment for Electronic Records managed by the system - update Operational Method SOP (Methods/Instrument) - update test documentation | System | 0.5 | 2.5 | YES | LES Supporting Systems | Valeria Geraci | Amit Krishna | 31/12/2026 | To be started
BRN | BRN-LAS_302 | BRN-LAS_302-T3-2-11 | BRN-LAS_302-T3-2-11-11.3-System | LAS_302 | 11.3 | Setup of periodic task | System | 0.2 | 0 | YES | LES Supporting Systems | Valeria Geraci | Amit Krishna | 31/12/2026 | To be started
BRN | BRN-LAS_302 | BRN-LAS_302-VD1-1-12 | BRN-LAS_302-VD1-1-12-12.1-System | LAS_302 | 12.1 | Review the Computer System Validation in place and identify the missing/incomplete validation documents or testing protocols | System | 1 | 1 | YES | LES Supporting Systems | Valeria Geraci | Amit Krishna | 31/12/2026 | To be started | Validation Plan not present, Global CSV SOPs not applied., Traceability Matrix is not present, VR (called Qualifizierungsbericht, eng. Qualification report) not complete, URS does not include the Regulatory Requirements and ERES definition, Not present, partially covered in delivered vendor documentation, Risk Assessment not present, Testing only for IQ/OQ for the Control System. The level of detail is not consistent with DI expectations, i.e. Security/Integrity/Traceability verifications. Missing tests for documental checks (e.g. Users List, SOPs, etc.), functional checks (Part 11 and Annex 11 verifications), PQ not identified.
BRN | BRN-LAS_302 | BRN-LAS_302-VD1-1-12 | BRN-LAS_302-VD1-1-12-12.2-System | LAS_302 | 12.2 | Issue and approve the missing validation documentation | System | 2 | 3 | YES | LES Supporting Systems | Valeria Geraci | Amit Krishna | 31/12/2026 | To be started
BRN | BRN-LAS_302 | BRN-LAS_302-VD1-1-12 | BRN-LAS_302-VD1-1-12-12.3-System | LAS_302 | 12.3 | Perform and document the missing/incomplete tests | System | 3 | 0 | YES | LES Supporting Systems | Valeria Geraci | Amit Krishna | 31/12/2026 | To be started
BRN | BRN-LAS_302 | BRN-LAS_302-VD1-1-12 | BRN-LAS_302-VD1-1-12-12.4-System | LAS_302 | 12.4 | Assure the Traceability of the testing with coded requirements against coded test and update the documentation accordingly | System | 2 | 2 | YES | LES Supporting Systems | Valeria Geraci | Amit Krishna | 31/12/2026 | To be started
BRN | BRN-LAS_304 | BRN-LAS_304-S1-1-1 | BRN-LAS_304-S1-1-1-1.1-System | LAS_304 | 1.1 | Change Control Management including impact assessment | System | 0.5 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_304 | BRN-LAS_304-S1-1-1 | BRN-LAS_304-S1-1-1-1.2-System | LAS_304 | 1.2 | Create personal and unique accounts in system | System | 1 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_304 | BRN-LAS_304-S1-1-1 | BRN-LAS_304-S1-1-1-1.3-System | LAS_304 | 1.3 | Remove generic accounts from the system | System | 0.5 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_304 | BRN-LAS_304-S1-1-1 | BRN-LAS_304-S1-1-1-1.4-System | LAS_304 | 1.4 | Issue and approve an updated User List | System | 0.1 | 0.5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_304 | BRN-LAS_304-S1-1-1 | BRN-LAS_304-S1-1-1-1.5-System | LAS_304 | 1.5 | Update relevant SOPs and periodically review the User List according to procedure | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_304 | BRN-LAS_304-S2-2-2 | BRN-LAS_304-S2-2-2-2.1-System | LAS_304 | 2.1 | Change Control Management including impact assessment | System | 0.5 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_304 | BRN-LAS_304-S2-2-2 | BRN-LAS_304-S2-2-2-2.2-System | LAS_304 | 2.2 | Configure 3 user groups and define the role of each user | System | 1 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_304 | BRN-LAS_304-S2-2-2 | BRN-LAS_304-S2-2-2-2.3-System | LAS_304 | 2.3 | Configure user privileges according to a proper segregation of duties | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_304 | BRN-LAS_304-S2-2-2 | BRN-LAS_304-S2-2-2-2.4-System | LAS_304 | 2.4 | Test and document the configuration changes | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_304 | BRN-LAS_304-S2-2-2 | BRN-LAS_304-S2-2-2-2.5-System | LAS_304 | 2.5 | Update relevant SOP | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_304 | BRN-LAS_304-S3-3-3 | BRN-LAS_304-S3-3-3-3.1-Generic | LAS_304 | 3.1 | Issue and approve a Security SOP with proper PW security features according to best practices (length, complexity, expiring) | Generic | 1 | 5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_304 | BRN-LAS_304-S3-3-3 | BRN-LAS_304-S3-3-3-3.2-System | LAS_304 | 3.2 | Update all passwords according to the approved Security SOP | System | 1 | 0.1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_304 | BRN-LAS_304-S3-3-3 | BRN-LAS_304-S3-3-3-3.3-System | LAS_304 | 3.3 | Test and document the Password policies | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_304 | BRN-LAS_304-S4-2-4 | BRN-LAS_304-S4-2-4-4.1-System | LAS_304 | 4.1 | Issue a User List with the actual status of users | System | 0.1 | 0.5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_304 | BRN-LAS_304-S4-2-4 | BRN-LAS_304-S4-2-4-4.2-Generic | LAS_304 | 4.2 | Issue and approve a Periodic Review for User List | Generic | 0.1 | 0.5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_304 | BRN-LAS_304-S4-2-4 | BRN-LAS_304-S4-2-4-4.3-System | LAS_304 | 4.3 | Execute Periodic Review | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_304 | BRN-LAS_304-S4-2-4 | BRN-LAS_304-S4-2-4-4.4-System | LAS_304 | 4.4 | Setup of periodic task in relevant system | System | 0.2 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_304 | BRN-LAS_304-I1-1-5 | BRN-LAS_304-I1-1-5-5.1-System | LAS_304 | 5.1 | Change Control Management including impact assessment | System | 0.5 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_304 | BRN-LAS_304-I1-1-5 | BRN-LAS_304-I1-1-5-5.2-System | LAS_304 | 5.2 | Implement a process of automatic data backup | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_304 | BRN-LAS_304-I1-1-5 | BRN-LAS_304-I1-1-5-5.3-Generic | LAS_304 | 5.3 | If automatic backup its not possible, document manual backups of system data with a proper frequency to be defined in a dedicated procedure | Generic | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_304 | BRN-LAS_304-I1-1-5 | BRN-LAS_304-I1-1-5-5.4-System | LAS_304 | 5.4 | Test and document the implemented changes | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_304 | BRN-LAS_304-I1-1-5 | BRN-LAS_304-I1-1-5-5.5-System | LAS_304 | 5.5 | Update relevant SOP | System | 0.2 | 0.2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_304 | BRN-LAS_304-I3-1-6 | BRN-LAS_304-I3-1-6-6.1-System | LAS_304 | 6.1 | Change Control Management including impact assessment | System | 0.5 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_304 | BRN-LAS_304-I3-1-6 | BRN-LAS_304-I3-1-6-6.2-System | LAS_304 | 6.2 | Configure the protection of input data through an automatic security policy or folder restrictions | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_304 | BRN-LAS_304-I3-1-6 | BRN-LAS_304-I3-1-6-6.3-System | LAS_304 | 6.3 | Configure user privileges to prevent the deletion or alteration of input data | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_304 | BRN-LAS_304-I3-1-6 | BRN-LAS_304-I3-1-6-6.4-System | LAS_304 | 6.4 | Test and document the configuration changes | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_304 | BRN-LAS_304-I3-1-6 | BRN-LAS_304-I3-1-6-6.5-System | LAS_304 | 6.5 | Update relevant SOP | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_304 | BRN-LAS_304-T1-1-7 | BRN-LAS_304-T1-1-7-7.1-System | LAS_304 | 7.1 | Change Control Management including impact assessment | System | 0.5 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_304 | BRN-LAS_304-T1-1-7 | BRN-LAS_304-T1-1-7-7.2-System | LAS_304 | 7.2 | Update Audit Trail functionality in order to track and record modifications to ER | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_304 | BRN-LAS_304-T1-1-7 | BRN-LAS_304-T1-1-7-7.3-Generic | LAS_304 | 7.3 | If Audit Trail is not compliant (e.g. does not track modifications to ER), implement a paper based management of system regulated input records (i.e. methods) with the following paper procedures: -user access log -verification log to be used by the Users before launching a method -traceability log to be used by the system administrators when changing a method | Generic | 2 | 3 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_304 | BRN-LAS_304-T1-1-7 | BRN-LAS_304-T1-1-7-7.4-System | LAS_304 | 7.4 | Test and document that Audit Trail is fully compliant or, in case of paper Audit Trail, that the personnel is trained to use it | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_304 | BRN-LAS_304-T1-1-7 | BRN-LAS_304-T1-1-7-7.5-System | LAS_304 | 7.5 | Update relevant SOP | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_304 | BRN-LAS_304-T2-1-8 | BRN-LAS_304-T2-1-8-8.1-System | LAS_304 | 8.1 | Change Control Management including impact assessment | System | 0.5 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_304 | BRN-LAS_304-T2-1-8 | BRN-LAS_304-T2-1-8-8.2-System | LAS_304 | 8.2 | Verify if Time Reference protection can be configured within the system | System | 0.5 | 0.5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_304 | BRN-LAS_304-T2-1-8 | BRN-LAS_304-T2-1-8-8.3-Generic | LAS_304 | 8.3 | If not possible, manage Date & Time protection through an approved procedure | Generic | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_304 | BRN-LAS_304-T2-1-8 | BRN-LAS_304-T2-1-8-8.4-System | LAS_304 | 8.4 | Test and document configuration changes | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_304 | BRN-LAS_304-T2-1-8 | BRN-LAS_304-T2-1-8-8.5-System | LAS_304 | 8.5 | Update relevant SOP | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_304 | BRN-LAS_304-T3-2-9 | BRN-LAS_304-T3-2-9-9.1-Generic | LAS_304 | 9.1 | Issue and approve a fully compliant Audit Trail Review Working Instruction | Generic | 0.5 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_304 | BRN-LAS_304-T3-2-9 | BRN-LAS_304-T3-2-9-9.2-System | LAS_304 | 9.2 | Execute Audit Trail Review Working Instruction: - perform Data Assessment for Electronic Records managed by the system - update Operational Method SOP (Methods/Instrument) - update test documentation | System | 0.5 | 2.5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_304 | BRN-LAS_304-T3-2-9 | BRN-LAS_304-T3-2-9-9.3-System | LAS_304 | 9.3 | Setup of periodic task | System | 0.2 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_304 | BRN-LAS_304-VD1-1-10 | BRN-LAS_304-VD1-1-10-10.1-System | LAS_304 | 10.1 | Review the Computer System Validation in place and identify the missing/incomplete validation documents or testing protocols | System | 1 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started | Validation Plan not present, Global CSV SOPs not applied., Traceability Matrix is not present, VR (called Qualifizierungsbericht, eng. Qualification report) not complete, URS does not include the Regulatory Requirements and ERES definition, Not present, partially covered in delivered vendor documentation, Risk Assessment not present, Testing only for IQ/OQ for the Control System. The level of detail is not consistent with DI expectations, i.e. Security/Integrity/Traceability verifications. Missing tests for documental checks (e.g. Users List, SOPs, etc.), functional checks (Part 11 and Annex 11 verifications), PQ not identified.
BRN | BRN-LAS_304 | BRN-LAS_304-VD1-1-10 | BRN-LAS_304-VD1-1-10-10.2-System | LAS_304 | 10.2 | Issue and approve the missing validation documentation | System | 2 | 3 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_304 | BRN-LAS_304-VD1-1-10 | BRN-LAS_304-VD1-1-10-10.3-System | LAS_304 | 10.3 | Perform and document the missing/incomplete tests | System | 3 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_304 | BRN-LAS_304-VD1-1-10 | BRN-LAS_304-VD1-1-10-10.4-System | LAS_304 | 10.4 | Assure the Traceability of the testing with coded requirements against coded test and update the documentation accordingly | System | 2 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_305 | BRN-LAS_305-S2-3-1 | BRN-LAS_305-S2-3-1-1.1-System | LAS_305 | 1.1 | Define the User Groups and the related privileges in an approved procedure | System | 2 | 3 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_305 | BRN-LAS_305-S2-3-1 | BRN-LAS_305-S2-3-1-1.2-System | LAS_305 | 1.2 | Personnel training to access the system | System | 0.5 | 0.5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_305 | BRN-LAS_305-S2-3-1 | BRN-LAS_305-S2-3-1-1.3-System | LAS_305 | 1.3 | Update relevant SOP | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_305 | BRN-LAS_305-S3-4-2 | BRN-LAS_305-S3-4-2-2.1-Generic | LAS_305 | 2.1 | Issue and approve a Security SOP with proper PW security features according to best practices (length, complexity, expiring) | Generic | 1 | 5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_305 | BRN-LAS_305-S3-4-2 | BRN-LAS_305-S3-4-2-2.2-System | LAS_305 | 2.2 | Update all passwords according to the approved Security SOP | System | 1 | 0.1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_305 | BRN-LAS_305-S3-4-2 | BRN-LAS_305-S3-4-2-2.3-System | LAS_305 | 2.3 | Test and document the Password policies | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_305 | BRN-LAS_305-S4-3-3 | BRN-LAS_305-S4-3-3-3.1-System | LAS_305 | 3.1 | Issue a User List with the actual status of users | System | 0.1 | 0.5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_305 | BRN-LAS_305-S4-3-3 | BRN-LAS_305-S4-3-3-3.2-Generic | LAS_305 | 3.2 | Issue and approve a Periodic Review for User List | Generic | 0.1 | 0.5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_305 | BRN-LAS_305-S4-3-3 | BRN-LAS_305-S4-3-3-3.3-System | LAS_305 | 3.3 | Execute Periodic Review | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_305 | BRN-LAS_305-S4-3-3 | BRN-LAS_305-S4-3-3-3.4-System | LAS_305 | 3.4 | Setup of periodic task in relevant system | System | 0.2 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_305 | BRN-LAS_305-I1-2-4 | BRN-LAS_305-I1-2-4-4.1-System | LAS_305 | 4.1 | Change Control Management including impact assessment | System | 0.5 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_305 | BRN-LAS_305-I1-2-4 | BRN-LAS_305-I1-2-4-4.2-System | LAS_305 | 4.2 | Implement a process of automatic data backup | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_305 | BRN-LAS_305-I1-2-4 | BRN-LAS_305-I1-2-4-4.3-Generic | LAS_305 | 4.3 | If automatic backup its not possible, document manual backups of system data with a proper frequency to be defined in a dedicated procedure | Generic | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_305 | BRN-LAS_305-I1-2-4 | BRN-LAS_305-I1-2-4-4.4-System | LAS_305 | 4.4 | Test and document the implemented changes | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_305 | BRN-LAS_305-I1-2-4 | BRN-LAS_305-I1-2-4-4.5-System | LAS_305 | 4.5 | Update relevant SOP | System | 0.2 | 0.2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_305 | BRN-LAS_305-I3-2-5 | BRN-LAS_305-I3-2-5-5.1-System | LAS_305 | 5.1 | Change Control Management including impact assessment | System | 0.5 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_305 | BRN-LAS_305-I3-2-5 | BRN-LAS_305-I3-2-5-5.2-System | LAS_305 | 5.2 | Configure the protection of input data through an automatic security policy or folder restrictions | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_305 | BRN-LAS_305-I3-2-5 | BRN-LAS_305-I3-2-5-5.3-System | LAS_305 | 5.3 | Configure user privileges to prevent the deletion or alteration of input data | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_305 | BRN-LAS_305-I3-2-5 | BRN-LAS_305-I3-2-5-5.4-System | LAS_305 | 5.4 | Test and document the configuration changes | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_305 | BRN-LAS_305-I3-2-5 | BRN-LAS_305-I3-2-5-5.5-System | LAS_305 | 5.5 | Update relevant SOP | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_305 | BRN-LAS_305-T2-2-6 | BRN-LAS_305-T2-2-6-6.1-System | LAS_305 | 6.1 | Change Control Management including impact assessment | System | 0.5 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_305 | BRN-LAS_305-T2-2-6 | BRN-LAS_305-T2-2-6-6.2-System | LAS_305 | 6.2 | Verify if Time Reference protection can be configured within the system | System | 0.5 | 0.5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_305 | BRN-LAS_305-T2-2-6 | BRN-LAS_305-T2-2-6-6.3-Generic | LAS_305 | 6.3 | If not possible, manage Date & Time protection through an approved procedure | Generic | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_305 | BRN-LAS_305-T2-2-6 | BRN-LAS_305-T2-2-6-6.4-System | LAS_305 | 6.4 | Test and document configuration changes | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_305 | BRN-LAS_305-T2-2-6 | BRN-LAS_305-T2-2-6-6.5-System | LAS_305 | 6.5 | Update relevant SOP | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_305 | BRN-LAS_305-T3-3-7 | BRN-LAS_305-T3-3-7-7.1-Generic | LAS_305 | 7.1 | Issue and approve a fully compliant Audit Trail Review Working Instruction | Generic | 0.5 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_305 | BRN-LAS_305-T3-3-7 | BRN-LAS_305-T3-3-7-7.2-System | LAS_305 | 7.2 | Execute Audit Trail Review Working Instruction: - perform Data Assessment for Electronic Records managed by the system - update Operational Method SOP (Methods/Instrument) - update test documentation | System | 0.5 | 2.5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_305 | BRN-LAS_305-T3-3-7 | BRN-LAS_305-T3-3-7-7.3-System | LAS_305 | 7.3 | Setup of periodic task | System | 0.2 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_305 | BRN-LAS_305-VD1-2-8 | BRN-LAS_305-VD1-2-8-8.1-System | LAS_305 | 8.1 | Review the Computer System Validation in place and identify the missing/incomplete validation documents or testing protocols | System | 1 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started | Validation Plan not present, Global CSV SOPs not applied., Traceability Matrix is not present, VR (called Qualifizierungsbericht, eng. Qualification report) not complete, URS does not include the Regulatory Requirements and ERES definition, Not present, partially covered in delivered vendor documentation, Risk Assessment not present, Testing only for IQ/OQ for the Control System. The level of detail is not consistent with DI expectations, i.e. Security/Integrity/Traceability verifications. Missing tests for documental checks (e.g. Users List, SOPs, etc.), functional checks (Part 11 and Annex 11 verifications), PQ not identified.
BRN | BRN-LAS_305 | BRN-LAS_305-VD1-2-8 | BRN-LAS_305-VD1-2-8-8.2-System | LAS_305 | 8.2 | Issue and approve the missing validation documentation | System | 2 | 3 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_305 | BRN-LAS_305-VD1-2-8 | BRN-LAS_305-VD1-2-8-8.3-System | LAS_305 | 8.3 | Perform and document the missing/incomplete tests | System | 3 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_305 | BRN-LAS_305-VD1-2-8 | BRN-LAS_305-VD1-2-8-8.4-System | LAS_305 | 8.4 | Assure the Traceability of the testing with coded requirements against coded test and update the documentation accordingly | System | 2 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_323 | BRN-LAS_323-S1-1-1 | BRN-LAS_323-S1-1-1-1.1-System | LAS_323 | 1.1 | Change Control Management including impact assessment | System | 0.5 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 31/12/2025 | To be started
BRN | BRN-LAS_323 | BRN-LAS_323-S1-1-1 | BRN-LAS_323-S1-1-1-1.2-System | LAS_323 | 1.2 | Update system administration SOP to describe double account's access mode and functionalities, and how to keep track of their actions to ensure that the user, when logged, follows the permitted actions for the specific user group | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 31/12/2025 | To be started
BRN | BRN-LAS_323 | BRN-LAS_323-S2-2-2 | BRN-LAS_323-S2-2-2-2.1-System | LAS_323 | 2.1 | Change Control Management including impact assessment | System | 0.5 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 31/12/2025 | To be started
BRN | BRN-LAS_323 | BRN-LAS_323-S2-2-2 | BRN-LAS_323-S2-2-2-2.2-System | LAS_323 | 2.2 | Configure 3 user groups and define the role of each user | System | 1 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 31/12/2025 | To be started
BRN | BRN-LAS_323 | BRN-LAS_323-S2-2-2 | BRN-LAS_323-S2-2-2-2.3-System | LAS_323 | 2.3 | Configure user privileges according to a proper segregation of duties | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 31/12/2025 | To be started
BRN | BRN-LAS_323 | BRN-LAS_323-S2-2-2 | BRN-LAS_323-S2-2-2-2.4-System | LAS_323 | 2.4 | Test and document the configuration changes | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 31/12/2025 | To be started
BRN | BRN-LAS_323 | BRN-LAS_323-S2-2-2 | BRN-LAS_323-S2-2-2-2.5-System | LAS_323 | 2.5 | Update relevant SOP | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 31/12/2025 | To be started
BRN | BRN-LAS_323 | BRN-LAS_323-S3-3-3 | BRN-LAS_323-S3-3-3-3.1-Generic | LAS_323 | 3.1 | Issue and approve a Security SOP with proper PW security features according to best practices (length, complexity, expiring) | Generic | 1 | 5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 31/12/2025 | To be started
BRN | BRN-LAS_323 | BRN-LAS_323-S3-3-3 | BRN-LAS_323-S3-3-3-3.2-System | LAS_323 | 3.2 | Update all passwords according to the approved Security SOP | System | 1 | 0.1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 31/12/2025 | To be started
BRN | BRN-LAS_323 | BRN-LAS_323-S3-3-3 | BRN-LAS_323-S3-3-3-3.3-System | LAS_323 | 3.3 | Test and document the Password policies | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 31/12/2025 | To be started
BRN | BRN-LAS_323 | BRN-LAS_323-S4-2-4 | BRN-LAS_323-S4-2-4-4.1-System | LAS_323 | 4.1 | Updating the User List with the actual status of users | System | 0.1 | 0.5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 31/12/2025 | To be started
BRN | BRN-LAS_323 | BRN-LAS_323-S4-2-4 | BRN-LAS_323-S4-2-4-4.2-Generic | LAS_323 | 4.2 | Issue and approve a Periodic Review for User List | Generic | 0.1 | 0.5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 31/12/2025 | To be started
BRN | BRN-LAS_323 | BRN-LAS_323-S4-2-4 | BRN-LAS_323-S4-2-4-4.3-System | LAS_323 | 4.3 | Execute Periodic Review | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 31/12/2025 | To be started
BRN | BRN-LAS_323 | BRN-LAS_323-S4-2-4 | BRN-LAS_323-S4-2-4-4.4-System | LAS_323 | 4.4 | Setup of periodic task in relevant system | System | 0.2 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 31/12/2025 | To be started
BRN | BRN-LAS_323 | BRN-LAS_323-I1-1-5 | BRN-LAS_323-I1-1-5-5.1-System | LAS_323 | 5.1 | Change Control Management including impact assessment | System | 0.5 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 31/12/2025 | To be started
BRN | BRN-LAS_323 | BRN-LAS_323-I1-1-5 | BRN-LAS_323-I1-1-5-5.2-System | LAS_323 | 5.2 | Implement a process of automatic data backup | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 31/12/2025 | To be started
BRN | BRN-LAS_323 | BRN-LAS_323-I1-1-5 | BRN-LAS_323-I1-1-5-5.3-Generic | LAS_323 | 5.3 | If automatic backup its not possible, document manual backups of system data with a proper frequency to be defined in a dedicated procedure | Generic | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 31/12/2025 | To be started
BRN | BRN-LAS_323 | BRN-LAS_323-I1-1-5 | BRN-LAS_323-I1-1-5-5.4-System | LAS_323 | 5.4 | Test and document the implemented changes | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 31/12/2025 | To be started
BRN | BRN-LAS_323 | BRN-LAS_323-I1-1-5 | BRN-LAS_323-I1-1-5-5.5-System | LAS_323 | 5.5 | Update relevant SOP | System | 0.2 | 0.2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 31/12/2025 | To be started
BRN | BRN-LAS_323 | BRN-LAS_323-I3-1-6 | BRN-LAS_323-I3-1-6-6.1-System | LAS_323 | 6.1 | Change Control Management including impact assessment | System | 0.5 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 31/12/2025 | To be started
BRN | BRN-LAS_323 | BRN-LAS_323-I3-1-6 | BRN-LAS_323-I3-1-6-6.2-System | LAS_323 | 6.2 | Configure the protection of input data through an automatic security policy or folder restrictions | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 31/12/2025 | To be started
BRN | BRN-LAS_323 | BRN-LAS_323-I3-1-6 | BRN-LAS_323-I3-1-6-6.3-System | LAS_323 | 6.3 | Configure user privileges to prevent the deletion or alteration of input data | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 31/12/2025 | To be started
BRN | BRN-LAS_323 | BRN-LAS_323-I3-1-6 | BRN-LAS_323-I3-1-6-6.4-System | LAS_323 | 6.4 | Test and document the configuration changes | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 31/12/2025 | To be started
BRN | BRN-LAS_323 | BRN-LAS_323-I3-1-6 | BRN-LAS_323-I3-1-6-6.5-System | LAS_323 | 6.5 | Update relevant SOP | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 31/12/2025 | To be started
BRN | BRN-LAS_323 | BRN-LAS_323-T2-1-7 | BRN-LAS_323-T2-1-7-7.1-System | LAS_323 | 7.1 | Change Control Management including impact assessment | System | 0.5 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 31/12/2025 | To be started
BRN | BRN-LAS_323 | BRN-LAS_323-T2-1-7 | BRN-LAS_323-T2-1-7-7.2-System | LAS_323 | 7.2 | Verify if Time Reference protection can be configured within the system | System | 0.5 | 0.5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 31/12/2025 | To be started
BRN | BRN-LAS_323 | BRN-LAS_323-T2-1-7 | BRN-LAS_323-T2-1-7-7.3-Generic | LAS_323 | 7.3 | If not possible, manage Date & Time protection through an approved procedure | Generic | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 31/12/2025 | To be started
BRN | BRN-LAS_323 | BRN-LAS_323-T2-1-7 | BRN-LAS_323-T2-1-7-7.4-System | LAS_323 | 7.4 | Test and document configuration changes | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 31/12/2025 | To be started
BRN | BRN-LAS_323 | BRN-LAS_323-T2-1-7 | BRN-LAS_323-T2-1-7-7.5-System | LAS_323 | 7.5 | Update relevant SOP | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 31/12/2025 | To be started
BRN | BRN-LAS_323 | BRN-LAS_323-T3-2-8 | BRN-LAS_323-T3-2-8-8.1-Generic | LAS_323 | 8.1 | Issue and approve a fully compliant Audit Trail Review Working Instruction | Generic | 0.5 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 31/12/2025 | To be started
BRN | BRN-LAS_323 | BRN-LAS_323-T3-2-8 | BRN-LAS_323-T3-2-8-8.2-System | LAS_323 | 8.2 | Execute Audit Trail Review Working Instruction: - perform Data Assessment for Electronic Records managed by the system - update Operational Method SOP (Methods/Instrument) - update test documentation | System | 0.5 | 2.5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 31/12/2025 | To be started
BRN | BRN-LAS_323 | BRN-LAS_323-T3-2-8 | BRN-LAS_323-T3-2-8-8.3-System | LAS_323 | 8.3 | Setup of periodic task | System | 0.2 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 31/12/2025 | To be started
BRN | BRN-LAS_323 | BRN-LAS_323-VD1-1-9 | BRN-LAS_323-VD1-1-9-9.1-System | LAS_323 | 9.1 | Review the Computer System Validation in place and identify the missing/incomplete validation documents or testing protocols | System | 1 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 31/12/2025 | To be started | Documentation not present, Global CSV SOPs not applied., Documentation not complete
BRN | BRN-LAS_323 | BRN-LAS_323-VD1-1-9 | BRN-LAS_323-VD1-1-9-9.2-System | LAS_323 | 9.2 | Issue and approve the missing validation documentation | System | 2 | 3 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 31/12/2025 | To be started
BRN | BRN-LAS_323 | BRN-LAS_323-VD1-1-9 | BRN-LAS_323-VD1-1-9-9.3-System | LAS_323 | 9.3 | Perform and document the missing/incomplete tests | System | 3 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 31/12/2025 | To be started
BRN | BRN-LAS_323 | BRN-LAS_323-VD1-1-9 | BRN-LAS_323-VD1-1-9-9.4-System | LAS_323 | 9.4 | Assure the Traceability of the testing with coded requirements against coded test and update the documentation accordingly | System | 2 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 31/12/2025 | To be started
BRN | BRN-LAS_324 | BRN-LAS_324-S1-1-1 | BRN-LAS_324-S1-1-1-1.1-System | LAS_324 | 1.1 | Change Control Management including impact assessment | System | 0.5 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 31/12/2025 | To be started
BRN | BRN-LAS_324 | BRN-LAS_324-S1-1-1 | BRN-LAS_324-S1-1-1-1.2-System | LAS_324 | 1.2 | Update system administration SOP to describe double account's access mode and functionalities, and how to keep track of their actions to ensure that the user, when logged, follows the permitted actions for the specific user group | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 31/12/2025 | To be started
BRN | BRN-LAS_324 | BRN-LAS_324-S2-2-2 | BRN-LAS_324-S2-2-2-2.1-System | LAS_324 | 2.1 | Change Control Management including impact assessment | System | 0.5 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 31/12/2025 | To be started
BRN | BRN-LAS_324 | BRN-LAS_324-S2-2-2 | BRN-LAS_324-S2-2-2-2.2-System | LAS_324 | 2.2 | Configure 3 user groups and define the role of each user | System | 1 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 31/12/2025 | To be started
BRN | BRN-LAS_324 | BRN-LAS_324-S2-2-2 | BRN-LAS_324-S2-2-2-2.3-System | LAS_324 | 2.3 | Configure user privileges according to a proper segregation of duties | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 31/12/2025 | To be started
BRN | BRN-LAS_324 | BRN-LAS_324-S2-2-2 | BRN-LAS_324-S2-2-2-2.4-System | LAS_324 | 2.4 | Test and document the configuration changes | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 31/12/2025 | To be started
BRN | BRN-LAS_324 | BRN-LAS_324-S2-2-2 | BRN-LAS_324-S2-2-2-2.5-System | LAS_324 | 2.5 | Update relevant SOP | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 31/12/2025 | To be started
BRN | BRN-LAS_324 | BRN-LAS_324-S3-3-3 | BRN-LAS_324-S3-3-3-3.1-Generic | LAS_324 | 3.1 | Issue and approve a Security SOP with proper PW security features according to best practices (length, complexity, expiring) | Generic | 1 | 5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 31/12/2025 | To be started
BRN | BRN-LAS_324 | BRN-LAS_324-S3-3-3 | BRN-LAS_324-S3-3-3-3.2-System | LAS_324 | 3.2 | Update all passwords according to the approved Security SOP | System | 1 | 0.1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 31/12/2025 | To be started
BRN | BRN-LAS_324 | BRN-LAS_324-S3-3-3 | BRN-LAS_324-S3-3-3-3.3-System | LAS_324 | 3.3 | Test and document the Password policies | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 31/12/2025 | To be started
BRN | BRN-LAS_324 | BRN-LAS_324-S4-2-4 | BRN-LAS_324-S4-2-4-4.1-System | LAS_324 | 4.1 | Updating the User List with the actual status of users | System | 0.1 | 0.5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 31/12/2025 | To be started
BRN | BRN-LAS_324 | BRN-LAS_324-S4-2-4 | BRN-LAS_324-S4-2-4-4.2-Generic | LAS_324 | 4.2 | Issue and approve a Periodic Review for User List | Generic | 0.1 | 0.5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 31/12/2025 | To be started
BRN | BRN-LAS_324 | BRN-LAS_324-S4-2-4 | BRN-LAS_324-S4-2-4-4.3-System | LAS_324 | 4.3 | Execute Periodic Review | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 31/12/2025 | To be started
BRN | BRN-LAS_324 | BRN-LAS_324-S4-2-4 | BRN-LAS_324-S4-2-4-4.4-System | LAS_324 | 4.4 | Setup of periodic task in relevant system | System | 0.2 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 31/12/2025 | To be started
BRN | BRN-LAS_324 | BRN-LAS_324-I1-1-5 | BRN-LAS_324-I1-1-5-5.1-System | LAS_324 | 5.1 | Change Control Management including impact assessment | System | 0.5 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 31/12/2025 | To be started
BRN | BRN-LAS_324 | BRN-LAS_324-I1-1-5 | BRN-LAS_324-I1-1-5-5.2-System | LAS_324 | 5.2 | Implement a process of automatic data backup | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 31/12/2025 | To be started
BRN | BRN-LAS_324 | BRN-LAS_324-I1-1-5 | BRN-LAS_324-I1-1-5-5.3-Generic | LAS_324 | 5.3 | If automatic backup its not possible, document manual backups of system data with a proper frequency to be defined in a dedicated procedure | Generic | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 31/12/2025 | To be started
BRN | BRN-LAS_324 | BRN-LAS_324-I1-1-5 | BRN-LAS_324-I1-1-5-5.4-System | LAS_324 | 5.4 | Test and document the implemented changes | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 31/12/2025 | To be started
BRN | BRN-LAS_324 | BRN-LAS_324-I1-1-5 | BRN-LAS_324-I1-1-5-5.5-System | LAS_324 | 5.5 | Update relevant SOP | System | 0.2 | 0.2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 31/12/2025 | To be started
BRN | BRN-LAS_324 | BRN-LAS_324-I3-1-6 | BRN-LAS_324-I3-1-6-6.1-System | LAS_324 | 6.1 | Change Control Management including impact assessment | System | 0.5 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 31/12/2025 | To be started
BRN | BRN-LAS_324 | BRN-LAS_324-I3-1-6 | BRN-LAS_324-I3-1-6-6.2-System | LAS_324 | 6.2 | Configure the protection of input data through an automatic security policy or folder restrictions | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 31/12/2025 | To be started
BRN | BRN-LAS_324 | BRN-LAS_324-I3-1-6 | BRN-LAS_324-I3-1-6-6.3-System | LAS_324 | 6.3 | Configure user privileges to prevent the deletion or alteration of input data | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 31/12/2025 | To be started
BRN | BRN-LAS_324 | BRN-LAS_324-I3-1-6 | BRN-LAS_324-I3-1-6-6.4-System | LAS_324 | 6.4 | Test and document the configuration changes | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 31/12/2025 | To be started
BRN | BRN-LAS_324 | BRN-LAS_324-I3-1-6 | BRN-LAS_324-I3-1-6-6.5-System | LAS_324 | 6.5 | Update relevant SOP | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 31/12/2025 | To be started
BRN | BRN-LAS_324 | BRN-LAS_324-T2-1-7 | BRN-LAS_324-T2-1-7-7.1-System | LAS_324 | 7.1 | Change Control Management including impact assessment | System | 0.5 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 31/12/2025 | To be started
BRN | BRN-LAS_324 | BRN-LAS_324-T2-1-7 | BRN-LAS_324-T2-1-7-7.2-System | LAS_324 | 7.2 | Verify if Time Reference protection can be configured within the system | System | 0.5 | 0.5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 31/12/2025 | To be started
BRN | BRN-LAS_324 | BRN-LAS_324-T2-1-7 | BRN-LAS_324-T2-1-7-7.3-Generic | LAS_324 | 7.3 | If not possible, manage Date & Time protection through an approved procedure | Generic | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 31/12/2025 | To be started
BRN | BRN-LAS_324 | BRN-LAS_324-T2-1-7 | BRN-LAS_324-T2-1-7-7.4-System | LAS_324 | 7.4 | Test and document configuration changes | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 31/12/2025 | To be started
BRN | BRN-LAS_324 | BRN-LAS_324-T2-1-7 | BRN-LAS_324-T2-1-7-7.5-System | LAS_324 | 7.5 | Update relevant SOP | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 31/12/2025 | To be started
BRN | BRN-LAS_324 | BRN-LAS_324-T3-2-8 | BRN-LAS_324-T3-2-8-8.1-Generic | LAS_324 | 8.1 | Issue and approve a fully compliant Audit Trail Review Working Instruction | Generic | 0.5 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 31/12/2025 | To be started
BRN | BRN-LAS_324 | BRN-LAS_324-T3-2-8 | BRN-LAS_324-T3-2-8-8.2-System | LAS_324 | 8.2 | Execute Audit Trail Review Working Instruction: - perform Data Assessment for Electronic Records managed by the system - update Operational Method SOP (Methods/Instrument) - update test documentation | System | 0.5 | 2.5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 31/12/2025 | To be started
BRN | BRN-LAS_324 | BRN-LAS_324-T3-2-8 | BRN-LAS_324-T3-2-8-8.3-System | LAS_324 | 8.3 | Setup of periodic task | System | 0.2 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 31/12/2025 | To be started
BRN | BRN-LAS_324 | BRN-LAS_324-VD1-1-9 | BRN-LAS_324-VD1-1-9-9.1-System | LAS_324 | 9.1 | Review the Computer System Validation in place and identify the missing/incomplete validation documents or testing protocols | System | 1 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 31/12/2025 | To be started | Documentation not present, Global CSV SOPs not applied., Documentation not complete
BRN | BRN-LAS_324 | BRN-LAS_324-VD1-1-9 | BRN-LAS_324-VD1-1-9-9.2-System | LAS_324 | 9.2 | Issue and approve the missing validation documentation | System | 2 | 3 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 31/12/2025 | To be started
BRN | BRN-LAS_324 | BRN-LAS_324-VD1-1-9 | BRN-LAS_324-VD1-1-9-9.3-System | LAS_324 | 9.3 | Perform and document the missing/incomplete tests | System | 3 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 31/12/2025 | To be started
BRN | BRN-LAS_324 | BRN-LAS_324-VD1-1-9 | BRN-LAS_324-VD1-1-9-9.4-System | LAS_324 | 9.4 | Assure the Traceability of the testing with coded requirements against coded test and update the documentation accordingly | System | 2 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 31/12/2025 | To be started
BRN | BRN-LAS_325 | BRN-LAS_325-S1-1-1 | BRN-LAS_325-S1-1-1-1.1-System | LAS_325 | 1.1 | Change Control Management including impact assessment | System | 0.5 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 31/12/2025 | To be started
BRN | BRN-LAS_325 | BRN-LAS_325-S1-1-1 | BRN-LAS_325-S1-1-1-1.2-System | LAS_325 | 1.2 | Update system administration SOP to describe double account's access mode and functionalities, and how to keep track of their actions to ensure that the user, when logged, follows the permitted actions for the specific user group | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 31/12/2025 | To be started
BRN | BRN-LAS_325 | BRN-LAS_325-S2-2-2 | BRN-LAS_325-S2-2-2-2.1-System | LAS_325 | 2.1 | Change Control Management including impact assessment | System | 0.5 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 31/12/2025 | To be started
BRN | BRN-LAS_325 | BRN-LAS_325-S2-2-2 | BRN-LAS_325-S2-2-2-2.2-System | LAS_325 | 2.2 | Configure 3 user groups and define the role of each user | System | 1 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 31/12/2025 | To be started
BRN | BRN-LAS_325 | BRN-LAS_325-S2-2-2 | BRN-LAS_325-S2-2-2-2.3-System | LAS_325 | 2.3 | Configure user privileges according to a proper segregation of duties | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 31/12/2025 | To be started
BRN | BRN-LAS_325 | BRN-LAS_325-S2-2-2 | BRN-LAS_325-S2-2-2-2.4-System | LAS_325 | 2.4 | Test and document the configuration changes | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 31/12/2025 | To be started
BRN | BRN-LAS_325 | BRN-LAS_325-S2-2-2 | BRN-LAS_325-S2-2-2-2.5-System | LAS_325 | 2.5 | Update relevant SOP | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 31/12/2025 | To be started
BRN | BRN-LAS_325 | BRN-LAS_325-S3-3-3 | BRN-LAS_325-S3-3-3-3.1-Generic | LAS_325 | 3.1 | Issue and approve a Security SOP with proper PW security features according to best practices (length, complexity, expiring) | Generic | 1 | 5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 31/12/2025 | To be started
BRN | BRN-LAS_325 | BRN-LAS_325-S3-3-3 | BRN-LAS_325-S3-3-3-3.2-System | LAS_325 | 3.2 | Update all passwords according to the approved Security SOP | System | 1 | 0.1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 31/12/2025 | To be started
BRN | BRN-LAS_325 | BRN-LAS_325-S3-3-3 | BRN-LAS_325-S3-3-3-3.3-System | LAS_325 | 3.3 | Test and document the Password policies | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 31/12/2025 | To be started
BRN | BRN-LAS_325 | BRN-LAS_325-S4-2-4 | BRN-LAS_325-S4-2-4-4.1-System | LAS_325 | 4.1 | Updating the User List with the actual status of users | System | 0.1 | 0.5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 31/12/2025 | To be started
BRN | BRN-LAS_325 | BRN-LAS_325-S4-2-4 | BRN-LAS_325-S4-2-4-4.2-Generic | LAS_325 | 4.2 | Issue and approve a Periodic Review for User List | Generic | 0.1 | 0.5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 31/12/2025 | To be started
BRN | BRN-LAS_325 | BRN-LAS_325-S4-2-4 | BRN-LAS_325-S4-2-4-4.3-System | LAS_325 | 4.3 | Execute Periodic Review | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 31/12/2025 | To be started
BRN | BRN-LAS_325 | BRN-LAS_325-S4-2-4 | BRN-LAS_325-S4-2-4-4.4-System | LAS_325 | 4.4 | Setup of periodic task in relevant system | System | 0.2 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 31/12/2025 | To be started
BRN | BRN-LAS_325 | BRN-LAS_325-I1-1-5 | BRN-LAS_325-I1-1-5-5.1-System | LAS_325 | 5.1 | Change Control Management including impact assessment | System | 0.5 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 31/12/2025 | To be started
BRN | BRN-LAS_325 | BRN-LAS_325-I1-1-5 | BRN-LAS_325-I1-1-5-5.2-System | LAS_325 | 5.2 | Implement a process of automatic data backup | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 31/12/2025 | To be started
BRN | BRN-LAS_325 | BRN-LAS_325-I1-1-5 | BRN-LAS_325-I1-1-5-5.3-Generic | LAS_325 | 5.3 | If automatic backup its not possible, document manual backups of system data with a proper frequency to be defined in a dedicated procedure | Generic | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 31/12/2025 | To be started
BRN | BRN-LAS_325 | BRN-LAS_325-I1-1-5 | BRN-LAS_325-I1-1-5-5.4-System | LAS_325 | 5.4 | Test and document the implemented changes | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 31/12/2025 | To be started
BRN | BRN-LAS_325 | BRN-LAS_325-I1-1-5 | BRN-LAS_325-I1-1-5-5.5-System | LAS_325 | 5.5 | Update relevant SOP | System | 0.2 | 0.2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 31/12/2025 | To be started
BRN | BRN-LAS_325 | BRN-LAS_325-I3-1-6 | BRN-LAS_325-I3-1-6-6.1-System | LAS_325 | 6.1 | Change Control Management including impact assessment | System | 0.5 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 31/12/2025 | To be started
BRN | BRN-LAS_325 | BRN-LAS_325-I3-1-6 | BRN-LAS_325-I3-1-6-6.2-System | LAS_325 | 6.2 | Configure the protection of input data through an automatic security policy or folder restrictions | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 31/12/2025 | To be started
BRN | BRN-LAS_325 | BRN-LAS_325-I3-1-6 | BRN-LAS_325-I3-1-6-6.3-System | LAS_325 | 6.3 | Configure user privileges to prevent the deletion or alteration of input data | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 31/12/2025 | To be started
BRN | BRN-LAS_325 | BRN-LAS_325-I3-1-6 | BRN-LAS_325-I3-1-6-6.4-System | LAS_325 | 6.4 | Test and document the configuration changes | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 31/12/2025 | To be started
BRN | BRN-LAS_325 | BRN-LAS_325-I3-1-6 | BRN-LAS_325-I3-1-6-6.5-System | LAS_325 | 6.5 | Update relevant SOP | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 31/12/2025 | To be started
BRN | BRN-LAS_325 | BRN-LAS_325-T2-1-7 | BRN-LAS_325-T2-1-7-7.1-System | LAS_325 | 7.1 | Change Control Management including impact assessment | System | 0.5 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 31/12/2025 | To be started
BRN | BRN-LAS_325 | BRN-LAS_325-T2-1-7 | BRN-LAS_325-T2-1-7-7.2-System | LAS_325 | 7.2 | Verify if Time Reference protection can be configured within the system | System | 0.5 | 0.5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 31/12/2025 | To be started
BRN | BRN-LAS_325 | BRN-LAS_325-T2-1-7 | BRN-LAS_325-T2-1-7-7.3-Generic | LAS_325 | 7.3 | If not possible, manage Date & Time protection through an approved procedure | Generic | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 31/12/2025 | To be started
BRN | BRN-LAS_325 | BRN-LAS_325-T2-1-7 | BRN-LAS_325-T2-1-7-7.4-System | LAS_325 | 7.4 | Test and document configuration changes | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 31/12/2025 | To be started
BRN | BRN-LAS_325 | BRN-LAS_325-T2-1-7 | BRN-LAS_325-T2-1-7-7.5-System | LAS_325 | 7.5 | Update relevant SOP | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 31/12/2025 | To be started
BRN | BRN-LAS_325 | BRN-LAS_325-T3-2-8 | BRN-LAS_325-T3-2-8-8.1-Generic | LAS_325 | 8.1 | Issue and approve a fully compliant Audit Trail Review Working Instruction | Generic | 0.5 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 31/12/2025 | To be started
BRN | BRN-LAS_325 | BRN-LAS_325-T3-2-8 | BRN-LAS_325-T3-2-8-8.2-System | LAS_325 | 8.2 | Execute Audit Trail Review Working Instruction: - perform Data Assessment for Electronic Records managed by the system - update Operational Method SOP (Methods/Instrument) - update test documentation | System | 0.5 | 2.5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 31/12/2025 | To be started
BRN | BRN-LAS_325 | BRN-LAS_325-T3-2-8 | BRN-LAS_325-T3-2-8-8.3-System | LAS_325 | 8.3 | Setup of periodic task | System | 0.2 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 31/12/2025 | To be started
BRN | BRN-LAS_325 | BRN-LAS_325-VD1-1-9 | BRN-LAS_325-VD1-1-9-9.1-System | LAS_325 | 9.1 | Review the Computer System Validation in place and identify the missing/incomplete validation documents or testing protocols | System | 1 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 31/12/2025 | To be started | Documentation not present, Global CSV SOPs not applied., Documentation not complete
BRN | BRN-LAS_325 | BRN-LAS_325-VD1-1-9 | BRN-LAS_325-VD1-1-9-9.2-System | LAS_325 | 9.2 | Issue and approve the missing validation documentation | System | 2 | 3 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 31/12/2025 | To be started
BRN | BRN-LAS_325 | BRN-LAS_325-VD1-1-9 | BRN-LAS_325-VD1-1-9-9.3-System | LAS_325 | 9.3 | Perform and document the missing/incomplete tests | System | 3 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 31/12/2025 | To be started
BRN | BRN-LAS_325 | BRN-LAS_325-VD1-1-9 | BRN-LAS_325-VD1-1-9-9.4-System | LAS_325 | 9.4 | Assure the Traceability of the testing with coded requirements against coded test and update the documentation accordingly | System | 2 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 31/12/2025 | To be started
BRN | BRN-LAS_326 | BRN-LAS_326-S1-1-1 | BRN-LAS_326-S1-1-1-1.1-System | LAS_326 | 1.1 | Change Control Management including impact assessment | System | 0.5 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 30/04/2025 | To be started
BRN | BRN-LAS_326 | BRN-LAS_326-S1-1-1 | BRN-LAS_326-S1-1-1-1.2-System | LAS_326 | 1.2 | Update system administration SOP to describe double account's access mode and functionalities, and how to keep track of their actions to ensure that the user, when logged, follows the permitted actions for the specific user group | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 30/04/2025 | To be started
BRN | BRN-LAS_326 | BRN-LAS_326-S2-2-2 | BRN-LAS_326-S2-2-2-2.1-System | LAS_326 | 2.1 | Change Control Management including impact assessment | System | 0.5 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 30/04/2025 | To be started
BRN | BRN-LAS_326 | BRN-LAS_326-S2-2-2 | BRN-LAS_326-S2-2-2-2.2-System | LAS_326 | 2.2 | Configure 3 user groups and define the role of each user | System | 1 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 30/04/2025 | To be started
BRN | BRN-LAS_326 | BRN-LAS_326-S2-2-2 | BRN-LAS_326-S2-2-2-2.3-System | LAS_326 | 2.3 | Configure user privileges according to a proper segregation of duties | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 30/04/2025 | To be started
BRN | BRN-LAS_326 | BRN-LAS_326-S2-2-2 | BRN-LAS_326-S2-2-2-2.4-System | LAS_326 | 2.4 | Test and document the configuration changes | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 30/04/2025 | To be started
BRN | BRN-LAS_326 | BRN-LAS_326-S2-2-2 | BRN-LAS_326-S2-2-2-2.5-System | LAS_326 | 2.5 | Update relevant SOP | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 30/04/2025 | To be started
BRN | BRN-LAS_326 | BRN-LAS_326-S3-3-3 | BRN-LAS_326-S3-3-3-3.1-Generic | LAS_326 | 3.1 | Issue and approve a Security SOP with proper PW security features according to best practices (length, complexity, expiring) | Generic | 1 | 5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 30/04/2025 | To be started
BRN | BRN-LAS_326 | BRN-LAS_326-S3-3-3 | BRN-LAS_326-S3-3-3-3.2-System | LAS_326 | 3.2 | Update all passwords according to the approved Security SOP | System | 1 | 0.1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 30/04/2025 | To be started
BRN | BRN-LAS_326 | BRN-LAS_326-S3-3-3 | BRN-LAS_326-S3-3-3-3.3-System | LAS_326 | 3.3 | Test and document the Password policies | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 30/04/2025 | To be started
BRN | BRN-LAS_326 | BRN-LAS_326-S4-2-4 | BRN-LAS_326-S4-2-4-4.1-System | LAS_326 | 4.1 | Updating the User List with the actual status of users | System | 0.1 | 0.5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 30/04/2025 | To be started
BRN | BRN-LAS_326 | BRN-LAS_326-S4-2-4 | BRN-LAS_326-S4-2-4-4.2-Generic | LAS_326 | 4.2 | Issue and approve a Periodic Review for User List | Generic | 0.1 | 0.5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 30/04/2025 | To be started
BRN | BRN-LAS_326 | BRN-LAS_326-S4-2-4 | BRN-LAS_326-S4-2-4-4.3-System | LAS_326 | 4.3 | Execute Periodic Review | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 30/04/2025 | To be started
BRN | BRN-LAS_326 | BRN-LAS_326-S4-2-4 | BRN-LAS_326-S4-2-4-4.4-System | LAS_326 | 4.4 | Setup of periodic task in relevant system | System | 0.2 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 30/04/2025 | To be started
BRN | BRN-LAS_326 | BRN-LAS_326-I1-1-5 | BRN-LAS_326-I1-1-5-5.1-System | LAS_326 | 5.1 | Change Control Management including impact assessment | System | 0.5 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 30/04/2025 | To be started
BRN | BRN-LAS_326 | BRN-LAS_326-I1-1-5 | BRN-LAS_326-I1-1-5-5.2-System | LAS_326 | 5.2 | Implement a process of automatic data backup | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 30/04/2025 | To be started
BRN | BRN-LAS_326 | BRN-LAS_326-I1-1-5 | BRN-LAS_326-I1-1-5-5.3-Generic | LAS_326 | 5.3 | If automatic backup its not possible, document manual backups of system data with a proper frequency to be defined in a dedicated procedure | Generic | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 30/04/2025 | To be started
BRN | BRN-LAS_326 | BRN-LAS_326-I1-1-5 | BRN-LAS_326-I1-1-5-5.4-System | LAS_326 | 5.4 | Test and document the implemented changes | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 30/04/2025 | To be started
BRN | BRN-LAS_326 | BRN-LAS_326-I1-1-5 | BRN-LAS_326-I1-1-5-5.5-System | LAS_326 | 5.5 | Update relevant SOP | System | 0.2 | 0.2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 30/04/2025 | To be started
BRN | BRN-LAS_326 | BRN-LAS_326-I3-1-6 | BRN-LAS_326-I3-1-6-6.1-System | LAS_326 | 6.1 | Change Control Management including impact assessment | System | 0.5 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 30/04/2025 | To be started
BRN | BRN-LAS_326 | BRN-LAS_326-I3-1-6 | BRN-LAS_326-I3-1-6-6.2-System | LAS_326 | 6.2 | Configure the protection of input data through an automatic security policy or folder restrictions | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 30/04/2025 | To be started
BRN | BRN-LAS_326 | BRN-LAS_326-I3-1-6 | BRN-LAS_326-I3-1-6-6.3-System | LAS_326 | 6.3 | Configure user privileges to prevent the deletion or alteration of input data | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 30/04/2025 | To be started
BRN | BRN-LAS_326 | BRN-LAS_326-I3-1-6 | BRN-LAS_326-I3-1-6-6.4-System | LAS_326 | 6.4 | Test and document the configuration changes | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 30/04/2025 | To be started
BRN | BRN-LAS_326 | BRN-LAS_326-I3-1-6 | BRN-LAS_326-I3-1-6-6.5-System | LAS_326 | 6.5 | Update relevant SOP | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 30/04/2025 | To be started
BRN | BRN-LAS_326 | BRN-LAS_326-T2-1-7 | BRN-LAS_326-T2-1-7-7.1-System | LAS_326 | 7.1 | Change Control Management including impact assessment | System | 0.5 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 30/04/2025 | To be started
BRN | BRN-LAS_326 | BRN-LAS_326-T2-1-7 | BRN-LAS_326-T2-1-7-7.2-System | LAS_326 | 7.2 | Verify if Time Reference protection can be configured within the system | System | 0.5 | 0.5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 30/04/2025 | To be started
BRN | BRN-LAS_326 | BRN-LAS_326-T2-1-7 | BRN-LAS_326-T2-1-7-7.3-Generic | LAS_326 | 7.3 | If not possible, manage Date & Time protection through an approved procedure | Generic | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 30/04/2025 | To be started
BRN | BRN-LAS_326 | BRN-LAS_326-T2-1-7 | BRN-LAS_326-T2-1-7-7.4-System | LAS_326 | 7.4 | Test and document configuration changes | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 30/04/2025 | To be started
BRN | BRN-LAS_326 | BRN-LAS_326-T2-1-7 | BRN-LAS_326-T2-1-7-7.5-System | LAS_326 | 7.5 | Update relevant SOP | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 30/04/2025 | To be started
BRN | BRN-LAS_326 | BRN-LAS_326-T3-2-8 | BRN-LAS_326-T3-2-8-8.1-Generic | LAS_326 | 8.1 | Issue and approve a fully compliant Audit Trail Review Working Instruction | Generic | 0.5 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 30/04/2025 | To be started
BRN | BRN-LAS_326 | BRN-LAS_326-T3-2-8 | BRN-LAS_326-T3-2-8-8.2-System | LAS_326 | 8.2 | Execute Audit Trail Review Working Instruction: - perform Data Assessment for Electronic Records managed by the system - update Operational Method SOP (Methods/Instrument) - update test documentation | System | 0.5 | 2.5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 30/04/2025 | To be started
BRN | BRN-LAS_326 | BRN-LAS_326-T3-2-8 | BRN-LAS_326-T3-2-8-8.3-System | LAS_326 | 8.3 | Setup of periodic task | System | 0.2 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 30/04/2025 | To be started
BRN | BRN-LAS_326 | BRN-LAS_326-VD1-1-9 | BRN-LAS_326-VD1-1-9-8.4-System | LAS_326 | 8.4 | Review the Computer System Validation in place and identify the missing/incomplete validation documents or testing protocols | System | 1 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 30/04/2025 | To be started | Documentation not present, Global CSV SOPs not applied., Documentation not complete
BRN | BRN-LAS_326 | BRN-LAS_326-VD1-1-9 | BRN-LAS_326-VD1-1-9-8.5-System | LAS_326 | 8.5 | Issue and approve the missing validation documentation | System | 2 | 3 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 30/04/2025 | To be started
BRN | BRN-LAS_326 | BRN-LAS_326-VD1-1-9 | BRN-LAS_326-VD1-1-9-9.1-System | LAS_326 | 9.1 | Perform and document the missing/incomplete tests | System | 3 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 30/04/2025 | To be started
BRN | BRN-LAS_326 | BRN-LAS_326-VD1-1-9 | BRN-LAS_326-VD1-1-9-9.2-System | LAS_326 | 9.2 | Assure the Traceability of the testing with coded requirements against coded test and update the documentation accordingly | System | 2 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 30/04/2025 | To be started
BRN | BRN-LAS_332 | BRN-LAS_332-S1-1-1 | BRN-LAS_332-S1-1-1-1.1-System | LAS_332 | 1.1 | Change Control Management including impact assessment | System | 0.5 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_332 | BRN-LAS_332-S1-1-1 | BRN-LAS_332-S1-1-1-1.2-System | LAS_332 | 1.2 | Update the application SW in order to configure unique and personal accounts. If it is not possible to configure personal account within application SW, implement a proper user management within OS accounts | System | 3 | 3 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_332 | BRN-LAS_332-S1-1-1 | BRN-LAS_332-S1-1-1-1.3-System | LAS_332 | 1.3 | Test and document the configuration changes or procedural changes | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_332 | BRN-LAS_332-S1-1-1 | BRN-LAS_332-S1-1-1-1.4-System | LAS_332 | 1.4 | Issue and approve a User List | System | 0.1 | 0.5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_332 | BRN-LAS_332-S1-1-1 | BRN-LAS_332-S1-1-1-1.5-System | LAS_332 | 1.5 | Update relevant SOPs and periodically review the User List according to procedure | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_332 | BRN-LAS_332-S2-2-2 | BRN-LAS_332-S2-2-2-2.1-System | LAS_332 | 2.1 | Change Control Management including impact assessment | System | 0.5 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_332 | BRN-LAS_332-S2-2-2 | BRN-LAS_332-S2-2-2-2.2-System | LAS_332 | 2.2 | Configure 3 user groups and define the role of each user | System | 1 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_332 | BRN-LAS_332-S2-2-2 | BRN-LAS_332-S2-2-2-2.3-System | LAS_332 | 2.3 | Configure user privileges according to a proper segregation of duties | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_332 | BRN-LAS_332-S2-2-2 | BRN-LAS_332-S2-2-2-2.4-System | LAS_332 | 2.4 | Test and document the configuration changes | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_332 | BRN-LAS_332-S2-2-2 | BRN-LAS_332-S2-2-2-2.5-System | LAS_332 | 2.5 | Update relevant SOP | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_332 | BRN-LAS_332-S3-3-3 | BRN-LAS_332-S3-3-3-3.1-System | LAS_332 | 3.1 | Investigate with the supplier if it is possible to upgrade the software to grant proper security features for user access | System | 1 | 0 | NO | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_332 | BRN-LAS_332-S3-3-3 | BRN-LAS_332-S3-3-3-3.2-Generic | LAS_332 | 3.2 | Define the Password features in an approved procedure | Generic | 1 | 3 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_332 | BRN-LAS_332-S3-3-3 | BRN-LAS_332-S3-3-3-3.3-System | LAS_332 | 3.3 | Personnel training to access the system | System | 0.5 | 0.5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_332 | BRN-LAS_332-S3-3-3 | BRN-LAS_332-S3-3-3-3.4-System | LAS_332 | 3.4 | Update relevant SOP | System | 0.2 | 0.2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_332 | BRN-LAS_332-S4-2-4 | BRN-LAS_332-S4-2-4-4.1-System | LAS_332 | 4.1 | Issue a User List with the actual status of users | System | 0.1 | 0.5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_332 | BRN-LAS_332-S4-2-4 | BRN-LAS_332-S4-2-4-4.2-Generic | LAS_332 | 4.2 | Issue and approve a Periodic Review for User List | Generic | 0.1 | 0.5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_332 | BRN-LAS_332-S4-2-4 | BRN-LAS_332-S4-2-4-4.3-System | LAS_332 | 4.3 | Execute Periodic Review | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_332 | BRN-LAS_332-S4-2-4 | BRN-LAS_332-S4-2-4-4.4-System | LAS_332 | 4.4 | Setup of periodic task in relevant system | System | 0.2 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_332 | BRN-LAS_332-I1-1-5 | BRN-LAS_332-I1-1-5-5.1-System | LAS_332 | 5.1 | Change Control Management including impact assessment | System | 0.5 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_332 | BRN-LAS_332-I1-1-5 | BRN-LAS_332-I1-1-5-5.2-System | LAS_332 | 5.2 | Implement a process of automatic data backup | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_332 | BRN-LAS_332-I1-1-5 | BRN-LAS_332-I1-1-5-5.3-Generic | LAS_332 | 5.3 | If automatic backup its not possible, document manual backups of system data with a proper frequency to be defined in a dedicated procedure | Generic | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_332 | BRN-LAS_332-I1-1-5 | BRN-LAS_332-I1-1-5-5.4-System | LAS_332 | 5.4 | Test and document the implemented changes | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_332 | BRN-LAS_332-I1-1-5 | BRN-LAS_332-I1-1-5-5.5-System | LAS_332 | 5.5 | Update relevant SOP | System | 0.2 | 0.2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_332 | BRN-LAS_332-I2-1-6 | BRN-LAS_332-I2-1-6-6.1-System | LAS_332 | 6.1 | Change Control Management including impact assessment | System | 0.5 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_332 | BRN-LAS_332-I2-1-6 | BRN-LAS_332-I2-1-6-6.2-System | LAS_332 | 6.2 | Change permissions for users not authorized to modify data, preventing the deletion or alteration. | System | 0.5 | 0 | NO | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_332 | BRN-LAS_332-I2-1-6 | BRN-LAS_332-I2-1-6-6.3-System | LAS_332 | 6.3 | Test and document the configuration changes | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_332 | BRN-LAS_332-I2-1-6 | BRN-LAS_332-I2-1-6-6.4-System | LAS_332 | 6.4 | Update relevant SOP | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_332 | BRN-LAS_332-I3-1-7 | BRN-LAS_332-I3-1-7-6.5-System | LAS_332 | 6.5 | Change Control Management including impact assessment | System | 0.5 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_332 | BRN-LAS_332-I3-1-7 | BRN-LAS_332-I3-1-7-7.1-System | LAS_332 | 7.1 | Configure the protection of input data through an automatic security policy or folder restrictions | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_332 | BRN-LAS_332-I3-1-7 | BRN-LAS_332-I3-1-7-7.2-System | LAS_332 | 7.2 | Configure user privileges to prevent the deletion or alteration of input data | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_332 | BRN-LAS_332-I3-1-7 | BRN-LAS_332-I3-1-7-7.3-System | LAS_332 | 7.3 | Test and document the configuration changes | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_332 | BRN-LAS_332-I3-1-7 | BRN-LAS_332-I3-1-7-8.1-System | LAS_332 | 8.1 | Update relevant SOP | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_332 | BRN-LAS_332-T1-2-8 | BRN-LAS_332-T1-2-8-8.1-System | LAS_332 | 8.1 | Change Control Management including impact assessment | System | 0.5 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_332 | BRN-LAS_332-T1-2-8 | BRN-LAS_332-T1-2-8-8.2-System | LAS_332 | 8.2 | Update Audit Trail functionality in order to track and record modifications to ER | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_332 | BRN-LAS_332-T1-2-8 | BRN-LAS_332-T1-2-8-8.3-System | LAS_332 | 8.3 | Define a naming convention for the input ER | System | 0.2 | 0.2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_332 | BRN-LAS_332-T1-2-8 | BRN-LAS_332-T1-2-8-8.4-Generic | LAS_332 | 8.4 | If Audit Trail is not compliant (e.g. does not track modifications to ER), implement a paper based management of system regulated input records (i.e. methods) with the following paper procedures: -user access log -verification log to be used by the Users before launching a method -traceability log to be used by the system administrators when changing a method | Generic | 2 | 3 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_332 | BRN-LAS_332-T1-2-8 | BRN-LAS_332-T1-2-8-8.5-System | LAS_332 | 8.5 | Test and document that Audit Trail is fully compliant or, in case of paper Audit Trail, that the personnel is trained to use it | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_332 | BRN-LAS_332-T1-2-8 | BRN-LAS_332-T1-2-8-8.6-System | LAS_332 | 8.6 | Update relevant SOP | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_332 | BRN-LAS_332-T2-1-9 | BRN-LAS_332-T2-1-9-9.1-System | LAS_332 | 9.1 | Change Control Management including impact assessment | System | 0.5 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_332 | BRN-LAS_332-T2-1-9 | BRN-LAS_332-T2-1-9-9.2-System | LAS_332 | 9.2 | Verify if Time Reference protection can be configured within the system | System | 0.5 | 0.5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_332 | BRN-LAS_332-T2-1-9 | BRN-LAS_332-T2-1-9-9.3-Generic | LAS_332 | 9.3 | If not possible, manage Date & Time protection through an approved procedure | Generic | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_332 | BRN-LAS_332-T2-1-9 | BRN-LAS_332-T2-1-9-9.4-System | LAS_332 | 9.4 | Test and document configuration changes | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_332 | BRN-LAS_332-T2-1-9 | BRN-LAS_332-T2-1-9-9.5-System | LAS_332 | 9.5 | Update relevant SOP | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_332 | BRN-LAS_332-T3-2-10 | BRN-LAS_332-T3-2-10-10.1-Generic | LAS_332 | 10.1 | Issue and approve a fully compliant Audit Trail Review Working Instruction | Generic | 0.5 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_332 | BRN-LAS_332-T3-2-10 | BRN-LAS_332-T3-2-10-10.2-System | LAS_332 | 10.2 | Execute Audit Trail Review Working Instruction: - perform Data Assessment for Electronic Records managed by the system - update Operational Method SOP (Methods/Instrument) - update test documentation | System | 0.5 | 2.5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_332 | BRN-LAS_332-T3-2-10 | BRN-LAS_332-T3-2-10-10.3-System | LAS_332 | 10.3 | Setup of periodic task | System | 0.2 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_332 | BRN-LAS_332-VD1-1-11 | BRN-LAS_332-VD1-1-11-11.1-System | LAS_332 | 11.1 | Review the Computer System Validation in place and identify the missing/incomplete validation documents or testing protocols | System | 1 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started | Computerized system validation documentation is not complete for Systems (VP, URS, RA, VR and Traceability Matrix are not present), Global CSV SOPs not applied., User Requirements, Functional/Process Risk Analysis or Configuration Specifications (included Security Matrix), is not included in the validation life-cycle., General commissioning documentation only for the Control System. IQ/OQ/PQ not identified. The level of detail is not consistent with DI expectations, i.e. Security/Integrity/Traceability verifications. Missing tests for documental checks (e.g. Users List, SOPs, etc.), functional checks (Part 11 verifications), and missing performance checks (e.g. Method Creation, Data Acquisition, and Report Printing)
BRN | BRN-LAS_332 | BRN-LAS_332-VD1-1-11 | BRN-LAS_332-VD1-1-11-11.2-System | LAS_332 | 11.2 | Issue and approve the missing validation documentation | System | 2 | 3 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_332 | BRN-LAS_332-VD1-1-11 | BRN-LAS_332-VD1-1-11-11.3-System | LAS_332 | 11.3 | Perform and document the missing/incomplete tests | System | 3 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_332 | BRN-LAS_332-VD1-1-11 | BRN-LAS_332-VD1-1-11-11.4-System | LAS_332 | 11.4 | Assure the Traceability of the testing with coded requirements against coded test and update the documentation accordingly | System | 2 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_333 | BRN-LAS_333-S1-1-1 | BRN-LAS_333-S1-1-1-1.1-System | LAS_333 | 1.1 | Change Control Management including impact assessment | System | 0.5 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_333 | BRN-LAS_333-S1-1-1 | BRN-LAS_333-S1-1-1-1.2-System | LAS_333 | 1.2 | Update the application SW in order to configure unique and personal accounts. If it is not possible to configure personal account within application SW, implement a proper user management within OS accounts | System | 3 | 3 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_333 | BRN-LAS_333-S1-1-1 | BRN-LAS_333-S1-1-1-1.3-System | LAS_333 | 1.3 | Test and document the configuration changes or procedural changes | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_333 | BRN-LAS_333-S1-1-1 | BRN-LAS_333-S1-1-1-1.4-System | LAS_333 | 1.4 | Issue and approve a User List | System | 0.1 | 0.5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_333 | BRN-LAS_333-S1-1-1 | BRN-LAS_333-S1-1-1-1.5-System | LAS_333 | 1.5 | Update relevant SOPs and periodically review the User List according to procedure | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_333 | BRN-LAS_333-S2-2-2 | BRN-LAS_333-S2-2-2-2.1-System | LAS_333 | 2.1 | Change Control Management including impact assessment | System | 0.5 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_333 | BRN-LAS_333-S2-2-2 | BRN-LAS_333-S2-2-2-2.2-System | LAS_333 | 2.2 | Configure 3 user groups and define the role of each user | System | 1 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_333 | BRN-LAS_333-S2-2-2 | BRN-LAS_333-S2-2-2-2.3-System | LAS_333 | 2.3 | Configure user privileges according to a proper segregation of duties | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_333 | BRN-LAS_333-S2-2-2 | BRN-LAS_333-S2-2-2-2.4-System | LAS_333 | 2.4 | Test and document the configuration changes | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_333 | BRN-LAS_333-S2-2-2 | BRN-LAS_333-S2-2-2-2.5-System | LAS_333 | 2.5 | Update relevant SOP | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_333 | BRN-LAS_333-S3-3-3 | BRN-LAS_333-S3-3-3-3.1-System | LAS_333 | 3.1 | Investigate with the supplier if it is possible to upgrade the software to grant proper security features for user access | System | 1 | 0 | NO | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_333 | BRN-LAS_333-S3-3-3 | BRN-LAS_333-S3-3-3-3.2-Generic | LAS_333 | 3.2 | Define the Password features in an approved procedure | Generic | 1 | 3 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_333 | BRN-LAS_333-S3-3-3 | BRN-LAS_333-S3-3-3-3.3-System | LAS_333 | 3.3 | Personnel training to access the system | System | 0.5 | 0.5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_333 | BRN-LAS_333-S3-3-3 | BRN-LAS_333-S3-3-3-3.4-System | LAS_333 | 3.4 | Update relevant SOP | System | 0.2 | 0.2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_333 | BRN-LAS_333-S4-2-4 | BRN-LAS_333-S4-2-4-4.1-System | LAS_333 | 4.1 | Issue a User List with the actual status of users | System | 0.1 | 0.5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_333 | BRN-LAS_333-S4-2-4 | BRN-LAS_333-S4-2-4-4.2-Generic | LAS_333 | 4.2 | Issue and approve a Periodic Review for User List | Generic | 0.1 | 0.5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_333 | BRN-LAS_333-S4-2-4 | BRN-LAS_333-S4-2-4-4.3-System | LAS_333 | 4.3 | Execute Periodic Review | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_333 | BRN-LAS_333-S4-2-4 | BRN-LAS_333-S4-2-4-4.4-System | LAS_333 | 4.4 | Setup of periodic task in relevant system | System | 0.2 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_333 | BRN-LAS_333-I1-1-5 | BRN-LAS_333-I1-1-5-5.1-System | LAS_333 | 5.1 | Change Control Management including impact assessment | System | 0.5 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_333 | BRN-LAS_333-I1-1-5 | BRN-LAS_333-I1-1-5-5.2-System | LAS_333 | 5.2 | Implement a process of automatic data backup | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_333 | BRN-LAS_333-I1-1-5 | BRN-LAS_333-I1-1-5-5.3-Generic | LAS_333 | 5.3 | If automatic backup its not possible, document manual backups of system data with a proper frequency to be defined in a dedicated procedure | Generic | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_333 | BRN-LAS_333-I1-1-5 | BRN-LAS_333-I1-1-5-5.4-System | LAS_333 | 5.4 | Test and document the implemented changes | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_333 | BRN-LAS_333-I1-1-5 | BRN-LAS_333-I1-1-5-5.5-System | LAS_333 | 5.5 | Update relevant SOP | System | 0.2 | 0.2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_333 | BRN-LAS_333-I2-1-6 | BRN-LAS_333-I2-1-6-6.1-System | LAS_333 | 6.1 | Change Control Management including impact assessment | System | 0.5 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_333 | BRN-LAS_333-I2-1-6 | BRN-LAS_333-I2-1-6-6.2-System | LAS_333 | 6.2 | Change permissions for users not authorized to modify data, preventing the deletion or alteration. | System | 0.5 | 0 | NO | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_333 | BRN-LAS_333-I2-1-6 | BRN-LAS_333-I2-1-6-6.3-System | LAS_333 | 6.3 | Test and document the configuration changes | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_333 | BRN-LAS_333-I2-1-6 | BRN-LAS_333-I2-1-6-6.4-System | LAS_333 | 6.4 | Update relevant SOP | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_333 | BRN-LAS_333-I3-1-7 | BRN-LAS_333-I3-1-7-6.5-System | LAS_333 | 6.5 | Change Control Management including impact assessment | System | 0.5 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_333 | BRN-LAS_333-I3-1-7 | BRN-LAS_333-I3-1-7-7.1-System | LAS_333 | 7.1 | Configure the protection of input data through an automatic security policy or folder restrictions | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_333 | BRN-LAS_333-I3-1-7 | BRN-LAS_333-I3-1-7-7.2-System | LAS_333 | 7.2 | Configure user privileges to prevent the deletion or alteration of input data | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_333 | BRN-LAS_333-I3-1-7 | BRN-LAS_333-I3-1-7-7.3-System | LAS_333 | 7.3 | Test and document the configuration changes | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_333 | BRN-LAS_333-I3-1-7 | BRN-LAS_333-I3-1-7-8.1-System | LAS_333 | 8.1 | Update relevant SOP | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_333 | BRN-LAS_333-T1-2-8 | BRN-LAS_333-T1-2-8-8.1-System | LAS_333 | 8.1 | Change Control Management including impact assessment | System | 0.5 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_333 | BRN-LAS_333-T1-2-8 | BRN-LAS_333-T1-2-8-8.2-System | LAS_333 | 8.2 | Update Audit Trail functionality in order to track and record modifications to ER | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_333 | BRN-LAS_333-T1-2-8 | BRN-LAS_333-T1-2-8-8.3-System | LAS_333 | 8.3 | Define a naming convention for the input ER | System | 0.2 | 0.2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_333 | BRN-LAS_333-T1-2-8 | BRN-LAS_333-T1-2-8-8.4-Generic | LAS_333 | 8.4 | If Audit Trail is not compliant (e.g. does not track modifications to ER), implement a paper based management of system regulated input records (i.e. methods) with the following paper procedures: -user access log -verification log to be used by the Users before launching a method -traceability log to be used by the system administrators when changing a method | Generic | 2 | 3 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_333 | BRN-LAS_333-T1-2-8 | BRN-LAS_333-T1-2-8-8.5-System | LAS_333 | 8.5 | Test and document that Audit Trail is fully compliant or, in case of paper Audit Trail, that the personnel is trained to use it | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_333 | BRN-LAS_333-T1-2-8 | BRN-LAS_333-T1-2-8-8.6-System | LAS_333 | 8.6 | Update relevant SOP | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_333 | BRN-LAS_333-T2-1-9 | BRN-LAS_333-T2-1-9-9.1-System | LAS_333 | 9.1 | Change Control Management including impact assessment | System | 0.5 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_333 | BRN-LAS_333-T2-1-9 | BRN-LAS_333-T2-1-9-9.2-System | LAS_333 | 9.2 | Verify if Time Reference protection can be configured within the system | System | 0.5 | 0.5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_333 | BRN-LAS_333-T2-1-9 | BRN-LAS_333-T2-1-9-9.3-Generic | LAS_333 | 9.3 | If not possible, manage Date & Time protection through an approved procedure | Generic | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_333 | BRN-LAS_333-T2-1-9 | BRN-LAS_333-T2-1-9-9.4-System | LAS_333 | 9.4 | Test and document configuration changes | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_333 | BRN-LAS_333-T2-1-9 | BRN-LAS_333-T2-1-9-9.5-System | LAS_333 | 9.5 | Update relevant SOP | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_333 | BRN-LAS_333-T3-2-10 | BRN-LAS_333-T3-2-10-10.1-Generic | LAS_333 | 10.1 | Issue and approve a fully compliant Audit Trail Review Working Instruction | Generic | 0.5 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_333 | BRN-LAS_333-T3-2-10 | BRN-LAS_333-T3-2-10-10.2-System | LAS_333 | 10.2 | Execute Audit Trail Review Working Instruction: - perform Data Assessment for Electronic Records managed by the system - update Operational Method SOP (Methods/Instrument) - update test documentation | System | 0.5 | 2.5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_333 | BRN-LAS_333-T3-2-10 | BRN-LAS_333-T3-2-10-10.3-System | LAS_333 | 10.3 | Setup of periodic task | System | 0.2 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_333 | BRN-LAS_333-VD1-1-11 | BRN-LAS_333-VD1-1-11-11.1-System | LAS_333 | 11.1 | Review the Computer System Validation in place and identify the missing/incomplete validation documents or testing protocols | System | 1 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started | Computerized system validation documentation is not complete for Systems (VP, URS, RA, VR and Traceability Matrix are not present), Global CSV SOPs not applied., User Requirements, Functional/Process Risk Analysis or Configuration Specifications (included Security Matrix), is not included in the validation life-cycle., General commissioning documentation only for the Control System. IQ/OQ/PQ not identified. The level of detail is not consistent with DI expectations, i.e. Security/Integrity/Traceability verifications. Missing tests for documental checks (e.g. Users List, SOPs, etc.), functional checks (Part 11 verifications), and missing performance checks (e.g. Method Creation, Data Acquisition, and Report Printing)
BRN | BRN-LAS_333 | BRN-LAS_333-VD1-1-11 | BRN-LAS_333-VD1-1-11-11.2-System | LAS_333 | 11.2 | Issue and approve the missing validation documentation | System | 2 | 3 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_333 | BRN-LAS_333-VD1-1-11 | BRN-LAS_333-VD1-1-11-11.3-System | LAS_333 | 11.3 | Perform and document the missing/incomplete tests | System | 3 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_333 | BRN-LAS_333-VD1-1-11 | BRN-LAS_333-VD1-1-11-11.4-System | LAS_333 | 11.4 | Assure the Traceability of the testing with coded requirements against coded test and update the documentation accordingly | System | 2 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_334 | BRN-LAS_334-S1-1-1 | BRN-LAS_334-S1-1-1-1.1-System | LAS_334 | 1.1 | Change Control Management including impact assessment | System | 0.5 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_334 | BRN-LAS_334-S1-1-1 | BRN-LAS_334-S1-1-1-1.2-System | LAS_334 | 1.2 | Create personal and unique accounts in system | System | 1 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_334 | BRN-LAS_334-S1-1-1 | BRN-LAS_334-S1-1-1-1.3-System | LAS_334 | 1.3 | Remove generic accounts from the system | System | 0.5 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_334 | BRN-LAS_334-S1-1-1 | BRN-LAS_334-S1-1-1-1.4-System | LAS_334 | 1.4 | Issue and approve an updated User List | System | 0.1 | 0.5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_334 | BRN-LAS_334-S1-1-1 | BRN-LAS_334-S1-1-1-1.5-System | LAS_334 | 1.5 | Update relevant SOPs and periodically review the User List according to procedure | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_334 | BRN-LAS_334-S2-2-2 | BRN-LAS_334-S2-2-2-2.1-System | LAS_334 | 2.1 | Define the User Groups and the related privileges in an approved procedure | System | 2 | 3 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_334 | BRN-LAS_334-S2-2-2 | BRN-LAS_334-S2-2-2-2.2-System | LAS_334 | 2.2 | Personnel training to access the system | System | 0.5 | 0.5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_334 | BRN-LAS_334-S2-2-2 | BRN-LAS_334-S2-2-2-2.3-System | LAS_334 | 2.3 | Update relevant SOP | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_334 | BRN-LAS_334-S3-3-3 | BRN-LAS_334-S3-3-3-3.1-Generic | LAS_334 | 3.1 | Issue and approve a Security SOP with proper PW security features according to best practices (length, complexity, expiring) | Generic | 1 | 5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_334 | BRN-LAS_334-S3-3-3 | BRN-LAS_334-S3-3-3-3.2-System | LAS_334 | 3.2 | Update all passwords according to the approved Security SOP | System | 1 | 0.1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_334 | BRN-LAS_334-S3-3-3 | BRN-LAS_334-S3-3-3-3.3-System | LAS_334 | 3.3 | Test and document the Password policies | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_334 | BRN-LAS_334-S4-2-4 | BRN-LAS_334-S4-2-4-4.1-System | LAS_334 | 4.1 | Issue a User List with the actual status of users | System | 0.1 | 0.5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_334 | BRN-LAS_334-S4-2-4 | BRN-LAS_334-S4-2-4-4.2-Generic | LAS_334 | 4.2 | Issue and approve a Periodic Review for User List | Generic | 0.1 | 0.5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_334 | BRN-LAS_334-S4-2-4 | BRN-LAS_334-S4-2-4-4.3-System | LAS_334 | 4.3 | Execute Periodic Review | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_334 | BRN-LAS_334-S4-2-4 | BRN-LAS_334-S4-2-4-4.4-System | LAS_334 | 4.4 | Setup of periodic task in relevant system | System | 0.2 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_334 | BRN-LAS_334-I2-1-5 | BRN-LAS_334-I2-1-5-5.1-System | LAS_334 | 5.1 | Change Control Management including impact assessment | System | 0.5 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_334 | BRN-LAS_334-I2-1-5 | BRN-LAS_334-I2-1-5-5.2-System | LAS_334 | 5.2 | Change permissions for users not authorized to modify data, preventing the deletion or alteration. | System | 0.5 | 0 | NO | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_334 | BRN-LAS_334-I2-1-5 | BRN-LAS_334-I2-1-5-5.3-System | LAS_334 | 5.3 | Test and document the configuration changes | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_334 | BRN-LAS_334-I2-1-5 | BRN-LAS_334-I2-1-5-5.4-System | LAS_334 | 5.4 | Update relevant SOP | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_334 | BRN-LAS_334-I3-1-6 | BRN-LAS_334-I3-1-6-6.1-System | LAS_334 | 6.1 | Change Control Management including impact assessment | System | 0.5 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_334 | BRN-LAS_334-I3-1-6 | BRN-LAS_334-I3-1-6-6.2-System | LAS_334 | 6.2 | Configure the protection of input data through an automatic security policy or folder restrictions | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_334 | BRN-LAS_334-I3-1-6 | BRN-LAS_334-I3-1-6-6.3-System | LAS_334 | 6.3 | Configure user privileges to prevent the deletion or alteration of input data | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_334 | BRN-LAS_334-I3-1-6 | BRN-LAS_334-I3-1-6-6.4-System | LAS_334 | 6.4 | Test and document the configuration changes | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_334 | BRN-LAS_334-I3-1-6 | BRN-LAS_334-I3-1-6-6.5-System | LAS_334 | 6.5 | Update relevant SOP | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_334 | BRN-LAS_334-I4-1-7 | BRN-LAS_334-I4-1-7-7.1-System | LAS_334 | 7.1 | Define a secure and protected location to save the output records | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_334 | BRN-LAS_334-I4-1-7 | BRN-LAS_334-I4-1-7-7.2-System | LAS_334 | 7.2 | Test and document the manual workaround for saving output records | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_334 | BRN-LAS_334-I4-1-7 | BRN-LAS_334-I4-1-7-7.3-System | LAS_334 | 7.3 | Schedule a SW update to include autosave of output records | System | 0.5 | 0 | NO | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_334 | BRN-LAS_334-VD1-1-8 | BRN-LAS_334-VD1-1-8-8.1-System | LAS_334 | 8.1 | Review the Computer System Validation in place and identify the missing/incomplete validation documents or testing protocols | System | 1 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started | Validation Plan not present, Global CSV SOPs not applied., VR (called Qualifizierungsbericht, eng. Qualification report) not complete, URS document present but it is missing Functional Process Requirements, Access Control and Security Roles partially covered, no reference to regulatory rules (e.g. Annex11 coverage), Not present, partially covered in delivered vendor documentation, Risk Assessment not present, IQ/OQ has been identified. The level of detail is not consistent with DI expectations, i.e. Security/Integrity/Traceability verifications. Missing tests for documental checks (e.g. Users List, SOPs, etc.), functional checks (Part 11 and Annex 11 verifications), PQ protocol is not identified
BRN | BRN-LAS_334 | BRN-LAS_334-VD1-1-8 | BRN-LAS_334-VD1-1-8-8.2-System | LAS_334 | 8.2 | Issue and approve the missing validation documentation | System | 2 | 3 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_334 | BRN-LAS_334-VD1-1-8 | BRN-LAS_334-VD1-1-8-8.3-System | LAS_334 | 8.3 | Perform and document the missing/incomplete tests | System | 3 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_334 | BRN-LAS_334-VD1-1-8 | BRN-LAS_334-VD1-1-8-8.4-System | LAS_334 | 8.4 | Assure the Traceability of the testing with coded requirements against coded test and update the documentation accordingly | System | 2 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_335 | BRN-LAS_335-S1-1-1 | BRN-LAS_335-S1-1-1-1.1-System | LAS_335 | 1.1 | Change Control Management including impact assessment | System | 0.5 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_335 | BRN-LAS_335-S1-1-1 | BRN-LAS_335-S1-1-1-1.2-System | LAS_335 | 1.2 | Create personal and unique accounts in system | System | 1 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_335 | BRN-LAS_335-S1-1-1 | BRN-LAS_335-S1-1-1-1.3-System | LAS_335 | 1.3 | Remove generic accounts from the system | System | 0.5 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_335 | BRN-LAS_335-S1-1-1 | BRN-LAS_335-S1-1-1-1.4-System | LAS_335 | 1.4 | Issue and approve an updated User List | System | 0.1 | 0.5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_335 | BRN-LAS_335-S1-1-1 | BRN-LAS_335-S1-1-1-1.5-System | LAS_335 | 1.5 | Update relevant SOPs and periodically review the User List according to procedure | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_335 | BRN-LAS_335-S2-2-2 | BRN-LAS_335-S2-2-2-2.1-System | LAS_335 | 2.1 | Define the User Groups and the related privileges in an approved procedure | System | 2 | 3 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_335 | BRN-LAS_335-S2-2-2 | BRN-LAS_335-S2-2-2-2.2-System | LAS_335 | 2.2 | Personnel training to access the system | System | 0.5 | 0.5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_335 | BRN-LAS_335-S2-2-2 | BRN-LAS_335-S2-2-2-2.3-System | LAS_335 | 2.3 | Update relevant SOP | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_335 | BRN-LAS_335-S3-3-3 | BRN-LAS_335-S3-3-3-3.1-Generic | LAS_335 | 3.1 | Issue and approve a Security SOP with proper PW security features according to best practices (length, complexity, expiring) | Generic | 1 | 5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_335 | BRN-LAS_335-S3-3-3 | BRN-LAS_335-S3-3-3-3.2-System | LAS_335 | 3.2 | Update all passwords according to the approved Security SOP | System | 1 | 0.1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_335 | BRN-LAS_335-S3-3-3 | BRN-LAS_335-S3-3-3-3.3-System | LAS_335 | 3.3 | Test and document the Password policies | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_335 | BRN-LAS_335-S4-2-4 | BRN-LAS_335-S4-2-4-4.1-System | LAS_335 | 4.1 | Issue a User List with the actual status of users | System | 0.1 | 0.5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_335 | BRN-LAS_335-S4-2-4 | BRN-LAS_335-S4-2-4-4.2-Generic | LAS_335 | 4.2 | Issue and approve a Periodic Review for User List | Generic | 0.1 | 0.5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_335 | BRN-LAS_335-S4-2-4 | BRN-LAS_335-S4-2-4-4.3-System | LAS_335 | 4.3 | Execute Periodic Review | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_335 | BRN-LAS_335-S4-2-4 | BRN-LAS_335-S4-2-4-4.4-System | LAS_335 | 4.4 | Setup of periodic task in relevant system | System | 0.2 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_335 | BRN-LAS_335-I2-1-5 | BRN-LAS_335-I2-1-5-5.1-System | LAS_335 | 5.1 | Change Control Management including impact assessment | System | 0.5 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_335 | BRN-LAS_335-I2-1-5 | BRN-LAS_335-I2-1-5-5.2-System | LAS_335 | 5.2 | Change permissions for users not authorized to modify data, preventing the deletion or alteration. | System | 0.5 | 0 | NO | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_335 | BRN-LAS_335-I2-1-5 | BRN-LAS_335-I2-1-5-5.3-System | LAS_335 | 5.3 | Test and document the configuration changes | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_335 | BRN-LAS_335-I2-1-5 | BRN-LAS_335-I2-1-5-5.4-System | LAS_335 | 5.4 | Update relevant SOP | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_335 | BRN-LAS_335-I3-1-6 | BRN-LAS_335-I3-1-6-6.1-System | LAS_335 | 6.1 | Change Control Management including impact assessment | System | 0.5 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_335 | BRN-LAS_335-I3-1-6 | BRN-LAS_335-I3-1-6-6.2-System | LAS_335 | 6.2 | Configure the protection of input data through an automatic security policy or folder restrictions | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_335 | BRN-LAS_335-I3-1-6 | BRN-LAS_335-I3-1-6-6.3-System | LAS_335 | 6.3 | Configure user privileges to prevent the deletion or alteration of input data | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_335 | BRN-LAS_335-I3-1-6 | BRN-LAS_335-I3-1-6-6.4-System | LAS_335 | 6.4 | Test and document the configuration changes | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_335 | BRN-LAS_335-I3-1-6 | BRN-LAS_335-I3-1-6-6.5-System | LAS_335 | 6.5 | Update relevant SOP | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_335 | BRN-LAS_335-I4-1-7 | BRN-LAS_335-I4-1-7-7.1-System | LAS_335 | 7.1 | Define a secure and protected location to save the output records | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_335 | BRN-LAS_335-I4-1-7 | BRN-LAS_335-I4-1-7-7.2-System | LAS_335 | 7.2 | Test and document the manual workaround for saving output records | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_335 | BRN-LAS_335-I4-1-7 | BRN-LAS_335-I4-1-7-7.3-System | LAS_335 | 7.3 | Schedule a SW update to include autosave of output records | System | 0.5 | 0 | NO | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_335 | BRN-LAS_335-VD1-1-8 | BRN-LAS_335-VD1-1-8-8.1-System | LAS_335 | 8.1 | Review the Computer System Validation in place and identify the missing/incomplete validation documents or testing protocols | System | 1 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started | Validation Plan not present, Global CSV SOPs not applied., VR (called Qualifizierungsbericht, eng. Qualification report) not complete, URS document present but it is missing Functional Process Requirements, Access Control and Security Roles partially covered, no reference to regulatory rules (e.g. Annex11 coverage), Not present, partially covered in delivered vendor documentation, Risk Assessment not present, IQ/OQ has been identified. The level of detail is not consistent with DI expectations, i.e. Security/Integrity/Traceability verifications. Missing tests for documental checks (e.g. Users List, SOPs, etc.), functional checks (Part 11 and Annex 11 verifications), PQ protocol is not identified
BRN | BRN-LAS_335 | BRN-LAS_335-VD1-1-8 | BRN-LAS_335-VD1-1-8-8.2-System | LAS_335 | 8.2 | Issue and approve the missing validation documentation | System | 2 | 3 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_335 | BRN-LAS_335-VD1-1-8 | BRN-LAS_335-VD1-1-8-8.3-System | LAS_335 | 8.3 | Perform and document the missing/incomplete tests | System | 3 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_335 | BRN-LAS_335-VD1-1-8 | BRN-LAS_335-VD1-1-8-8.4-System | LAS_335 | 8.4 | Assure the Traceability of the testing with coded requirements against coded test and update the documentation accordingly | System | 2 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_336 | BRN-LAS_336-S3-3-1 | BRN-LAS_336-S3-3-1-1.1-Generic | LAS_336 | 1.1 | Issue and approve a Security SOP with proper PW security features according to best practices (length, complexity, expiring) | Generic | 1 | 5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_336 | BRN-LAS_336-S3-3-1 | BRN-LAS_336-S3-3-1-1.2-System | LAS_336 | 1.2 | Update all passwords according to the approved Security SOP | System | 1 | 0.1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_336 | BRN-LAS_336-S3-3-1 | BRN-LAS_336-S3-3-1-1.3-System | LAS_336 | 1.3 | Test and document the Password policies | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_336 | BRN-LAS_336-S4-2-2 | BRN-LAS_336-S4-2-2-2.1-System | LAS_336 | 2.1 | Issue a User List with the actual status of users | System | 0.1 | 0.5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_336 | BRN-LAS_336-S4-2-2 | BRN-LAS_336-S4-2-2-2.2-Generic | LAS_336 | 2.2 | Issue and approve a Periodic Review for User List | Generic | 0.1 | 0.5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_336 | BRN-LAS_336-S4-2-2 | BRN-LAS_336-S4-2-2-2.3-System | LAS_336 | 2.3 | Execute Periodic Review | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_336 | BRN-LAS_336-S4-2-2 | BRN-LAS_336-S4-2-2-2.4-System | LAS_336 | 2.4 | Setup of periodic task in relevant system | System | 0.2 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_336 | BRN-LAS_336-I2-1-3 | BRN-LAS_336-I2-1-3-3.1-System | LAS_336 | 3.1 | Change Control Management including impact assessment | System | 0.5 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_336 | BRN-LAS_336-I2-1-3 | BRN-LAS_336-I2-1-3-3.2-System | LAS_336 | 3.2 | Change permissions for users not authorized to modify data, preventing the deletion or alteration. | System | 0.5 | 0 | NO | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_336 | BRN-LAS_336-I2-1-3 | BRN-LAS_336-I2-1-3-3.3-System | LAS_336 | 3.3 | Test and document the configuration changes | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_336 | BRN-LAS_336-I2-1-3 | BRN-LAS_336-I2-1-3-3.4-System | LAS_336 | 3.4 | Update relevant SOP | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_336 | BRN-LAS_336-I3-1-4 | BRN-LAS_336-I3-1-4-4.1-System | LAS_336 | 4.1 | Change Control Management including impact assessment | System | 0.5 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_336 | BRN-LAS_336-I3-1-4 | BRN-LAS_336-I3-1-4-4.2-System | LAS_336 | 4.2 | Configure the protection of input data through an automatic security policy or folder restrictions | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_336 | BRN-LAS_336-I3-1-4 | BRN-LAS_336-I3-1-4-4.3-System | LAS_336 | 4.3 | Configure user privileges to prevent the deletion or alteration of input data | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_336 | BRN-LAS_336-I3-1-4 | BRN-LAS_336-I3-1-4-4.4-System | LAS_336 | 4.4 | Test and document the configuration changes | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_336 | BRN-LAS_336-I3-1-4 | BRN-LAS_336-I3-1-4-4.5-System | LAS_336 | 4.5 | Update relevant SOP | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_336 | BRN-LAS_336-I4-1-5 | BRN-LAS_336-I4-1-5-5.1-System | LAS_336 | 5.1 | Define a secure and protected location to save the output records | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_336 | BRN-LAS_336-I4-1-5 | BRN-LAS_336-I4-1-5-5.2-System | LAS_336 | 5.2 | Test and document the manual workaround for saving output records | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_336 | BRN-LAS_336-I4-1-5 | BRN-LAS_336-I4-1-5-5.3-System | LAS_336 | 5.3 | Schedule a SW update to include autosave of output records | System | 0.5 | 0 | NO | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_336 | BRN-LAS_336-T2-1-6 | BRN-LAS_336-T2-1-6-6.1-System | LAS_336 | 6.1 | Change Control Management including impact assessment | System | 0.5 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_336 | BRN-LAS_336-T2-1-6 | BRN-LAS_336-T2-1-6-6.2-System | LAS_336 | 6.2 | Verify if Time Reference protection can be configured within the system | System | 0.5 | 0.5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_336 | BRN-LAS_336-T2-1-6 | BRN-LAS_336-T2-1-6-6.3-Generic | LAS_336 | 6.3 | If not possible, manage Date & Time protection through an approved procedure | Generic | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_336 | BRN-LAS_336-T2-1-6 | BRN-LAS_336-T2-1-6-6.4-System | LAS_336 | 6.4 | Test and document configuration changes | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_336 | BRN-LAS_336-T2-1-6 | BRN-LAS_336-T2-1-6-6.5-System | LAS_336 | 6.5 | Update relevant SOP | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_336 | BRN-LAS_336-T3-2-7 | BRN-LAS_336-T3-2-7-7.1-Generic | LAS_336 | 7.1 | Issue and approve a fully compliant Audit Trail Review Working Instruction | Generic | 0.5 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_336 | BRN-LAS_336-T3-2-7 | BRN-LAS_336-T3-2-7-7.2-System | LAS_336 | 7.2 | Execute Audit Trail Review Working Instruction: - perform Data Assessment for Electronic Records managed by the system - update Operational Method SOP (Methods/Instrument) - update test documentation | System | 0.5 | 2.5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_336 | BRN-LAS_336-T3-2-7 | BRN-LAS_336-T3-2-7-7.3-System | LAS_336 | 7.3 | Setup of periodic task | System | 0.2 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_336 | BRN-LAS_336-VD1-1-8 | BRN-LAS_336-VD1-1-8-8.1-System | LAS_336 | 8.1 | Review the Computer System Validation in place and identify the missing/incomplete validation documents or testing protocols | System | 1 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started | Validation Plan not present, Global CSV SOPs not applied., VR (called Qualifizierungsbericht, eng. Qualification report) not complete, URS document present but it is missing Functional Process Requirements, Access Control and Security Roles partially covered, no reference to regulatory rules (e.g. Annex11 coverage), Not present, partially covered in delivered vendor documentation, Risk Assessment not present, IQ/OQ has been identified. The level of detail is not consistent with DI expectations, i.e. Security/Integrity/Traceability verifications. Missing tests for documental checks (e.g. Users List, SOPs, etc.), functional checks (Part 11 and Annex 11 verifications), PQ protocol is not identified
BRN | BRN-LAS_336 | BRN-LAS_336-VD1-1-8 | BRN-LAS_336-VD1-1-8-8.2-System | LAS_336 | 8.2 | Issue and approve the missing validation documentation | System | 2 | 3 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_336 | BRN-LAS_336-VD1-1-8 | BRN-LAS_336-VD1-1-8-8.3-System | LAS_336 | 8.3 | Perform and document the missing/incomplete tests | System | 3 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_336 | BRN-LAS_336-VD1-1-8 | BRN-LAS_336-VD1-1-8-8.4-System | LAS_336 | 8.4 | Assure the Traceability of the testing with coded requirements against coded test and update the documentation accordingly | System | 2 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_337 | BRN-LAS_337-S3-3-1 | BRN-LAS_337-S3-3-1-1.1-Generic | LAS_337 | 1.1 | Issue and approve a Security SOP with proper PW security features according to best practices (length, complexity, expiring) | Generic | 1 | 5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_337 | BRN-LAS_337-S3-3-1 | BRN-LAS_337-S3-3-1-1.2-System | LAS_337 | 1.2 | Update all passwords according to the approved Security SOP | System | 1 | 0.1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_337 | BRN-LAS_337-S3-3-1 | BRN-LAS_337-S3-3-1-1.3-System | LAS_337 | 1.3 | Test and document the Password policies | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_337 | BRN-LAS_337-S4-2-2 | BRN-LAS_337-S4-2-2-2.1-System | LAS_337 | 2.1 | Issue a User List with the actual status of users | System | 0.1 | 0.5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_337 | BRN-LAS_337-S4-2-2 | BRN-LAS_337-S4-2-2-2.2-Generic | LAS_337 | 2.2 | Issue and approve a Periodic Review for User List | Generic | 0.1 | 0.5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_337 | BRN-LAS_337-S4-2-2 | BRN-LAS_337-S4-2-2-2.3-System | LAS_337 | 2.3 | Execute Periodic Review | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_337 | BRN-LAS_337-S4-2-2 | BRN-LAS_337-S4-2-2-2.4-System | LAS_337 | 2.4 | Setup of periodic task in relevant system | System | 0.2 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_337 | BRN-LAS_337-I2-1-3 | BRN-LAS_337-I2-1-3-3.1-System | LAS_337 | 3.1 | Change Control Management including impact assessment | System | 0.5 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_337 | BRN-LAS_337-I2-1-3 | BRN-LAS_337-I2-1-3-3.2-System | LAS_337 | 3.2 | Change permissions for users not authorized to modify data, preventing the deletion or alteration. | System | 0.5 | 0 | NO | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_337 | BRN-LAS_337-I2-1-3 | BRN-LAS_337-I2-1-3-3.3-System | LAS_337 | 3.3 | Test and document the configuration changes | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_337 | BRN-LAS_337-I2-1-3 | BRN-LAS_337-I2-1-3-3.4-System | LAS_337 | 3.4 | Update relevant SOP | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_337 | BRN-LAS_337-I3-1-4 | BRN-LAS_337-I3-1-4-4.1-System | LAS_337 | 4.1 | Change Control Management including impact assessment | System | 0.5 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_337 | BRN-LAS_337-I3-1-4 | BRN-LAS_337-I3-1-4-4.2-System | LAS_337 | 4.2 | Configure the protection of input data through an automatic security policy or folder restrictions | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_337 | BRN-LAS_337-I3-1-4 | BRN-LAS_337-I3-1-4-4.3-System | LAS_337 | 4.3 | Configure user privileges to prevent the deletion or alteration of input data | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_337 | BRN-LAS_337-I3-1-4 | BRN-LAS_337-I3-1-4-4.4-System | LAS_337 | 4.4 | Test and document the configuration changes | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_337 | BRN-LAS_337-I3-1-4 | BRN-LAS_337-I3-1-4-4.5-System | LAS_337 | 4.5 | Update relevant SOP | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_337 | BRN-LAS_337-I4-1-5 | BRN-LAS_337-I4-1-5-5.1-System | LAS_337 | 5.1 | Define a secure and protected location to save the output records | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_337 | BRN-LAS_337-I4-1-5 | BRN-LAS_337-I4-1-5-5.2-System | LAS_337 | 5.2 | Test and document the manual workaround for saving output records | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_337 | BRN-LAS_337-I4-1-5 | BRN-LAS_337-I4-1-5-5.3-System | LAS_337 | 5.3 | Schedule a SW update to include autosave of output records | System | 0.5 | 0 | NO | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_337 | BRN-LAS_337-T3-2-6 | BRN-LAS_337-T3-2-6-6.1-Generic | LAS_337 | 6.1 | Issue and approve a fully compliant Audit Trail Review Working Instruction | Generic | 0.5 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_337 | BRN-LAS_337-T3-2-6 | BRN-LAS_337-T3-2-6-6.2-System | LAS_337 | 6.2 | Execute Audit Trail Review Working Instruction: - perform Data Assessment for Electronic Records managed by the system - update Operational Method SOP (Methods/Instrument) - update test documentation | System | 0.5 | 2.5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_337 | BRN-LAS_337-T3-2-6 | BRN-LAS_337-T3-2-6-6.3-System | LAS_337 | 6.3 | Setup of periodic task | System | 0.2 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_337 | BRN-LAS_337-VD1-1-7 | BRN-LAS_337-VD1-1-7-7.1-System | LAS_337 | 7.1 | Review the Computer System Validation in place and identify the missing/incomplete validation documents or testing protocols | System | 1 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started | Validation Plan not present, Global CSV SOPs not applied., VR (called Qualifizierungsbericht, eng. Qualification report) not complete, URS document present but it is missing Functional Process Requirements, Access Control and Security Roles partially covered, no reference to regulatory rules (e.g. Annex11 coverage), Not present, partially covered in delivered vendor documentation, Risk Assessment not present, IQ/OQ has been identified. The level of detail is not consistent with DI expectations, i.e. Security/Integrity/Traceability verifications. Missing tests for documental checks (e.g. Users List, SOPs, etc.), functional checks (Part 11 and Annex 11 verifications), PQ protocol is not identified
BRN | BRN-LAS_337 | BRN-LAS_337-VD1-1-7 | BRN-LAS_337-VD1-1-7-7.2-System | LAS_337 | 7.2 | Issue and approve the missing validation documentation | System | 2 | 3 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_337 | BRN-LAS_337-VD1-1-7 | BRN-LAS_337-VD1-1-7-7.3-System | LAS_337 | 7.3 | Perform and document the missing/incomplete tests | System | 3 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_337 | BRN-LAS_337-VD1-1-7 | BRN-LAS_337-VD1-1-7-7.4-System | LAS_337 | 7.4 | Assure the Traceability of the testing with coded requirements against coded test and update the documentation accordingly | System | 2 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_338 | BRN-LAS_338-S3-3-1 | BRN-LAS_338-S3-3-1-1.1-Generic | LAS_338 | 1.1 | Issue and approve a Security SOP with proper PW security features according to best practices (length, complexity, expiring) | Generic | 1 | 5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_338 | BRN-LAS_338-S3-3-1 | BRN-LAS_338-S3-3-1-1.2-System | LAS_338 | 1.2 | Update all passwords according to the approved Security SOP | System | 1 | 0.1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_338 | BRN-LAS_338-S3-3-1 | BRN-LAS_338-S3-3-1-1.3-System | LAS_338 | 1.3 | Test and document the Password policies | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_338 | BRN-LAS_338-S4-2-2 | BRN-LAS_338-S4-2-2-2.1-System | LAS_338 | 2.1 | Issue a User List with the actual status of users | System | 0.1 | 0.5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_338 | BRN-LAS_338-S4-2-2 | BRN-LAS_338-S4-2-2-2.2-Generic | LAS_338 | 2.2 | Issue and approve a Periodic Review for User List | Generic | 0.1 | 0.5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_338 | BRN-LAS_338-S4-2-2 | BRN-LAS_338-S4-2-2-2.3-System | LAS_338 | 2.3 | Execute Periodic Review | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_338 | BRN-LAS_338-S4-2-2 | BRN-LAS_338-S4-2-2-2.4-System | LAS_338 | 2.4 | Setup of periodic task in relevant system | System | 0.2 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_338 | BRN-LAS_338-I2-1-3 | BRN-LAS_338-I2-1-3-3.1-System | LAS_338 | 3.1 | Change Control Management including impact assessment | System | 0.5 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_338 | BRN-LAS_338-I2-1-3 | BRN-LAS_338-I2-1-3-3.2-System | LAS_338 | 3.2 | Change permissions for users not authorized to modify data, preventing the deletion or alteration. | System | 0.5 | 0 | NO | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_338 | BRN-LAS_338-I2-1-3 | BRN-LAS_338-I2-1-3-3.3-System | LAS_338 | 3.3 | Test and document the configuration changes | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_338 | BRN-LAS_338-I2-1-3 | BRN-LAS_338-I2-1-3-3.4-System | LAS_338 | 3.4 | Update relevant SOP | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_338 | BRN-LAS_338-I3-1-4 | BRN-LAS_338-I3-1-4-4.1-System | LAS_338 | 4.1 | Change Control Management including impact assessment | System | 0.5 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_338 | BRN-LAS_338-I3-1-4 | BRN-LAS_338-I3-1-4-4.2-System | LAS_338 | 4.2 | Configure the protection of input data through an automatic security policy or folder restrictions | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_338 | BRN-LAS_338-I3-1-4 | BRN-LAS_338-I3-1-4-4.3-System | LAS_338 | 4.3 | Configure user privileges to prevent the deletion or alteration of input data | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_338 | BRN-LAS_338-I3-1-4 | BRN-LAS_338-I3-1-4-4.4-System | LAS_338 | 4.4 | Test and document the configuration changes | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_338 | BRN-LAS_338-I3-1-4 | BRN-LAS_338-I3-1-4-4.5-System | LAS_338 | 4.5 | Update relevant SOP | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_338 | BRN-LAS_338-I4-1-5 | BRN-LAS_338-I4-1-5-5.1-System | LAS_338 | 5.1 | Define a secure and protected location to save the output records | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_338 | BRN-LAS_338-I4-1-5 | BRN-LAS_338-I4-1-5-5.2-System | LAS_338 | 5.2 | Test and document the manual workaround for saving output records | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_338 | BRN-LAS_338-I4-1-5 | BRN-LAS_338-I4-1-5-5.3-System | LAS_338 | 5.3 | Schedule a SW update to include autosave of output records | System | 0.5 | 0 | NO | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_338 | BRN-LAS_338-T2-1-6 | BRN-LAS_338-T2-1-6-6.1-System | LAS_338 | 6.1 | Change Control Management including impact assessment | System | 0.5 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_338 | BRN-LAS_338-T2-1-6 | BRN-LAS_338-T2-1-6-6.2-System | LAS_338 | 6.2 | Verify if Time Reference protection can be configured within the system | System | 0.5 | 0.5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_338 | BRN-LAS_338-T2-1-6 | BRN-LAS_338-T2-1-6-6.3-Generic | LAS_338 | 6.3 | If not possible, manage Date & Time protection through an approved procedure | Generic | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_338 | BRN-LAS_338-T2-1-6 | BRN-LAS_338-T2-1-6-6.4-System | LAS_338 | 6.4 | Test and document configuration changes | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_338 | BRN-LAS_338-T2-1-6 | BRN-LAS_338-T2-1-6-6.5-System | LAS_338 | 6.5 | Update relevant SOP | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_338 | BRN-LAS_338-T3-2-7 | BRN-LAS_338-T3-2-7-7.1-Generic | LAS_338 | 7.1 | Issue and approve a fully compliant Audit Trail Review Working Instruction | Generic | 0.5 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_338 | BRN-LAS_338-T3-2-7 | BRN-LAS_338-T3-2-7-7.2-System | LAS_338 | 7.2 | Execute Audit Trail Review Working Instruction: - perform Data Assessment for Electronic Records managed by the system - update Operational Method SOP (Methods/Instrument) - update test documentation | System | 0.5 | 2.5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_338 | BRN-LAS_338-T3-2-7 | BRN-LAS_338-T3-2-7-7.3-System | LAS_338 | 7.3 | Setup of periodic task | System | 0.2 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_338 | BRN-LAS_338-VD1-1-8 | BRN-LAS_338-VD1-1-8-8.1-System | LAS_338 | 8.1 | Review the Computer System Validation in place and identify the missing/incomplete validation documents or testing protocols | System | 1 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started | Validation Plan has been identified, however it has been issued by the vendor and it is not covering the validation strategy regarding the Regulatory and ERES definition, Global CSV SOPs not applied., Traceability Matrix present, VR (called Qualifizierungsbericht, eng. Qualification report) not complete, URS document present but it is missing the ERES definition and reference to regulatory rules (e.g. Annex11 coverage), Not present, partially covered in delivered vendor documentation, RA is identified but does not cover the risk associated to Regulatory Requirements and ERES definition., IQ and OQ protocols identified, however the level of details is not consistent with DI expectations., PQ protocol is not identified
BRN | BRN-LAS_338 | BRN-LAS_338-VD1-1-8 | BRN-LAS_338-VD1-1-8-8.2-System | LAS_338 | 8.2 | Issue and approve the missing validation documentation | System | 2 | 3 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_338 | BRN-LAS_338-VD1-1-8 | BRN-LAS_338-VD1-1-8-8.3-System | LAS_338 | 8.3 | Perform and document the missing/incomplete tests | System | 3 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_338 | BRN-LAS_338-VD1-1-8 | BRN-LAS_338-VD1-1-8-8.4-System | LAS_338 | 8.4 | Assure the Traceability of the testing with coded requirements against coded test and update the documentation accordingly | System | 2 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_339 | BRN-LAS_339-S1-1-1 | BRN-LAS_339-S1-1-1-1.1-System | LAS_339 | 1.1 | Change Control Management including impact assessment | System | 0.5 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 30/06/2026 | To be started
BRN | BRN-LAS_339 | BRN-LAS_339-S1-1-1 | BRN-LAS_339-S1-1-1-1.2-System | LAS_339 | 1.2 | Create personal and unique accounts in system | System | 1 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 30/06/2026 | To be started
BRN | BRN-LAS_339 | BRN-LAS_339-S1-1-1 | BRN-LAS_339-S1-1-1-1.3-System | LAS_339 | 1.3 | Remove generic accounts from the system | System | 0.5 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 30/06/2026 | To be started
BRN | BRN-LAS_339 | BRN-LAS_339-S1-1-1 | BRN-LAS_339-S1-1-1-1.4-System | LAS_339 | 1.4 | Issue and approve an updated User List | System | 0.1 | 0.5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 30/06/2026 | To be started
BRN | BRN-LAS_339 | BRN-LAS_339-S1-1-1 | BRN-LAS_339-S1-1-1-1.5-System | LAS_339 | 1.5 | Update relevant SOPs and periodically review the User List according to procedure | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 30/06/2026 | To be started
BRN | BRN-LAS_339 | BRN-LAS_339-S2-2-2 | BRN-LAS_339-S2-2-2-2.1-System | LAS_339 | 2.1 | Change Control Management including impact assessment | System | 0.5 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 30/06/2026 | To be started
BRN | BRN-LAS_339 | BRN-LAS_339-S2-2-2 | BRN-LAS_339-S2-2-2-2.2-System | LAS_339 | 2.2 | Configure 3 user groups and define the role of each user | System | 1 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 30/06/2026 | To be started
BRN | BRN-LAS_339 | BRN-LAS_339-S2-2-2 | BRN-LAS_339-S2-2-2-2.3-System | LAS_339 | 2.3 | Configure user privileges according to a proper segregation of duties | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 30/06/2026 | To be started
BRN | BRN-LAS_339 | BRN-LAS_339-S2-2-2 | BRN-LAS_339-S2-2-2-2.4-System | LAS_339 | 2.4 | Test and document the configuration changes | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 30/06/2026 | To be started
BRN | BRN-LAS_339 | BRN-LAS_339-S2-2-2 | BRN-LAS_339-S2-2-2-2.5-System | LAS_339 | 2.5 | Update relevant SOP | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 30/06/2026 | To be started
BRN | BRN-LAS_339 | BRN-LAS_339-I2-1-3 | BRN-LAS_339-I2-1-3-3.1-System | LAS_339 | 3.1 | Change Control Management including impact assessment | System | 0.5 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 30/06/2026 | To be started
BRN | BRN-LAS_339 | BRN-LAS_339-I2-1-3 | BRN-LAS_339-I2-1-3-3.2-System | LAS_339 | 3.2 | Change permissions for users not authorized to modify data, preventing the deletion or alteration. | System | 0.5 | 0 | NO | LES Lab Support | Valeria Geraci | Dario Ruberto | 30/06/2026 | To be started
BRN | BRN-LAS_339 | BRN-LAS_339-I2-1-3 | BRN-LAS_339-I2-1-3-3.3-System | LAS_339 | 3.3 | Test and document the configuration changes | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 30/06/2026 | To be started
BRN | BRN-LAS_339 | BRN-LAS_339-I2-1-3 | BRN-LAS_339-I2-1-3-3.4-System | LAS_339 | 3.4 | Update relevant SOP | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 30/06/2026 | To be started
BRN | BRN-LAS_339 | BRN-LAS_339-I3-1-4 | BRN-LAS_339-I3-1-4-4.1-System | LAS_339 | 4.1 | Change Control Management including impact assessment | System | 0.5 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 30/06/2026 | To be started
BRN | BRN-LAS_339 | BRN-LAS_339-I3-1-4 | BRN-LAS_339-I3-1-4-4.2-System | LAS_339 | 4.2 | Configure the protection of input data through an automatic security policy or folder restrictions | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 30/06/2026 | To be started
BRN | BRN-LAS_339 | BRN-LAS_339-I3-1-4 | BRN-LAS_339-I3-1-4-4.3-System | LAS_339 | 4.3 | Configure user privileges to prevent the deletion or alteration of input data | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 30/06/2026 | To be started
BRN | BRN-LAS_339 | BRN-LAS_339-I3-1-4 | BRN-LAS_339-I3-1-4-4.4-System | LAS_339 | 4.4 | Test and document the configuration changes | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 30/06/2026 | To be started
BRN | BRN-LAS_339 | BRN-LAS_339-I3-1-4 | BRN-LAS_339-I3-1-4-4.5-System | LAS_339 | 4.5 | Update relevant SOP | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 30/06/2026 | To be started
BRN | BRN-LAS_339 | BRN-LAS_339-I4-1-5 | BRN-LAS_339-I4-1-5-5.1-System | LAS_339 | 5.1 | Define a secure and protected location to save the output records | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 30/06/2026 | To be started
BRN | BRN-LAS_339 | BRN-LAS_339-I4-1-5 | BRN-LAS_339-I4-1-5-5.2-System | LAS_339 | 5.2 | Test and document the manual workaround for saving output records | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 30/06/2026 | To be started
BRN | BRN-LAS_339 | BRN-LAS_339-I4-1-5 | BRN-LAS_339-I4-1-5-5.3-System | LAS_339 | 5.3 | Schedule a SW update to include autosave of output records | System | 0.5 | 0 | NO | LES Lab Support | Valeria Geraci | Dario Ruberto | 30/06/2026 | To be started
BRN | BRN-LAS_339 | BRN-LAS_339-T2-1-6 | BRN-LAS_339-T2-1-6-6.1-System | LAS_339 | 6.1 | Change Control Management including impact assessment | System | 0.5 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 30/06/2026 | To be started
BRN | BRN-LAS_339 | BRN-LAS_339-T2-1-6 | BRN-LAS_339-T2-1-6-6.2-System | LAS_339 | 6.2 | Verify if Time Reference protection can be configured within the system | System | 0.5 | 0.5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 30/06/2026 | To be started
BRN | BRN-LAS_339 | BRN-LAS_339-T2-1-6 | BRN-LAS_339-T2-1-6-6.3-Generic | LAS_339 | 6.3 | If not possible, manage Date & Time protection through an approved procedure | Generic | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 30/06/2026 | To be started
BRN | BRN-LAS_339 | BRN-LAS_339-T2-1-6 | BRN-LAS_339-T2-1-6-6.4-System | LAS_339 | 6.4 | Test and document configuration changes | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 30/06/2026 | To be started
BRN | BRN-LAS_339 | BRN-LAS_339-T2-1-6 | BRN-LAS_339-T2-1-6-6.5-System | LAS_339 | 6.5 | Update relevant SOP | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 30/06/2026 | To be started
BRN | BRN-LAS_339 | BRN-LAS_339-T3-2-7 | BRN-LAS_339-T3-2-7-7.1-Generic | LAS_339 | 7.1 | Issue and approve a fully compliant Audit Trail Review Working Instruction | Generic | 0.5 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 30/06/2026 | To be started
BRN | BRN-LAS_339 | BRN-LAS_339-T3-2-7 | BRN-LAS_339-T3-2-7-7.2-System | LAS_339 | 7.2 | Execute Audit Trail Review Working Instruction: - perform Data Assessment for Electronic Records managed by the system - update Operational Method SOP (Methods/Instrument) - update test documentation | System | 0.5 | 2.5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 30/06/2026 | To be started
BRN | BRN-LAS_339 | BRN-LAS_339-T3-2-7 | BRN-LAS_339-T3-2-7-7.3-System | LAS_339 | 7.3 | Setup of periodic task | System | 0.2 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 30/06/2026 | To be started
BRN | BRN-LAS_339 | BRN-LAS_339-VD1-1-8 | BRN-LAS_339-VD1-1-8-8.1-System | LAS_339 | 8.1 | Review the Computer System Validation in place and identify the missing/incomplete validation documents or testing protocols | System | 1 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 30/06/2026 | To be started | Validation Plan has been identified, however it has been issued by the vendor and it is not covering the validation strategy regarding the Regulatory and ERES definition, Global CSV SOPs not applied., Traceability Matrix present, VR (called Qualifizierungsbericht, eng. Qualification report) not complete, URS document present but it is missing the ERES definition and reference to regulatory rules (e.g. Annex11 coverage), Not present, partially covered in delivered vendor documentation, RA is identified but does not cover the risk associated to Regulatory Requirements and ERES definition., IQ and OQ protocols identified, however the level of details is not consistent with DI expectations., PQ protocol is not identified
BRN | BRN-LAS_339 | BRN-LAS_339-VD1-1-8 | BRN-LAS_339-VD1-1-8-8.2-System | LAS_339 | 8.2 | Issue and approve the missing validation documentation | System | 2 | 3 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 30/06/2026 | To be started
BRN | BRN-LAS_339 | BRN-LAS_339-VD1-1-8 | BRN-LAS_339-VD1-1-8-8.3-System | LAS_339 | 8.3 | Perform and document the missing/incomplete tests | System | 3 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 30/06/2026 | To be started
BRN | BRN-LAS_339 | BRN-LAS_339-VD1-1-8 | BRN-LAS_339-VD1-1-8-8.4-System | LAS_339 | 8.4 | Assure the Traceability of the testing with coded requirements against coded test and update the documentation accordingly | System | 2 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 30/06/2026 | To be started
BRN | BRN-LAS_340 | BRN-LAS_340-S1-1-1 | BRN-LAS_340-S1-1-1-1.1-System | LAS_340 | 1.1 | Change Control Management including impact assessment | System | 0.5 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 30/06/2026 | To be started
BRN | BRN-LAS_340 | BRN-LAS_340-S1-1-1 | BRN-LAS_340-S1-1-1-1.2-System | LAS_340 | 1.2 | Create personal and unique accounts in system | System | 1 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 30/06/2026 | To be started
BRN | BRN-LAS_340 | BRN-LAS_340-S1-1-1 | BRN-LAS_340-S1-1-1-1.3-System | LAS_340 | 1.3 | Remove generic accounts from the system | System | 0.5 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 30/06/2026 | To be started
BRN | BRN-LAS_340 | BRN-LAS_340-S1-1-1 | BRN-LAS_340-S1-1-1-1.4-System | LAS_340 | 1.4 | Issue and approve an updated User List | System | 0.1 | 0.5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 30/06/2026 | To be started
BRN | BRN-LAS_340 | BRN-LAS_340-S1-1-1 | BRN-LAS_340-S1-1-1-1.5-System | LAS_340 | 1.5 | Update relevant SOPs and periodically review the User List according to procedure | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 30/06/2026 | To be started
BRN | BRN-LAS_340 | BRN-LAS_340-S2-2-2 | BRN-LAS_340-S2-2-2-2.1-System | LAS_340 | 2.1 | Change Control Management including impact assessment | System | 0.5 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 30/06/2026 | To be started
BRN | BRN-LAS_340 | BRN-LAS_340-S2-2-2 | BRN-LAS_340-S2-2-2-2.2-System | LAS_340 | 2.2 | Configure 3 user groups and define the role of each user | System | 1 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 30/06/2026 | To be started
BRN | BRN-LAS_340 | BRN-LAS_340-S2-2-2 | BRN-LAS_340-S2-2-2-2.3-System | LAS_340 | 2.3 | Configure user privileges according to a proper segregation of duties | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 30/06/2026 | To be started
BRN | BRN-LAS_340 | BRN-LAS_340-S2-2-2 | BRN-LAS_340-S2-2-2-2.4-System | LAS_340 | 2.4 | Test and document the configuration changes | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 30/06/2026 | To be started
BRN | BRN-LAS_340 | BRN-LAS_340-S2-2-2 | BRN-LAS_340-S2-2-2-2.5-System | LAS_340 | 2.5 | Update relevant SOP | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 30/06/2026 | To be started
BRN | BRN-LAS_340 | BRN-LAS_340-I2-1-3 | BRN-LAS_340-I2-1-3-3.1-System | LAS_340 | 3.1 | Change Control Management including impact assessment | System | 0.5 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 30/06/2026 | To be started
BRN | BRN-LAS_340 | BRN-LAS_340-I2-1-3 | BRN-LAS_340-I2-1-3-3.2-System | LAS_340 | 3.2 | Change permissions for users not authorized to modify data, preventing the deletion or alteration. | System | 0.5 | 0 | NO | LES Lab Support | Valeria Geraci | Dario Ruberto | 30/06/2026 | To be started
BRN | BRN-LAS_340 | BRN-LAS_340-I2-1-3 | BRN-LAS_340-I2-1-3-3.3-System | LAS_340 | 3.3 | Test and document the configuration changes | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 30/06/2026 | To be started
BRN | BRN-LAS_340 | BRN-LAS_340-I2-1-3 | BRN-LAS_340-I2-1-3-3.4-System | LAS_340 | 3.4 | Update relevant SOP | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 30/06/2026 | To be started
BRN | BRN-LAS_340 | BRN-LAS_340-I3-1-4 | BRN-LAS_340-I3-1-4-4.1-System | LAS_340 | 4.1 | Change Control Management including impact assessment | System | 0.5 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 30/06/2026 | To be started
BRN | BRN-LAS_340 | BRN-LAS_340-I3-1-4 | BRN-LAS_340-I3-1-4-4.2-System | LAS_340 | 4.2 | Configure the protection of input data through an automatic security policy or folder restrictions | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 30/06/2026 | To be started
BRN | BRN-LAS_340 | BRN-LAS_340-I3-1-4 | BRN-LAS_340-I3-1-4-4.3-System | LAS_340 | 4.3 | Configure user privileges to prevent the deletion or alteration of input data | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 30/06/2026 | To be started
BRN | BRN-LAS_340 | BRN-LAS_340-I3-1-4 | BRN-LAS_340-I3-1-4-4.4-System | LAS_340 | 4.4 | Test and document the configuration changes | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 30/06/2026 | To be started
BRN | BRN-LAS_340 | BRN-LAS_340-I3-1-4 | BRN-LAS_340-I3-1-4-4.5-System | LAS_340 | 4.5 | Update relevant SOP | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 30/06/2026 | To be started
BRN | BRN-LAS_340 | BRN-LAS_340-I4-1-5 | BRN-LAS_340-I4-1-5-5.1-System | LAS_340 | 5.1 | Define a secure and protected location to save the output records | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 30/06/2026 | To be started
BRN | BRN-LAS_340 | BRN-LAS_340-I4-1-5 | BRN-LAS_340-I4-1-5-5.2-System | LAS_340 | 5.2 | Test and document the manual workaround for saving output records | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 30/06/2026 | To be started
BRN | BRN-LAS_340 | BRN-LAS_340-I4-1-5 | BRN-LAS_340-I4-1-5-5.3-System | LAS_340 | 5.3 | Schedule a SW update to include autosave of output records | System | 0.5 | 0 | NO | LES Lab Support | Valeria Geraci | Dario Ruberto | 30/06/2026 | To be started
BRN | BRN-LAS_340 | BRN-LAS_340-T2-1-6 | BRN-LAS_340-T2-1-6-6.1-System | LAS_340 | 6.1 | Change Control Management including impact assessment | System | 0.5 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 30/06/2026 | To be started
BRN | BRN-LAS_340 | BRN-LAS_340-T2-1-6 | BRN-LAS_340-T2-1-6-6.2-System | LAS_340 | 6.2 | Verify if Time Reference protection can be configured within the system | System | 0.5 | 0.5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 30/06/2026 | To be started
BRN | BRN-LAS_340 | BRN-LAS_340-T2-1-6 | BRN-LAS_340-T2-1-6-6.3-Generic | LAS_340 | 6.3 | If not possible, manage Date & Time protection through an approved procedure | Generic | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 30/06/2026 | To be started
BRN | BRN-LAS_340 | BRN-LAS_340-T2-1-6 | BRN-LAS_340-T2-1-6-6.4-System | LAS_340 | 6.4 | Test and document configuration changes | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 30/06/2026 | To be started
BRN | BRN-LAS_340 | BRN-LAS_340-T2-1-6 | BRN-LAS_340-T2-1-6-6.5-System | LAS_340 | 6.5 | Update relevant SOP | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 30/06/2026 | To be started
BRN | BRN-LAS_340 | BRN-LAS_340-T3-2-7 | BRN-LAS_340-T3-2-7-7.1-Generic | LAS_340 | 7.1 | Issue and approve a fully compliant Audit Trail Review Working Instruction | Generic | 0.5 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 30/06/2026 | To be started
BRN | BRN-LAS_340 | BRN-LAS_340-T3-2-7 | BRN-LAS_340-T3-2-7-7.2-System | LAS_340 | 7.2 | Execute Audit Trail Review Working Instruction: - perform Data Assessment for Electronic Records managed by the system - update Operational Method SOP (Methods/Instrument) - update test documentation | System | 0.5 | 2.5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 30/06/2026 | To be started
BRN | BRN-LAS_340 | BRN-LAS_340-T3-2-7 | BRN-LAS_340-T3-2-7-7.3-System | LAS_340 | 7.3 | Setup of periodic task | System | 0.2 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 30/06/2026 | To be started
BRN | BRN-LAS_340 | BRN-LAS_340-VD1-1-8 | BRN-LAS_340-VD1-1-8-8.1-System | LAS_340 | 8.1 | Review the Computer System Validation in place and identify the missing/incomplete validation documents or testing protocols | System | 1 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 30/06/2026 | To be started | Validation Plan has been identified, however it has been issued by the vendor and it is not covering the validation strategy regarding the Regulatory and ERES definition, Global CSV SOPs not applied., Traceability Matrix present, VR (called Qualifizierungsbericht, eng. Qualification report) not complete, URS document present but it is missing the ERES definition and reference to regulatory rules (e.g. Annex11 coverage), Not present, partially covered in delivered vendor documentation, RA is identified but does not cover the risk associated to Regulatory Requirements and ERES definition., IQ and OQ protocols identified, however the level of details is not consistent with DI expectations., PQ protocol is not identified
BRN | BRN-LAS_340 | BRN-LAS_340-VD1-1-8 | BRN-LAS_340-VD1-1-8-8.2-System | LAS_340 | 8.2 | Issue and approve the missing validation documentation | System | 2 | 3 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 30/06/2026 | To be started
BRN | BRN-LAS_340 | BRN-LAS_340-VD1-1-8 | BRN-LAS_340-VD1-1-8-8.3-System | LAS_340 | 8.3 | Perform and document the missing/incomplete tests | System | 3 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 30/06/2026 | To be started
BRN | BRN-LAS_340 | BRN-LAS_340-VD1-1-8 | BRN-LAS_340-VD1-1-8-8.4-System | LAS_340 | 8.4 | Assure the Traceability of the testing with coded requirements against coded test and update the documentation accordingly | System | 2 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 30/06/2026 | To be started
BRN | BRN-LAS_342 | BRN-LAS_342-S1-2-1 | BRN-LAS_342-S1-2-1-1.1-System | LAS_342 | 1.1 | Change Control Management including impact assessment | System | 0.5 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_342 | BRN-LAS_342-S1-2-1 | BRN-LAS_342-S1-2-1-1.2-System | LAS_342 | 1.2 | Update the application SW in order to configure unique and personal accounts. If it is not possible to configure personal account within application SW, implement a proper user management within OS accounts | System | 3 | 3 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_342 | BRN-LAS_342-S1-2-1 | BRN-LAS_342-S1-2-1-1.3-System | LAS_342 | 1.3 | Test and document the configuration changes or procedural changes | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_342 | BRN-LAS_342-S1-2-1 | BRN-LAS_342-S1-2-1-1.4-System | LAS_342 | 1.4 | Issue and approve a User List | System | 0.1 | 0.5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_342 | BRN-LAS_342-S1-2-1 | BRN-LAS_342-S1-2-1-1.5-System | LAS_342 | 1.5 | Update relevant SOPs and periodically review the User List according to procedure | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_342 | BRN-LAS_342-S2-3-2 | BRN-LAS_342-S2-3-2-2.1-System | LAS_342 | 2.1 | Change Control Management including impact assessment | System | 2 | 3 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_342 | BRN-LAS_342-S2-3-2 | BRN-LAS_342-S2-3-2-2.2-System | LAS_342 | 2.2 | Configure 3 user groups and define the role of each user | System | 1 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_342 | BRN-LAS_342-S2-3-2 | BRN-LAS_342-S2-3-2-2.3-System | LAS_342 | 2.3 | Configure user privileges according to a proper segregation of duties | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_342 | BRN-LAS_342-S2-3-2 | BRN-LAS_342-S2-3-2-2.4-System | LAS_342 | 2.4 | Test and document the configuration changes | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_342 | BRN-LAS_342-S2-3-2 | BRN-LAS_342-S2-3-2-2.5-System | LAS_342 | 2.5 | Update relevant SOP | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_342 | BRN-LAS_342-S3-4-3 | BRN-LAS_342-S3-4-3-3.1-Generic | LAS_342 | 3.1 | Issue and approve a Security SOP with proper PW security features according to best practices (length, complexity, expiring) | Generic | 1 | 5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_342 | BRN-LAS_342-S3-4-3 | BRN-LAS_342-S3-4-3-3.2-System | LAS_342 | 3.2 | Update all passwords according to the approved Security SOP | System | 1 | 0.1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_342 | BRN-LAS_342-S3-4-3 | BRN-LAS_342-S3-4-3-3.3-System | LAS_342 | 3.3 | Test and document the Password policies | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_342 | BRN-LAS_342-S4-3-4 | BRN-LAS_342-S4-3-4-4.1-System | LAS_342 | 4.1 | Issue a User List with the actual status of users | System | 0.1 | 0.5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_342 | BRN-LAS_342-S4-3-4 | BRN-LAS_342-S4-3-4-4.2-Generic | LAS_342 | 4.2 | Issue and approve a Periodic Review for User List | Generic | 0.1 | 0.5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_342 | BRN-LAS_342-S4-3-4 | BRN-LAS_342-S4-3-4-4.3-System | LAS_342 | 4.3 | Execute Periodic Review | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_342 | BRN-LAS_342-S4-3-4 | BRN-LAS_342-S4-3-4-4.4-System | LAS_342 | 4.4 | Setup of periodic task in relevant system | System | 0.2 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_342 | BRN-LAS_342-I1-2-5 | BRN-LAS_342-I1-2-5-5.1-System | LAS_342 | 5.1 | Change Control Management including impact assessment | System | 0.5 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_342 | BRN-LAS_342-I1-2-5 | BRN-LAS_342-I1-2-5-5.2-System | LAS_342 | 5.2 | Implement a process of automatic data backup | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_342 | BRN-LAS_342-I1-2-5 | BRN-LAS_342-I1-2-5-5.3-Generic | LAS_342 | 5.3 | If automatic backup its not possible, document manual backups of system data with a proper frequency to be defined in a dedicated procedure | Generic | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_342 | BRN-LAS_342-I1-2-5 | BRN-LAS_342-I1-2-5-5.4-System | LAS_342 | 5.4 | Test and document the implemented changes | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_342 | BRN-LAS_342-I1-2-5 | BRN-LAS_342-I1-2-5-5.5-System | LAS_342 | 5.5 | Update relevant SOP | System | 0.2 | 0.2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_342 | BRN-LAS_342-I3-2-6 | BRN-LAS_342-I3-2-6-6.1-System | LAS_342 | 6.1 | Change Control Management including impact assessment | System | 0.5 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_342 | BRN-LAS_342-I3-2-6 | BRN-LAS_342-I3-2-6-6.2-System | LAS_342 | 6.2 | Configure the protection of input data through an automatic security policy or folder restrictions | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_342 | BRN-LAS_342-I3-2-6 | BRN-LAS_342-I3-2-6-6.3-System | LAS_342 | 6.3 | Configure user privileges to prevent the deletion or alteration of input data | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_342 | BRN-LAS_342-I3-2-6 | BRN-LAS_342-I3-2-6-6.4-System | LAS_342 | 6.4 | Test and document the configuration changes | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_342 | BRN-LAS_342-I3-2-6 | BRN-LAS_342-I3-2-6-6.5-System | LAS_342 | 6.5 | Update relevant SOP | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_342 | BRN-LAS_342-T1-2-7 | BRN-LAS_342-T1-2-7-7.1-System | LAS_342 | 7.1 | Change Control Management including impact assessment | System | 0.5 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_342 | BRN-LAS_342-T1-2-7 | BRN-LAS_342-T1-2-7-7.2-System | LAS_342 | 7.2 | Update Audit Trail functionality in order to track and record modifications to ER | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_342 | BRN-LAS_342-T1-2-7 | BRN-LAS_342-T1-2-7-7.3-Generic | LAS_342 | 7.3 | If Audit Trail is not compliant (e.g. does not track modifications to ER), implement a paper based management of system regulated input records (i.e. methods) with the following paper procedures: -user access log -verification log to be used by the Users before launching a method -traceability log to be used by the system administrators when changing a method | Generic | 2 | 3 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_342 | BRN-LAS_342-T1-2-7 | BRN-LAS_342-T1-2-7-7.4-System | LAS_342 | 7.4 | Test and document that Audit Trail is fully compliant or, in case of paper Audit Trail, that the personnel is trained to use it | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_342 | BRN-LAS_342-T1-2-7 | BRN-LAS_342-T1-2-7-7.5-System | LAS_342 | 7.5 | Update relevant SOP | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_342 | BRN-LAS_342-T2-2-8 | BRN-LAS_342-T2-2-8-8.1-System | LAS_342 | 8.1 | Change Control Management including impact assessment | System | 0.5 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_342 | BRN-LAS_342-T2-2-8 | BRN-LAS_342-T2-2-8-8.2-System | LAS_342 | 8.2 | Verify if Time Reference protection can be configured within the system | System | 0.5 | 0.5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_342 | BRN-LAS_342-T2-2-8 | BRN-LAS_342-T2-2-8-8.3-Generic | LAS_342 | 8.3 | If not possible, manage Date & Time protection through an approved procedure | Generic | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_342 | BRN-LAS_342-T2-2-8 | BRN-LAS_342-T2-2-8-8.4-System | LAS_342 | 8.4 | Test and document configuration changes | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_342 | BRN-LAS_342-T2-2-8 | BRN-LAS_342-T2-2-8-8.5-System | LAS_342 | 8.5 | Update relevant SOP | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_342 | BRN-LAS_342-T3-3-9 | BRN-LAS_342-T3-3-9-9.1-Generic | LAS_342 | 9.1 | If there is no Audit Trail Process fully compliant, issue and approve a fully compliant Audit Trail Review Working Instruction | Generic | 1 | 3 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_342 | BRN-LAS_342-T3-3-9 | BRN-LAS_342-T3-3-9-9.2-System | LAS_342 | 9.2 | Execute Audit Trail Review Working Instruction: - perform Data Assessment for Electronic Records managed by the system - update Operational Method SOP (Methods/Instrument) - update test documentation | System | 0.5 | 2.5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_342 | BRN-LAS_342-T3-3-9 | BRN-LAS_342-T3-3-9-9.3-System | LAS_342 | 9.3 | Setup of periodic task | System | 0.2 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_342 | BRN-LAS_342-VD1-2-10 | BRN-LAS_342-VD1-2-10-10.1-System | LAS_342 | 10.1 | Review the Computer System Validation in place and identify the missing/incomplete validation documents or testing protocols | System | 1 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started | Validation Plan has been identified, however it has been issued by the vendor and it is not covering the validation strategy regarding the Regulatory and ERES definition, Global CSV SOPs not applied., Traceability Matrix present, VR (called Qualifizierungsbericht, eng. Qualification report) not complete, URS document present but it is missing the ERES definition and reference to regulatory rules (e.g. Annex11 coverage), Not present, partially covered in delivered vendor documentation, RA is identified but does not cover the risk associated to Regulatory Requirements and ERES definition., IQ and OQ protocols identified, however the level of details is not consistent with DI expectations., PQ protocol is not identified
BRN | BRN-LAS_342 | BRN-LAS_342-VD1-2-10 | BRN-LAS_342-VD1-2-10-10.2-System | LAS_342 | 10.2 | Issue and approve the missing validation documentation | System | 2 | 3 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_342 | BRN-LAS_342-VD1-2-10 | BRN-LAS_342-VD1-2-10-10.3-System | LAS_342 | 10.3 | Perform and document the missing/incomplete tests | System | 3 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_342 | BRN-LAS_342-VD1-2-10 | BRN-LAS_342-VD1-2-10-10.4-System | LAS_342 | 10.4 | Assure the Traceability of the testing with coded requirements against coded test and update the documentation accordingly | System | 2 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_348 | BRN-LAS_348-S3-4-1 | BRN-LAS_348-S3-4-1-1.1-System | LAS_348 | 1.1 | Investigate with the supplier if it is possible to upgrade the software to grant proper security features for user access | System | 1 | 0 | NO | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_348 | BRN-LAS_348-S3-4-1 | BRN-LAS_348-S3-4-1-1.2-Generic | LAS_348 | 1.2 | Define the Password features in an approved procedure | Generic | 1 | 3 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_348 | BRN-LAS_348-S3-4-1 | BRN-LAS_348-S3-4-1-1.3-System | LAS_348 | 1.3 | Personnel training to access the system | System | 0.5 | 0.5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_348 | BRN-LAS_348-S3-4-1 | BRN-LAS_348-S3-4-1-1.4-System | LAS_348 | 1.4 | Update relevant SOP | System | 0.2 | 0.2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_348 | BRN-LAS_348-S4-3-2 | BRN-LAS_348-S4-3-2-2.1-System | LAS_348 | 2.1 | Issue a User List with the actual status of users | System | 0.1 | 0.5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_348 | BRN-LAS_348-S4-3-2 | BRN-LAS_348-S4-3-2-2.2-Generic | LAS_348 | 2.2 | Issue and approve a Periodic Review for User List | Generic | 0.1 | 0.5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_348 | BRN-LAS_348-S4-3-2 | BRN-LAS_348-S4-3-2-2.3-System | LAS_348 | 2.3 | Execute Periodic Review | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_348 | BRN-LAS_348-S4-3-2 | BRN-LAS_348-S4-3-2-2.4-System | LAS_348 | 2.4 | Setup of periodic task in relevant system | System | 0.2 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_348 | BRN-LAS_348-I1-2-3 | BRN-LAS_348-I1-2-3-3.1-System | LAS_348 | 3.1 | Change Control Management including impact assessment | System | 0.5 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_348 | BRN-LAS_348-I1-2-3 | BRN-LAS_348-I1-2-3-3.2-System | LAS_348 | 3.2 | Implement a process of automatic data backup | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_348 | BRN-LAS_348-I1-2-3 | BRN-LAS_348-I1-2-3-3.3-Generic | LAS_348 | 3.3 | If automatic backup its not possible, document manual backups of system data with a proper frequency to be defined in a dedicated procedure | Generic | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_348 | BRN-LAS_348-I1-2-3 | BRN-LAS_348-I1-2-3-3.4-System | LAS_348 | 3.4 | Test and document the implemented changes | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_348 | BRN-LAS_348-I1-2-3 | BRN-LAS_348-I1-2-3-3.5-System | LAS_348 | 3.5 | Update relevant SOP | System | 0.2 | 0.2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_348 | BRN-LAS_348-I3-2-4 | BRN-LAS_348-I3-2-4-4.1-System | LAS_348 | 4.1 | Change Control Management including impact assessment | System | 0.5 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_348 | BRN-LAS_348-I3-2-4 | BRN-LAS_348-I3-2-4-4.2-System | LAS_348 | 4.2 | Configure the protection of input data through an automatic security policy or folder restrictions | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_348 | BRN-LAS_348-I3-2-4 | BRN-LAS_348-I3-2-4-4.3-System | LAS_348 | 4.3 | Configure user privileges to prevent the deletion or alteration of input data | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_348 | BRN-LAS_348-I3-2-4 | BRN-LAS_348-I3-2-4-4.4-System | LAS_348 | 4.4 | Test and document the configuration changes | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_348 | BRN-LAS_348-I3-2-4 | BRN-LAS_348-I3-2-4-4.5-System | LAS_348 | 4.5 | Update relevant SOP | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_348 | BRN-LAS_348-T1-2-5 | BRN-LAS_348-T1-2-5-5.1-System | LAS_348 | 5.1 | Change Control Management including impact assessment | System | 0.5 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_348 | BRN-LAS_348-T1-2-5 | BRN-LAS_348-T1-2-5-5.2-System | LAS_348 | 5.2 | Update Audit Trail functionality in order to track and record modifications to ER | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_348 | BRN-LAS_348-T1-2-5 | BRN-LAS_348-T1-2-5-5.3-Generic | LAS_348 | 5.3 | If Audit Trail is not compliant (e.g. does not track modifications to ER), implement a paper based management of system regulated input records (i.e. methods) with the following paper procedures: -user access log -verification log to be used by the Users before launching a method -traceability log to be used by the system administrators when changing a method | Generic | 2 | 3 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_348 | BRN-LAS_348-T1-2-5 | BRN-LAS_348-T1-2-5-5.4-System | LAS_348 | 5.4 | Test and document that Audit Trail is fully compliant or, in case of paper Audit Trail, that the personnel is trained to use it | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_348 | BRN-LAS_348-T1-2-5 | BRN-LAS_348-T1-2-5-5.5-System | LAS_348 | 5.5 | Update relevant SOP | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_348 | BRN-LAS_348-T2-2-6 | BRN-LAS_348-T2-2-6-6.1-System | LAS_348 | 6.1 | Change Control Management including impact assessment | System | 0.5 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_348 | BRN-LAS_348-T2-2-6 | BRN-LAS_348-T2-2-6-6.2-System | LAS_348 | 6.2 | Verify if Time Reference protection can be configured within the system | System | 0.5 | 0.5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_348 | BRN-LAS_348-T2-2-6 | BRN-LAS_348-T2-2-6-6.3-Generic | LAS_348 | 6.3 | If not possible, manage Date & Time protection through an approved procedure | Generic | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_348 | BRN-LAS_348-T2-2-6 | BRN-LAS_348-T2-2-6-6.4-System | LAS_348 | 6.4 | Test and document configuration changes | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_348 | BRN-LAS_348-T2-2-6 | BRN-LAS_348-T2-2-6-6.5-System | LAS_348 | 6.5 | Update relevant SOP | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_348 | BRN-LAS_348-T3-3-7 | BRN-LAS_348-T3-3-7-7.1-Generic | LAS_348 | 7.1 | Issue and approve a fully compliant Audit Trail Review Working Instruction | Generic | 0.5 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_348 | BRN-LAS_348-T3-3-7 | BRN-LAS_348-T3-3-7-7.2-System | LAS_348 | 7.2 | Execute Audit Trail Review Working Instruction: - perform Data Assessment for Electronic Records managed by the system - update Operational Method SOP (Methods/Instrument) - update test documentation | System | 0.5 | 2.5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_348 | BRN-LAS_348-T3-3-7 | BRN-LAS_348-T3-3-7-7.3-System | LAS_348 | 7.3 | Setup of periodic task | System | 0.2 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_348 | BRN-LAS_348-T4-3-8 | BRN-LAS_348-T4-3-8-8.1-System | LAS_348 | 8.1 | Implement a process of automatic data transfer | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_348 | BRN-LAS_348-T4-3-8 | BRN-LAS_348-T4-3-8-8.2-Generic | LAS_348 | 8.2 | If automatic backup its not possible, document manual transfers of system data with a proper frequency to be defined in a dedicated procedure | Generic | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_348 | BRN-LAS_348-T4-3-8 | BRN-LAS_348-T4-3-8-8.3-System | LAS_348 | 8.3 | Test and document the implemented changes | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_348 | BRN-LAS_348-T4-3-8 | BRN-LAS_348-T4-3-8-8.4-System | LAS_348 | 8.4 | Update relevant SOP | System | 0.2 | 0.2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_348 | BRN-LAS_348-VD1-2-9 | BRN-LAS_348-VD1-2-9-9.1-System | LAS_348 | 9.1 | Review the Computer System Validation in place and identify the missing/incomplete validation documents or testing protocols | System | 1 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started | Validation Plan not present, Traceability Matrix present, VR (called Qualifizierungsbericht, eng. Qualification report) does not address the procedures., URS document present but it is missing Functional Process Requirements, Access Control and Security Roles partially covered, no reference to regulatory rules (e.g. Annex11 coverage), Configuration Specification not identified., RA is identified but does not cover the risk associated to Regulatory Requirements and ERES definition., IQ/OQ has been identified, but the level of detail is not consistent with DI expectations, i.e. Security/Integrity/Traceability verifications. Missing tests for documental checks (e.g. Users List, SOPs, etc.), functional checks (Part 11 and Annex 11 verifications), PQ protocol is not identified
BRN | BRN-LAS_348 | BRN-LAS_348-VD1-2-9 | BRN-LAS_348-VD1-2-9-9.2-System | LAS_348 | 9.2 | Issue and approve the missing validation documentation | System | 2 | 3 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_348 | BRN-LAS_348-VD1-2-9 | BRN-LAS_348-VD1-2-9-9.3-System | LAS_348 | 9.3 | Perform and document the missing/incomplete tests | System | 3 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_348 | BRN-LAS_348-VD1-2-9 | BRN-LAS_348-VD1-2-9-9.4-System | LAS_348 | 9.4 | Assure the Traceability of the testing with coded requirements against coded test and update the documentation accordingly | System | 2 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 2027-06-30 | To be started
BRN | BRN-LAS_354 | BRN-LAS_354-S4-2-1 | BRN-LAS_354-S4-2-1-1.1-System | LAS_354 | 1.1 | Issue a User List with the actual status of users | System | 0.1 | 0.5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 30/04/2025 | To be started
BRN | BRN-LAS_354 | BRN-LAS_354-S4-2-1 | BRN-LAS_354-S4-2-1-1.2-Generic | LAS_354 | 1.2 | Issue and approve a Periodic Review for User List | Generic | 0.1 | 0.5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 30/04/2025 | To be started
BRN | BRN-LAS_354 | BRN-LAS_354-S4-2-1 | BRN-LAS_354-S4-2-1-1.3-System | LAS_354 | 1.3 | Execute Periodic Review | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 30/04/2025 | To be started
BRN | BRN-LAS_354 | BRN-LAS_354-S4-2-1 | BRN-LAS_354-S4-2-1-1.4-System | LAS_354 | 1.4 | Setup of periodic task in relevant system | System | 0.2 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 30/04/2025 | To be started
BRN | BRN-LAS_354 | BRN-LAS_354-I1-1-2 | BRN-LAS_354-I1-1-2-2.1-System | LAS_354 | 2.1 | Change Control Management including impact assessment | System | 0.5 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 30/04/2025 | To be started
BRN | BRN-LAS_354 | BRN-LAS_354-I1-1-2 | BRN-LAS_354-I1-1-2-2.2-System | LAS_354 | 2.2 | Implement a process of automatic data backup | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 30/04/2025 | To be started
BRN | BRN-LAS_354 | BRN-LAS_354-I1-1-2 | BRN-LAS_354-I1-1-2-2.3-Generic | LAS_354 | 2.3 | If automatic backup its not possible, document manual backups of system data with a proper frequency to be defined in a dedicated procedure | Generic | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 30/04/2025 | To be started
BRN | BRN-LAS_354 | BRN-LAS_354-I1-1-2 | BRN-LAS_354-I1-1-2-2.4-System | LAS_354 | 2.4 | Test and document the implemented changes | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 30/04/2025 | To be started
BRN | BRN-LAS_354 | BRN-LAS_354-I1-1-2 | BRN-LAS_354-I1-1-2-2.5-System | LAS_354 | 2.5 | Update relevant SOP | System | 0.2 | 0.2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 30/04/2025 | To be started
BRN | BRN-LAS_354 | BRN-LAS_354-I3-1-3 | BRN-LAS_354-I3-1-3-3.1-System | LAS_354 | 3.1 | Change Control Management including impact assessment | System | 0.5 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 30/04/2025 | To be started
BRN | BRN-LAS_354 | BRN-LAS_354-I3-1-3 | BRN-LAS_354-I3-1-3-3.2-System | LAS_354 | 3.2 | Configure the protection of input data through an automatic security policy or folder restrictions | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 30/04/2025 | To be started
BRN | BRN-LAS_354 | BRN-LAS_354-I3-1-3 | BRN-LAS_354-I3-1-3-3.3-System | LAS_354 | 3.3 | Configure user privileges to prevent the deletion or alteration of input data | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 30/04/2025 | To be started
BRN | BRN-LAS_354 | BRN-LAS_354-I3-1-3 | BRN-LAS_354-I3-1-3-3.4-System | LAS_354 | 3.4 | Test and document the configuration changes | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 30/04/2025 | To be started
BRN | BRN-LAS_354 | BRN-LAS_354-I3-1-3 | BRN-LAS_354-I3-1-3-3.5-System | LAS_354 | 3.5 | Update relevant SOP | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 30/04/2025 | To be started
BRN | BRN-LAS_354 | BRN-LAS_354-T3-2-4 | BRN-LAS_354-T3-2-4-4.1-Generic | LAS_354 | 4.1 | Issue and approve a fully compliant Audit Trail Review Working Instruction | Generic | 0.5 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 30/04/2025 | To be started
BRN | BRN-LAS_354 | BRN-LAS_354-T3-2-4 | BRN-LAS_354-T3-2-4-4.2-System | LAS_354 | 4.2 | Execute Audit Trail Review Working Instruction: - perform Data Assessment for Electronic Records managed by the system - update Operational Method SOP (Methods/Instrument) - update test documentation | System | 0.5 | 2.5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 30/04/2025 | To be started
BRN | BRN-LAS_354 | BRN-LAS_354-T3-2-4 | BRN-LAS_354-T3-2-4-4.3-System | LAS_354 | 4.3 | Setup of periodic task | System | 0.2 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 30/04/2025 | To be started
BRN | BRN-LAS_354 | BRN-LAS_354-VD1-1-5 | BRN-LAS_354-VD1-1-5-5.1-System | LAS_354 | 5.1 | Review the Computer System Validation in place and identify the missing/incomplete validation documents or testing protocols | System | 1 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 30/04/2025 | To be started | Validation Plan not present, Global CSV SOPs not applied., VR (called Qualifizierungsbericht, eng. Qualification report) not complete, URS Document present, however does not reference regulatory requirements (the general 21CFR Part 11 Compliance is present but should be broken down to the specific requirements to meet the expectation). , Not present, partially covered in delivered vendor documentation, Risk assessment not complete, Supplier testing has been performed and it can be leveraged to cover partially the SW configuration, users, privileges, back and access control. Detailed revision shall be performed and the remaining elements tested in additional validation protocol
BRN | BRN-LAS_354 | BRN-LAS_354-VD1-1-5 | BRN-LAS_354-VD1-1-5-5.2-System | LAS_354 | 5.2 | Issue and approve the missing validation documentation | System | 2 | 3 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 30/04/2025 | To be started
BRN | BRN-LAS_354 | BRN-LAS_354-VD1-1-5 | BRN-LAS_354-VD1-1-5-5.3-System | LAS_354 | 5.3 | Perform and document the missing/incomplete tests | System | 3 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 30/04/2025 | To be started
BRN | BRN-LAS_354 | BRN-LAS_354-VD1-1-5 | BRN-LAS_354-VD1-1-5-5.4-System | LAS_354 | 5.4 | Assure the Traceability of the testing with coded requirements against coded test and update the documentation accordingly | System | 2 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 30/04/2025 | To be started
BRN | BRN-LAS_355 | BRN-LAS_355-S4-2-1 | BRN-LAS_355-S4-2-1-1.1-System | LAS_355 | 1.1 | Issue a User List with the actual status of users | System | 0.1 | 0.5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 30/04/2025 | To be started
BRN | BRN-LAS_355 | BRN-LAS_355-S4-2-1 | BRN-LAS_355-S4-2-1-1.2-Generic | LAS_355 | 1.2 | Issue and approve a Periodic Review for User List | Generic | 0.1 | 0.5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 30/04/2025 | To be started
BRN | BRN-LAS_355 | BRN-LAS_355-S4-2-1 | BRN-LAS_355-S4-2-1-1.3-System | LAS_355 | 1.3 | Execute Periodic Review | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 30/04/2025 | To be started
BRN | BRN-LAS_355 | BRN-LAS_355-S4-2-1 | BRN-LAS_355-S4-2-1-1.4-System | LAS_355 | 1.4 | Setup of periodic task in relevant system | System | 0.2 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 30/04/2025 | To be started
BRN | BRN-LAS_355 | BRN-LAS_355-I1-1-2 | BRN-LAS_355-I1-1-2-2.1-System | LAS_355 | 2.1 | Change Control Management including impact assessment | System | 0.5 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 30/04/2025 | To be started
BRN | BRN-LAS_355 | BRN-LAS_355-I1-1-2 | BRN-LAS_355-I1-1-2-2.2-System | LAS_355 | 2.2 | Implement a process of automatic data backup | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 30/04/2025 | To be started
BRN | BRN-LAS_355 | BRN-LAS_355-I1-1-2 | BRN-LAS_355-I1-1-2-2.3-Generic | LAS_355 | 2.3 | If automatic backup its not possible, document manual backups of system data with a proper frequency to be defined in a dedicated procedure | Generic | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 30/04/2025 | To be started
BRN | BRN-LAS_355 | BRN-LAS_355-I1-1-2 | BRN-LAS_355-I1-1-2-2.4-System | LAS_355 | 2.4 | Test and document the implemented changes | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 30/04/2025 | To be started
BRN | BRN-LAS_355 | BRN-LAS_355-I1-1-2 | BRN-LAS_355-I1-1-2-2.5-System | LAS_355 | 2.5 | Update relevant SOP | System | 0.2 | 0.2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 30/04/2025 | To be started
BRN | BRN-LAS_355 | BRN-LAS_355-I3-1-3 | BRN-LAS_355-I3-1-3-3.1-System | LAS_355 | 3.1 | Change Control Management including impact assessment | System | 0.5 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 30/04/2025 | To be started
BRN | BRN-LAS_355 | BRN-LAS_355-I3-1-3 | BRN-LAS_355-I3-1-3-3.2-System | LAS_355 | 3.2 | Configure the protection of input data through an automatic security policy or folder restrictions | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 30/04/2025 | To be started
BRN | BRN-LAS_355 | BRN-LAS_355-I3-1-3 | BRN-LAS_355-I3-1-3-3.3-System | LAS_355 | 3.3 | Configure user privileges to prevent the deletion or alteration of input data | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 30/04/2025 | To be started
BRN | BRN-LAS_355 | BRN-LAS_355-I3-1-3 | BRN-LAS_355-I3-1-3-3.4-System | LAS_355 | 3.4 | Test and document the configuration changes | System | 1 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 30/04/2025 | To be started
BRN | BRN-LAS_355 | BRN-LAS_355-I3-1-3 | BRN-LAS_355-I3-1-3-3.5-System | LAS_355 | 3.5 | Update relevant SOP | System | 0.5 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 30/04/2025 | To be started
BRN | BRN-LAS_355 | BRN-LAS_355-T3-2-4 | BRN-LAS_355-T3-2-4-4.1-Generic | LAS_355 | 4.1 | Issue and approve a fully compliant Audit Trail Review Working Instruction | Generic | 0.5 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 30/04/2025 | To be started
BRN | BRN-LAS_355 | BRN-LAS_355-T3-2-4 | BRN-LAS_355-T3-2-4-4.2-System | LAS_355 | 4.2 | Execute Audit Trail Review Working Instruction: - perform Data Assessment for Electronic Records managed by the system - update Operational Method SOP (Methods/Instrument) - update test documentation | System | 0.5 | 2.5 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 30/04/2025 | To be started
BRN | BRN-LAS_355 | BRN-LAS_355-T3-2-4 | BRN-LAS_355-T3-2-4-4.3-System | LAS_355 | 4.3 | Setup of periodic task | System | 0.2 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 30/04/2025 | To be started
BRN | BRN-LAS_355 | BRN-LAS_355-VD1-1-5 | BRN-LAS_355-VD1-1-5-5.1-System | LAS_355 | 5.1 | Review the Computer System Validation in place and identify the missing/incomplete validation documents or testing protocols | System | 1 | 1 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 30/04/2025 | To be started | Validation Plan not present, Global CSV SOPs not applied., VR (called Qualifizierungsbericht, eng. Qualification report) not complete, URS Document present, however does not reference regulatory requirements (the general 21CFR Part 11 Compliance is present but should be broken down to the specific requirements to meet the expectation). , Not present, partially covered in delivered vendor documentation, Risk assessment not complete, Supplier testing has been performed and it can be leveraged to cover partially the SW configuration, users, privileges, back and access control. Detailed revision shall be performed and the remaining elements tested in additional validation protocol
BRN | BRN-LAS_355 | BRN-LAS_355-VD1-1-5 | BRN-LAS_355-VD1-1-5-5.2-System | LAS_355 | 5.2 | Issue and approve the missing validation documentation | System | 2 | 3 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 30/04/2025 | To be started
BRN | BRN-LAS_355 | BRN-LAS_355-VD1-1-5 | BRN-LAS_355-VD1-1-5-5.3-System | LAS_355 | 5.3 | Perform and document the missing/incomplete tests | System | 3 | 0 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 30/04/2025 | To be started
BRN | BRN-LAS_355 | BRN-LAS_355-VD1-1-5 | BRN-LAS_355-VD1-1-5-5.4-System | LAS_355 | 5.4 | Assure the Traceability of the testing with coded requirements against coded test and update the documentation accordingly | System | 2 | 2 | YES | LES Lab Support | Valeria Geraci | Dario Ruberto | 30/04/2025 | To be started

## Inventory (hidden)
LAS_001 | Broadmeadows | Chemistry
LAS_002 | Broadmeadows | Chemistry
LAS_003 | Broadmeadows | Chemistry
LAS_004 | Broadmeadows | BioChem
LAS_006 | Broadmeadows | BioChem
LAS_007 | Broadmeadows | BioChem
LAS_008 | Broadmeadows | BioChem
LAS_009 | Broadmeadows | Chemistry
LAS_010 | Broadmeadows | Chemistry
LAS_012 | Broadmeadows | BioChem
LAS_013 | Broadmeadows | Chemistry
LAS_014 | Broadmeadows | Chemistry
LAS_015 | Broadmeadows | Chemistry
LAS_016 | Broadmeadows | Chemistry
LAS_017 | Broadmeadows | Chemistry
LAS_018 | Broadmeadows | BioChem
LAS_019 | Broadmeadows | Chemistry
LAS_020 | Broadmeadows | Chemistry
LAS_021 | Broadmeadows | Chemistry
LAS_022 | Broadmeadows | Chemistry
LAS_023 | Broadmeadows | Chemistry
LAS_024 | Broadmeadows | BioChem
LAS_025 | Broadmeadows | BioChem
LAS_026 | Broadmeadows | Chemistry
LAS_027 | Broadmeadows | Chemistry
LAS_028 | Broadmeadows | BioChem
LAS_029 | Broadmeadows | BioChem
LAS_030 | Broadmeadows | BioChem
LAS_031 | Broadmeadows | BioChem
LAS_032 | Broadmeadows | BioChem
LAS_033 | Broadmeadows | BioChem
LAS_034 | Broadmeadows | BioChem
LAS_035 | Broadmeadows | BioChem
LAS_036 | Broadmeadows | Chemistry
LAS_038 | Broadmeadows | Chemistry
LAS_039 | Broadmeadows | Chemistry
LAS_040 | Broadmeadows | Chemistry
LAS_041 | Broadmeadows | Chemistry
LAS_042 | Broadmeadows | Chemistry
LAS_043 | Broadmeadows | Chemistry
LAS_046 | Broadmeadows | Microbiology
LAS_047 | Broadmeadows | BioChem
LAS_048 | Broadmeadows | BioChem
LAS_049 | Broadmeadows | BioChem
LAS_050 | Broadmeadows | BioChem
LAS_052 | Broadmeadows | Chemistry
LAS_055 | Broadmeadows | Chemistry
LAS_056 | Broadmeadows | Chemistry
LAS_057 | Broadmeadows | Chemistry
LAS_059 | Broadmeadows | BioChem
LAS_060 | Broadmeadows | BioChem
LAS_061 | Broadmeadows | Chemistry
LAS_062 | Broadmeadows | Chemistry
LAS_063 | Broadmeadows | Chemistry
LAS_064 | Broadmeadows | Chemistry
LAS_065 | Broadmeadows | Chemistry
LAS_067 | Broadmeadows | Chemistry
LAS_068 | Broadmeadows | Chemistry
LAS_069 | Broadmeadows | Chemistry
LAS_070 | Broadmeadows | Chemistry
LAS_071 | Broadmeadows | Chemistry
LAS_072 | Broadmeadows | Chemistry
LAS_073 | Broadmeadows | Chemistry
LAS_074 | Broadmeadows | Chemistry
LAS_075 | Broadmeadows | Chemistry
LAS_076 | Broadmeadows | Chemistry
LAS_077 | Broadmeadows | BioChem
LAS_078 | Broadmeadows | BioChem
LAS_079 | Broadmeadows | BioChem
LAS_080 | Broadmeadows | BioChem
LAS_081 | Broadmeadows | BioChem
LAS_082 | Broadmeadows | BioChem
LAS_083 | Broadmeadows | Microbiology
LAS_084 | Broadmeadows | Microbiology
LAS_085 | Broadmeadows | Microbiology
LAS_086 | Broadmeadows | BioChem
LAS_087 | Broadmeadows | Non-Production Area
LAS_089 | Broadmeadows | Chemistry
LAS_090 | Broadmeadows | Chemistry
LAS_091 | Broadmeadows | Chemistry
LAS_092 | Broadmeadows | Chemistry
LAS_093 | Broadmeadows | Non-Production Area
LAS_094 | Broadmeadows | Non-Production Area
LAS_095 | Broadmeadows | Non-Production Area
LAS_096 | Broadmeadows | Non-Production Area
LAS_097 | Broadmeadows | Non-Production Area
LAS_098 | Broadmeadows | Non-Production Area
LAS_099 | Broadmeadows | Non-Production Area
LAS_100 | Broadmeadows | Non-Production Area
PCS_001 | 999 PMCS (33A / 33B) | Toll Process
PCS_006 | 110 | Toll Process
PCS_007 | 110 | Toll Process
PCS_008 | 110 | Toll Process
PCS_009 | TOLL / PMCS | Toll Process
PCS_010 | 999 | Toll Process
PCS_011 | 999 | Toll Process
PCS_012 | 999 | Toll Process
PCS_013 | 999 PMCS | Toll Process
PCS_014 | 999 PMCS | Toll Process
PCS_015 | 999 PMCS | Toll Process
PCS_016 | 999 PMCS | Toll Process
PCS_017 | 999 PMCS | Toll Process
PCS_018 | 999 PMCS | Toll Process
PCS_019 | 999 PMCS | Toll Process
PCS_020 | 999 PMCS | Toll Process
PCS_021 | PFF and BMW | Toll Process
PCS_022 | 999 PMCS | BMF Process
PCS_023 | 999 PMCS | BMF Process
PCS_024 | 999 PMCS | BMF Process
PCS_025 | 240 | BMF Process
PCS_026 | 242 | BMF Process
PCS_027 | 287 | BMF Process
PCS_028 | 113 | BMF Process
PCS_029 | 113 | BMF Process
PCS_030 | 113 | BMF Process
PCS_031 | 113 | BMF Process
PCS_033 | 113 | BMF Process
PCS_034 | 113 | BMF Process
PCS_035 | 113 | BMF Process
PCS_036 | 113 | BMF Process
PCS_037 | 113 | BMF Process
PCS_039 | 113 | BMF Process
PCS_040 | 113 | BMF Process
PCS_041 | 113 | BMF Process
PCS_042 | 113 | BMF Process
PCS_043 | 113 | BMF Process
PCS_044 | 113 | BMF Process
PCS_045 | 113 | BMF Process
PCS_046 | 113 | BMF Process
PCS_047 | 113 | BMF Process
PCS_048 | 113 | BMF Process
PCS_049 | 113 | BMF Process
PCS_050 | BMF / PMCS | BMF Process
PCS_051 | 120 | Turner Facility
PCS_052 | 120 | Turner Facility
PCS_055 | Turner / PMCS | Turner Facility
PCS_056 | Turner / PMCS | Turner Facility
PCS_057 | 999 PMCS | Turner Facility
PCS_058 | 999 PMCS | Turner Facility
PCS_059 | 120 | Turner Facility
PCS_060 | Facility A / PMCS | Facility A (AlbuRx) Process
PCS_061 | 999 PMCS | Facility A (AlbuRx) Process
PCS_062 | 999 PMCS | Facility A (AlbuRx) Process
PCS_063 | 999 PMCS | Facility A (AlbuRx) Process
PCS_064 | 999 PMCS | Facility A (AlbuRx) Process
PCS_065 | 999 PMCS | Facility A (AlbuRx) Process
PCS_066 | 461 | Central Services
PCS_067 | 420 | Central Services
PCS_068 | 420 | Central Services
PCS_069 | 420 | Central Services
PCS_070 | 420 | Central Services
PCS_071 | 462 | Central Services
PCS_072 | Common / Utilities | Central Services
PCS_073 | PRIVIGEN Turner Facility | Central Services
PCS_074 | PRIVIGEN Turner Facility | Central Services
PCS_075 | Common / Utilities | Central Services (Tank Farm and Facility F)
PCS_079 | 650 / Utilities | Central Services (Tank Farm and Facility F)
PCS_080 | 650 / Utilities | Central Services (Tank Farm and Facility F)
PCS_081 | 650 / Utilities | Central Services (Tank Farm and Facility F)
PCS_082 | 651 / Utilities | Central Services (Tank Farm and Facility F)
PCS_083 | 651 / Utilities | Central Services (Tank Farm and Facility F)
PCS_084 | 654 / Utilities | Central Services (Tank Farm and Facility F)
PCS_085 | 203 | Filling and Packaging
PCS_086 | 203 | Filling and Packaging
PCS_087 | 203 | Filling and Packaging
PCS_088 | 203 | Filling and Packaging
PCS_089 | 203 | Filling and Packaging
PCS_090 | 203 | Filling and Packaging
PCS_091 | 203 | Filling and Packaging
PCS_092 | 203 | Filling and Packaging
PCS_093 | 203 | Filling and Packaging
PCS_094 | 203 | Filling and Packaging
PCS_095 | 170 | Filling and Packaging
PCS_096 | 170 | Filling and Packaging
PCS_097 | 170 | Filling and Packaging
PCS_098 | 190 | Filling and Packaging
PCS_099 | 203 | Filling and Packaging
PCS_102 | 102 (Dispensing) | Filling and Packaging
PCS_105 | 102 | Filling and Packaging
PCS_113 | 180 | Filling and Packaging
PCS_114 | 180 | Filling and Packaging
PCS_115 | 180 | Filling and Packaging
PCS_116 | 180 | Filling and Packaging
PCS_117 | 180 | Filling and Packaging
PCS_118 | 180 | Filling and Packaging
PCS_119 | 180 | Filling and Packaging
PCS_120 | 103 | Filling and Packaging
PCS_121 | 103 | Filling and Packaging
PCS_124 | 103 (Bottle Preparation) | Filling and Packaging
PCS_127 | 103 | Filling and Packaging
PCS_129 | TOLL / Packaging | Filling and Packaging
PCS_130 | TOLL / Packaging | Filling and Packaging
PCS_136 | 104 | Filling and Packaging
PCS_137 | 104 | Filling and Packaging
PCS_138 | 104 | Filling and Packaging
PCS_139 | 104 | Filling and Packaging
PCS_140 | 104 | Filling and Packaging
PCS_141 | TOLL / Packaging | Filling and Packaging
PCS_142 | TOLL / Packaging | Filling and Packaging
PCS_149 | 205 | Filling and Packaging
PCS_150 | 999 PMCS | Filling and Packaging
PCS_151 | 999 PMCS | Filling and Packaging
PCS_152 | Turner Facility/Facility A | Filling and Packaging
PCS_153 | 377 | Common Systems
PCS_154 | 377 | Common Systems
PCS_155 | 377 | Common Systems
PCS_156 | 377 | Common Systems
PCS_157 | 999 PMCS | Common Systems
PCS_158 | Common / PMCS | Common Systems
PCS_159 | Old Village | Common Systems
PCS_160 | New Village | Common Systems
PCS_161 | TOLL / PMCS | Common Systems
PCS_162 | Utilities, BMF / PMCS | Common Systems
PCS_163 | 301 | Common Systems
PCS_164 | 301 | Common Systems
PCS_165 | 302 | Common Systems
PCS_166 | 303 | Common Systems
PCS_167 | 304 | Common Systems
PCS_168 | 305 | Common Systems
PCS_169 | N/A | Common Systems
PCS_170 | 230 | Q-Fever Process
PCS_171 | 112 | Q-Fever Process
PCS_172 | 112 | Q-Fever Process
PCS_173 | 111 | Laboratories
PCS_175 | 999 / Facility F | Facility F (Base Fractionation Facility) Process
PCS_176 | 999 / Facility F | Facility F (Base Fractionation Facility) Process
PCS_177 | 641 / Pooling | Facility F (Base Fractionation Facility) Process
PCS_178 | 641 / Pooling | Facility F (Base Fractionation Facility) Process
PCS_179 | 641 / Pooling | Facility F (Base Fractionation Facility) Process
PCS_180 | 641 / Pooling | Facility F (Base Fractionation Facility) Process
PCS_181 | 641 / Pooling | Facility F (Base Fractionation Facility) Process
PCS_182 | 641 / Pooling | Facility F (Base Fractionation Facility) Process
PCS_183 | 641 / Pooling | Facility F (Base Fractionation Facility) Process
PCS_184 | 641 / Pooling | Facility F (Base Fractionation Facility) Process
PCS_185 | 641 / Pooling | Facility F (Base Fractionation Facility) Process
PCS_186 | 641 / Pooling | Facility F (Base Fractionation Facility) Process
PCS_188 | 645 / Fractionation | Facility F (Base Fractionation Facility) Process
PCS_189 | 645 / Fractionation | Facility F (Base Fractionation Facility) Process
PCS_190 | 645 / Fractionation | Facility F (Base Fractionation Facility) Process
PCS_191 | 645 / Fractionation | Facility F (Base Fractionation Facility) Process
PCS_192 | 645 / Fractionation | Facility F (Base Fractionation Facility) Process
PCS_193 | 645 / Fractionation | Facility F (Base Fractionation Facility) Process
PCS_194 | 665 / General | Facility F (Base Fractionation Facility) Process
PCS_196 | 645 / Fractionation | Facility F (Base Fractionation Facility) Process
PCS_197 | 645 / Fractionation | Facility F (Base Fractionation Facility) Process
PCS_198 | 642 / DEAE (PC) Elution | Facility F (Base Fractionation Facility) Process
PCS_199 | 642 / DEAE (PC) Elution | Facility F (Base Fractionation Facility) Process
PCS_200 | 642 / DEAE (PC) Elution | Facility F (Base Fractionation Facility) Process
PCS_201 | Toll Facility | Filling line 6
PCS_202 | Toll Facility | Filling line 6
PCS_203 | Toll Facility | Filling line 6
PCS_204 | Toll Facility | Filling line 6
PCS_205 | Toll Facility | Autoclave 15
PCS_206 | Toll Facility | Motus trayoff unit
PCS_207 | Toll Facility | Toll/Filling line 6
PCS_208 | Toll Facility | Toll/Filling line 6
PCS_209 | Toll Facility | Toll/Filling line 6
PCS_210 | AlbuRX facility (A) | Filling
PCS_211 | AlbuRX facility (A) | Bulk
PCS_212 | AlbuRX facility (A) | Filling
PCS_213 | AlbuRX facility (A) | Bulk
PCS_214 | AlbuRX facility (A) | Bulk
PCS_215 | CSL BMW | Qualification/Requalification Department
PCS_216 | CSL BMW | Qualification/Requalification Department
PCS_217 | CSL BMW | Qualification/Requalification Department
PCS_218 | CSL BMW | Qualification/Requalification Department
PCS_219 | CSL BMW | Qualification/Requalification Department
PCS_220 | CSL BMW | Qualification/Requalification Department
PCS_221 | CSL BMW | Qualification/Requalification Department
PCS_222 | 203 | Filling and Packaging
PCS_223 | BMF Process | Filling and Packaging
PCS_224 | BMF Process | Filling and Packaging
PCS_225 | BMF Process | Filling and Packaging
PCS_242 | BMF Process | Filling and Packaging
PCS_243 | BMF Process | Filling and Packaging
PCS_244 | BMF Process | Filling and Packaging
PCS_245 | BMF Process | Filling and Packaging
PCS_246 | BMF Process | Filling and Packaging
PCS_247 | BMF Process | Filling and Packaging
PCS_248 | BMF Process | Filling and Packaging
PCS_249 | BMF Process | Filling and Packaging
PCS_250 | BMF Process | Filling and Packaging
PCS_251 | BMF Process | Filling and Packaging
PCS_252 | BMF Process | Filling and Packaging
PCS_253 | BMF Process | Filling and Packaging
PCS_254 | BMF Process | Filling and Packaging
PCS_255 | BMF Process | Filling and Packaging
PCS_256 | 642 / DEAE (PC) Elution | Facility F (Base Fractionation Facility) Process

## CSL Groups (hidden)
QC Chemistry
QC Biochemistry
QC Microbiology
QC Sample Management
QC Excellence
QC Analytical Technology
LES Lab Support
LES Supporting Systems
Fractionation
Execution Systems - Frac
Bulk
Execution Systems - Bulk
Biotechnology
Execution Systems - Biotechnology
Filling
Execution Systems - Filling
Visual Inspection
Execution Systems - Visual Inspection
Packaging
Execution Systems - Packaging
I & T
CSV