## Slide 1: Changeover process map | future state (1/2)
Start
ASO 1
Filler Techni-cian 1
Filler Techni-cian 2
QAO / Super-visor
Notified of machine availability time
Support (incl. support to clean isolator)
ASO 2
Seal door and start SCADA
5 min.
Assist in VHP Sign-off
5 min.
Reconcile EOF
5 min.
VHP sign off
5 min.
Seal door and start SCADA
5 min.
Assist in VHP Sign-off
5 min.
Remove Fill Assembly
10 min.
Remove format parts from Capper
10 min.
Capper C/O
10 min.
Finalize VHP prep work (e.g. sic sensor barriers)
10 min.
Remove Fill Assembly
10 min.
Remove Fill Assembly
10 min.
Remove format parts from Capper
10 min.
Capper C/O
10 min.
Finalize VHP prep work (e.g. sic sensor barriers)
10 min.
Pre fill Glove IT test 15 min.
Pre fill Glove IT test 15 min.
Assist in finalize VHP prep work (e.g. sic sensor barriers)
15 min.
Close out Fill paper-work
10 min.
Pre fill Glove IT test 15 min.
Install format Part & stoppering equipment
35 min.
Empty out tunnel of glass
30 min.
Final glove preparation
30 min.
Empty out tunnel of glass
30 min.
Post fill Glove IT test 25 min.
Final glove preparation
30 min.
Alcohol wipe and install glove extenders on tested gloves
30 min.
Final glove preparation
30 min.
Alcohol wipe and install glove extenders on tested gloves
30 min.
Install VHP load parts
30 min.
Manual cleaning Inspection
30 min.
Empty out tunnel of glass
30 min.
Final glove preparation
30 min.
Break
35 min.
Empty out tunnel of glass
40 min.
End of Fill plating
45 min.
Disassemble Isolator and clean
30 min.
Sanitization/Steri-perox Isolator
30 min.
End of Fill plating
45 min.
Disassemble Isolator and clean
30 min.
Sanitization/Steri-perox Isolator
30 min.
End of Fill plating
45 min.
Disassemble Isolator and clean
30 min.
Sanitization/Steri-perox Isolator
30 min.
End of Fill plating
45 min.
Disassemble Isolator and clean
30 min.
Sanitization/Steri-perox Isolator
30 min.
Pre-VHP dry run
20 min.
Disassemble Isolator and clean
30 min.
Sanitization/Steri-perox Isolator
30 min.
Preliminary – For Discussion
5 hrs. 15 min

## Slide 2: Changeover process map | future state (2/2)
End
Vial Washer/tunnel Loading
ASO 1
Filler Techni-cian 1
Filler Techni-cian 2
Support (incl. support to clean isolator)
ASO 2
Pre check washer and start
5 min.
Monitor Isolator SMA plates
5 min.
Monitor Isolator SMA plates
5 min.
Complete post filter test docume-ntation 5 min.
Pre fill sign off
5 min.
Post VHP sign off and post VHP visual glove inspection
5 min.
Pre fill sign off
5 min.
Pre check washer and start
5 min.
Take out glove extenders
10 min.
Complete equipment log-in and document-tation (e.g., fill assembly, stopper)
10 min.
Soak the filters
10 min.
Instal post VHP format parts
10 min.
Setup Test Vials
10 min.
1. Check load cells with scale
2. Fill needle setup
15 min.
Fill assembly prepping and docking
15 min.
Hand needles to ASO 15 min.
Instal post VHP format parts
10 min.
Setup Test Vials
10 min.
1. Check load cells with scale
2. Fill needle setup
15 min.
Aseptic Connection and Hold time
25 min.
Aseptic Connection and Hold time
25 min.
Filter testing (***Monitor the times on new tester when RTO) 25 min.
Vial washer Changeover
60 min.
Big Room Sanitation 30 min.
Big Room Sanitation 30 min.
Vial washer Changeover
60 min.
VHP
210 min.
VHP
210 min.
QAO / Super-visor
Big Room Sanitation 30 min.
Preliminary – For Discussion
10 hrs. 30 min (total)

## Slide 3
Process
Name of process
Created by
Modiby
Total hrs

## Slide 4
Department Type
Type : Aso techn …
Created by
Modiby

## Slide 5
Task Type
Task Name Task time Task description Created by
Modiby

## Slide 6
User
User Name : Nehul Department : ASO starting time : 7
Created by
Modiby

## Slide 7
Change over Process Mapping List
Process Name : change over process 1 ( dropdown) Process time : time from process list - text Username : Nehul ( dropdown) Department : automatic from user list starting time : from user list Select Task ( Combobox multi select)
Created by
Modiby

## Slide 8
Basic Layout Screen
With progress bar

## Slide 9
Green tile Layout Screen
With progress bar